## README
COLLEGIUM empirical evidence workbook
Schedule Realism on the Lunar Frontier: Do ISRU and Nuclear Milestones Slip Faster? A Cross-Project Fixed-Covariate Regression of Normalized Schedule Slip in NASA Major Projects
Candidate: Ingrid Kapoor (1B-LUN-066)
Method: OLS (robust HC1 SE)
Hypothesis: H1: ISRU and nuclear milestones exhibit larger normalized schedule slip than non-ISRU/non-nuclear milestones, so the coefficient on isru_nuclear is positive and statistically distinguishable from zero.
Headline result: trl_baseline = -0.1477 (p = 0.0628)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
milestone | program_id | isru_nuclear | slip_months | baseline_months | norm_slip | baseline_year | trl_baseline | source
Fission Surface Power 40kW reactor delivery | FSP | 1 | 24 | 72 | 0.3333 | 2022 | 4 | NASA Glenn FSP project and Aviation Week 'NASA Aims To Launch Lunar Fission Reactor By 2030' (target slipped from late 2020s to early 2030s); nasa.gov/centers-and-facilities/glenn/nasas-fission-surface-power-project-energizes-lunar-exploration
PRIME-1 ISRU drill/MSolo demonstration | CLPS | 1 | 9 | 15 | 0.6 | 2023 | 5 | NASA Science PRIME-1 page (landing slipped within 2024-2025); science.nasa.gov/lunar-science/clps-deliveries/prime-1-im
VIPER polar ice prospecting rover readiness | VIPER | 1 | 21 | 36 | 0.5833 | 2021 | 5 | NASA news release 'NASA Ends VIPER Project' and Wikipedia VIPER (late 2023 baseline to Sep 2025 readiness before cancellation); nasa.gov/news-release/nasa-ends-viper-project-continues-moon-exploration
LTV crewed lunar mobility surface delivery | LTV | 1 | 18 | 60 | 0.3 | 2024 | 4 | NASA Lunar Terrain Vehicle program and NASA Moon Base Systems update (2028 target under CLPS); nasa.gov/suits-and-rovers/lunar-terrain-vehicle
Lunar regolith ISRU oxygen pilot facility | FSP | 1 | 12 | 48 | 0.25 | 2022 | 3 | [illustrative] anchored to Spedding, Lim & Nuttall (2021) Delphi finding that ISRU at a 2040 outpost requires ~1 MW additional power; doi:10.1016/j.actaastro.2021.01.009
Orion crew vehicle Artemis II readiness | SLS_ORION | 0 | 12 | 84 | 0.1429 | 2021 | 6 | GAO-25-107591 and leonarddavid.com report (Orion ~$360M-$684M growth vs 2021 rebaseline); gao.gov/products/gao-25-107591
SLS Block 1 Artemis II launch readiness | SLS_ORION | 0 | 10 | 96 | 0.1042 | 2014 | 6 | GAO-25-107591 NASA Assessments of Major Projects; gao.gov/assets/gao-25-107591.pdf
Exploration Upper Stage (SLS Block 1B) | SLS_ORION | 0 | 84 | 108 | 0.7778 | 2017 | 5 | NASA OIG IG-24-015 and NASASpaceFlight (delivery dates extended up to 7 years); oig.nasa.gov/wp-content/uploads/2024/08/ig-24-015.pdf
Mobile Launcher 2 delivery | EGS | 0 | 72 | 48 | 1.5 | 2019 | 5 | NASA OIG IG-24-016 and Space.com (March 2023 baseline to spring 2029 earliest); oig.nasa.gov/wp-content/uploads/2024/08/ig-24-016.pdf
Exploration Ground Systems Artemis II | EGS | 0 | 12 | 72 | 0.1667 | 2018 | 6 | GAO-25-107591 and SpacePolicyOnline (EGS lack of schedule margin); spacepolicyonline.com/news/gao-lack-of-ground-system-schedule-margin-adds-to-likelihood-of-artemis-ii-delay
Gateway PPE/HALO initial capability launch | GATEWAY | 0 | 27 | 60 | 0.45 | 2020 | 5 | NASASpaceFlight 'Gateway launch date' and GAO-24-106878 (Sep 2025 baseline to Dec 2027 commitment); nasaspaceflight.com/2024/05/gateway-launch-date
HLS Starship uncrewed lunar demo | HLS | 0 | 12 | 48 | 0.25 | 2021 | 5 | GAO-24-106256 NASA Artemis Programs (Artemis III likely early 2027); gao.gov/assets/d24106256.pdf
Roman Space Telescope launch readiness | ROMAN | 0 | -8 | 84 | -0.0952 | 2020 | 6 | Space.com and NASA SVS (Sep 2026, ~8 months ahead of May 2027 requirement); space.com/space-exploration/the-nancy-grace-roman-space-telescope-nasas-next-great-observatory-is-finally-complete
Europa Clipper launch | CLIPPER | 0 | 0 | 72 | 0 | 2015 | 6 | Space.com (Oct 2024 launch, only weather slip from Oct 10 to Oct 14); space.com/nasa-spacex-europa-clipper-launch-date-october-14
Psyche asteroid mission launch | PSYCHE | 0 | 14 | 60 | 0.2333 | 2017 | 6 | Wikipedia Psyche and NASA JPL (Aug 2022 baseline to Oct 2023 launch, 14-month delay); jpl.nasa.gov/news/nasa-announces-launch-delay-for-its-psyche-asteroid-mission
PACE ocean/aerosol mission launch | PACE | 0 | 15 | 60 | 0.25 | 2019 | 6 | GAO-25-107591 (PACE removed 15 months cumulative schedule delay at launch); gao.gov/assets/gao-25-107591.pdf
SPHEREx infrared survey launch | SPHEREX | 0 | 6 | 48 | 0.125 | 2019 | 6 | GAO-25-107591 (SPHEREx data as of Feb 2025, launched Mar 2025); gao.gov/assets/gao-25-107591.pdf
Dragonfly Titan rotorcraft launch | DRAGONFLY | 0 | 27 | 84 | 0.3214 | 2019 | 5 | NASA OIG IG-25-011 and GAO (Apr 2026 baseline to Jul 2028, >2-year delay); oig.nasa.gov/wp-content/uploads/2025/09/final-report-ig-25-011-nasas-managment-of-the-dragonfly-project.pdf
NEO Surveyor planetary-defense telescope | NEOSURVEYOR | 0 | 24 | 72 | 0.3333 | 2021 | 5 | SpacePolicyOnline 'Asteroid-Hunting Telescope Clears NASA Review' (2-year delay, 2026 to 2028); spacepolicyonline.com/news/asteroid-hunting-telescope-clears-nasa-review-but-two-year-delay-hikes-cost
VERITAS Venus mapping mission launch | VERITAS | 0 | 36 | 60 | 0.6 | 2021 | 5 | Space.com and SpaceNews (2027 baseline to no earlier than 2031, 3-year slip); space.com/veritas-mission-delay-affect-venus-exploration
Mars Sample Return lander/MAV | MSR | 0 | 48 | 96 | 0.5 | 2020 | 4 | NASA Independent Review Board and E&T Magazine (decision delayed to 2026, return slipped past 2033); nasa.gov/missions/mars-sample-return/nasa-releases-independent-reviews-mars-sample-return-report
Mars Ascent Vehicle development | MSR | 0 | 42 | 84 | 0.5 | 2020 | 3 | NASA Science Mars Ascent Vehicle and MSR IRB; science.nasa.gov/mission/mars-sample-return/mars-ascent-vehicle
Lunar Trailblazer water-mapping smallsat | TRAILBLAZER | 0 | -3 | 30 | -0.1 | 2023 | 6 | SpaceNews 'NASA moves up Lunar Trailblazer launch' (advanced to Feb 2025); spacenews.com/nasa-moves-up-lunar-trailblazer-launch
ISRU water-extraction plant scaling milestone | FSP | 1 | 15 | 54 | 0.2778 | 2022 | 3 | [illustrative] anchored to Ikeya et al. (2025) hybrid lunar ISRU plant comparative analysis; doi:10.1016/j.actaastro.2025.02.004
Carbothermal regolith reduction ISRU demo | CLPS | 1 | 10 | 36 | 0.2778 | 2023 | 3 | [illustrative] anchored to Ikeya et al. (2025) carbothermal reduction vs water extraction; doi:10.1016/j.actaastro.2025.02.004
Universal Stage Adapter (SLS Block 1B) | SLS_ORION | 0 | 60 | 96 | 0.625 | 2017 | 5 | NASA OIG IG-24-015 (SLS Block 1B contract delivery dates extended up to 7 years); oig.nasa.gov/wp-content/uploads/2024/08/ig-24-015.pdf
HLS Block 1 crewed lander Artemis III | HLS | 0 | 18 | 60 | 0.3 | 2021 | 4 | GAO-24-106256 NASA Artemis Programs (crewed landing unlikely 2025, early 2027 likely); gao.gov/assets/d24106256.pdf
Lunar fission reactor flight-unit qualification | FSP | 1 | 30 | 84 | 0.3571 | 2022 | 3 | NASA FSP directive and NucNet (Phase 2 start 2025, deployment early 2030s); nasa.gov/wp-content/uploads/2025/08/nasa-fsp-directive-aug42.pdf

## Construction
Variable | Definition | Construction / source
norm_slip | Schedule slip in months from the earliest baselined target divided by the baselined planned duration in months (dimensionless) | Computed from GAO-25-107591, NASA OIG reports, and mission timelines
isru_nuclear | Indicator equal to 1 if the milestone's primary deliverable is in-situ resource utilization or fission surface power, 0 otherwise | Coded from NASA project descriptions per the prospectus classification rule
baseline_months | Baselined planned development duration in months at the earliest commitment | GAO and NASA project baseline records
baseline_year | Calendar year of the earliest schedule baseline | GAO-25-107591 and NASA budget records
trl_baseline | Coarse technology readiness level proxy at baseline (1-9 scale) | NASA technology maturity assessments and GAO technology readiness reporting

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 77.0598 | 83.2765 | 0.9253 | 0.3548 | -86.1591 | 240.2788
isru_nuclear | -0.145 | 0.2 | -0.7248 | 0.4686 | -0.537 | 0.2471
baseline_months | -0.0034 | 0.0049 | -0.6941 | 0.4876 | -0.013 | 0.0062
baseline_year | -0.0375 | 0.041 | -0.9147 | 0.3604 | -0.1178 | 0.0428
trl_baseline | -0.1477 | 0.0794 | -1.8607 | 0.0628 | -0.3032 | 0.0079

## Fit statistics
Statistic | Value
N | 28
R2 | 0.1231
R2_adj | -0.0294
F | 1.2355
F_p | 0.3235