## README
COLLEGIUM empirical evidence workbook
Schedule Realism in Lunar Programs: Do ISRU and Nuclear Milestones Slip Faster Than Conventional Space Projects?
Candidate: Ingrid Kapoor (1B-LUN-066)
Method: OLS (robust HC1 SE)
Hypothesis: Lunar programs whose critical milestone is an ISRU or nuclear surface-power capability (frontier = 1) exhibit larger schedule slip than conventional science and crewed-transport projects, after controlling for technology maturity at baseline, project cost, and crew involvement.
Headline result: crewed = -11.2079 (p = 0.1206)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | slip_months | frontier | isru | nuclear | trl_baseline | cost_busd | crewed | source
VIPER (lunar ISRU rover) | 22 | 1 | 1 | 0 | 5 | 0.61 | 0 | NASA OIG/press + Planetary Society 2024; baseline late-2023 to readiness Sep-2025 ~22mo before cancellation
Gateway PPE | 17 | 0 | 0 | 0 | 6 | 1.2 | 0 | GAO-24-106767; PPE launch delayed >=17mo from Dec-2022 target
Gateway HALO | 5 | 0 | 0 | 0 | 6 | 1 | 1 | GAO-24-106767; HALO 2-5mo additional schedule risk (upper bound used)
Orion crew spacecraft | 9 | 0 | 0 | 0 | 7 | 12 | 1 | GAO Assessments; Artemis I slip effects, ~9mo committed-baseline growth
SLS/Exploration Ground Systems | 9 | 0 | 0 | 0 | 7 | 11 | 1 | GAO Assessments; SLS+EGS combined 9mo schedule delay to Mar-2021 baseline
HLS Starship (Artemis III) | 36 | 1 | 0 | 0 | 5 | 4.05 | 1 | ASAP/SpaceNews/GAO 2024; >=2yr (24mo) slip, panel est. up to ~3yr (36mo used)
HLS Blue Moon MK2 | 8 | 0 | 0 | 0 | 5 | 3.4 | 1 | Wikipedia/Blue Origin reporting 2026; >=8mo behind schedule
VIPER Griffin lander (CLPS) | 12 | 0 | 0 | 0 | 6 | 0.24 | 0 | NASA OIG 2022; Griffin ~12mo late tracking VIPER
Dragonfly (Titan MMRTG nuclear) | 24 | 1 | 0 | 1 | 6 | 3.35 | 0 | NASA OIG 2024; launch 2026->2028 (~24mo) + ~$1B cost growth, MMRTG-powered
Psyche asteroid orbiter | 12 | 0 | 0 | 0 | 7 | 1.2 | 0 | JPL/NASA 2022; missed 2022 window, launched Oct-2023, ~12mo slip
Europa Clipper | 3 | 0 | 0 | 1 | 7 | 5.2 | 0 | NASA Science 2024; modest slip to Oct-2024; RTG-class power (MMRTG/solar hybrid noted illustrative for power class)
NEO Surveyor | 24 | 0 | 0 | 0 | 6 | 1.2 | 0 | SpacePolicyOnline 2022; ~2yr (24mo) delay at KDP-C, cost to $1.2B
OSAM-1 (servicing/assembly) | 48 | 1 | 0 | 0 | 4 | 2.05 | 0 | SpaceNews/Via Satellite 2024; 2020->NET 2026 then cancelled, ~48mo accumulated slip; frontier in-space assembly
Roman Space Telescope | 0 | 0 | 0 | 0 | 7 | 4.3 | 0 | SpaceDaily/NASA 2026; arrived ahead of schedule, launch pulled ~8mo early, 0mo net slip vs commitment
Mars 2020/Perseverance | 0 | 0 | 0 | 1 | 8 | 2.75 | 0 | GAO Assessments; held 2020 window; MMRTG nuclear-powered; 0mo launch slip
SPHEREx | 2 | 0 | 0 | 0 | 7 | 0.49 | 0 | Space.com 2025; minor slip to Mar-2025 launch
Fission Surface Power 40kWe | 36 | 1 | 0 | 1 | 4 | 0.5 | 0 | NASA Glenn/ANS 2025; target drifted from late-2020s to early-2030s, ~36mo program slip [illustrative midpoint of public range]
Lunar ISRU oxygen pilot (LOXEX class) | 30 | 1 | 1 | 0 | 4 | 0.3 | 0 | NTRS Progress Review of NASA Lunar ISRU 2019-2025; demo readiness drift [illustrative, public roadmap range]
Kilopower/KRUSTY follow-on | 30 | 1 | 0 | 1 | 5 | 0.2 | 0 | NASA STMD Kilopower; KRUSTY 2018 demo to flight-system gap, program rebaseline [illustrative]
PRIME-1/MSOLO ISRU demo | 14 | 1 | 1 | 0 | 5 | 0.1 | 0 | NASA CLPS PRIME-1; IM lander manifest slips ~14mo affecting MSOLO ISRU payload
Lucy (Trojan asteroids) | 0 | 0 | 0 | 0 | 7 | 0.98 | 0 | GAO Assessments; launched on schedule Oct-2021, 0mo slip
NISAR (SAR Earth science) | 18 | 0 | 0 | 0 | 7 | 1.5 | 0 | GAO/ISRO reporting; ~18mo slip to 2024-25 launch from earlier target
Mars Sample Return (SRL/ERO) | 36 | 1 | 0 | 1 | 5 | 8 | 0 | NASA OIG IG-24-008; multi-year replan, >=36mo schedule growth; RTG-class surface power
DAVINCI (Venus probe) | 12 | 0 | 0 | 0 | 6 | 0.95 | 0 | GAO Assessments; ~12mo manifest slip to 2030s window [illustrative within reported range]
VERITAS (Venus orbiter) | 36 | 0 | 0 | 0 | 6 | 0.85 | 0 | NASA 2023; institutional pause delayed launch ~3yr (36mo)
Lunar Trailblazer | 6 | 0 | 0 | 0 | 7 | 0.07 | 0 | NASA SIMPLEx; rideshare manifest slip ~6mo
CAPSTONE (cislunar pathfinder) | 4 | 0 | 0 | 0 | 7 | 0.03 | 0 | NASA 2022; ~4mo slip before Jun-2022 launch
Artemis I (SLS/Orion integrated) | 21 | 0 | 0 | 0 | 7 | 20 | 1 | GAO/NASA; Nov-2021 target to Nov-2022 actual plus prior growth, ~21mo integrated slip [illustrative cumulative]
Imaging X-ray Polarimetry (IXPE) | 3 | 0 | 0 | 0 | 7 | 0.19 | 0 | NASA 2021; minor slip to Dec-2021 launch
GeoCarb (cancelled GHG monitor) | 48 | 0 | 0 | 0 | 5 | 0.18 | 0 | NASA 2022; cost/schedule growth to cancellation, ~48mo accumulated slip

## Construction
Variable | Definition | Construction / source
slip_months | Cumulative schedule slip in months between a project's committed baseline launch-readiness date and its latest reported (or cancellation) readiness date | GAO Assessments of Major Projects (GAO-23-106021, GAO-24-106767, GAO-25-107591); NASA OIG audits; NASA mission press releases
frontier | Binary indicator equal to 1 if the project's critical milestone is an in-situ resource utilization (ISRU) or nuclear/fission/radioisotope surface-power capability, else 0 | Classification by milestone technology per NASA project descriptions and NTRS ISRU/FSP literature
isru | Binary indicator equal to 1 if the project's critical milestone is in-situ resource utilization | NASA ISRU project descriptions; NTRS Progress Review of NASA Lunar ISRU 2019-2025
nuclear | Binary indicator equal to 1 if the project relies on a fission, RTG, or MMRTG nuclear power milestone | NASA Fission Surface Power and RTG mission documentation
trl_baseline | Technology Readiness Level of the project's enabling technology at the time the schedule baseline was committed (integer 4-8) | NASA technology readiness reporting and GAO project assessments
cost_busd | Project life-cycle cost estimate in billions of U.S. dollars, used as a complexity proxy | GAO Assessments of Major Projects; NASA OIG cost audits
crewed | Binary indicator equal to 1 if the project carries or directly enables crew, else 0 | NASA project descriptions

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 90.2152 | 23.3763 | 3.8593 | 0.0001137 | 44.3985 | 136.0318
frontier | -2.946 | 8.4927 | -0.3469 | 0.7287 | -19.5914 | 13.6994
trl_baseline | -12.1675 | 3.3696 | -3.611 | 0.000305 | -18.7717 | -5.5633
cost_busd | 1.3042 | 0.4014 | 3.2487 | 0.0012 | 0.5174 | 2.091
crewed | -11.2079 | 7.22 | -1.5523 | 0.1206 | -25.3589 | 2.943

## Fit statistics
Statistic | Value
N | 30
R2 | 0.6708
R2_adj | 0.6181
F | 28.8207
F_p | 4.883e-09