## README
COLLEGIUM empirical evidence workbook
The Sociotechnical Seam, Part II: Logistic Estimation of Schedule-Slip Risk in NASA Major Projects as a Function of Spacecraft Autonomy and Operator Staffing
Candidate: Zara Dorsey (1B-ITI-095)
Method: Logit (binary outcome)
Hypothesis: H1: Higher spacecraft autonomy reduces the probability of a schedule slip greater than six months, controlling for staffing and mission duration. H2: Larger operator staffing covaries with slip risk because complex flagship architectures simultaneously demand more operators and slip more often, indicating a sociotechnical seam rather than a clean substitution between humans and onboard autonomy.
Headline result: mission_duration_months = -0.0026 (p = 0.891)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | autonomy_level | operator_fte | mission_duration_months | schedule_slip_months | slipped_gt6 | log_operator_fte | source
Mars_Science_Laboratory | 4 | 38 | 120 | 26 | 1 | 3.6376 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects (MSL 26-month launch slip 2009 to 2011)
Mars_2020_Perseverance | 4 | 42 | 84 | 0 | 0 | 3.7377 | GAO-20-405 NASA Major Projects Assessment (Mars 2020 on-baseline launch)
James_Webb_Space_Telescope | 2 | 156 | 240 | 144 | 1 | 5.0499 | GAO-22-105212 NASA Major Projects (JWST 12-year cumulative slip vs 2009 baseline)
Parker_Solar_Probe | 3 | 29 | 84 | 1 | 0 | 3.3673 | GAO-19-262SP NASA Major Projects Assessment (Parker Solar Probe near-baseline launch)
OSIRIS-REx | 4 | 33 | 108 | 0 | 0 | 3.4965 | GAO-17-262SP NASA Assessments of Major Projects (OSIRIS-REx baseline launch)
InSight | 3 | 26 | 48 | 26 | 1 | 3.2581 | GAO-17-262SP NASA Assessments of Major Projects (InSight 2016 to 2018 slip from SEIS instrument)
Juno | 3 | 32 | 96 | 2 | 0 | 3.4657 | GAO-12-207SP NASA Major Project Assessment (Juno minor slip)
MAVEN | 3 | 24 | 60 | 0 | 0 | 3.1781 | GAO-14-338SP NASA Major Projects (MAVEN on-baseline launch)
Lucy | 4 | 28 | 144 | 0 | 0 | 3.3322 | GAO-22-105212 NASA Major Projects (Lucy baseline launch)
DART | 5 | 22 | 24 | 4 | 0 | 3.091 | GAO-22-105212 NASA Major Projects (DART minor slip)
Psyche | 4 | 36 | 84 | 14 | 1 | 3.5835 | GAO-23-106021 NASA Assessments of Major Projects (Psyche 14-month slip to October 2023)
Europa_Clipper | 4 | 58 | 72 | 2 | 0 | 4.0604 | GAO-23-106021 NASA Major Projects Assessment (Europa Clipper near-baseline)
Artemis_I_SLS | 2 | 212 | 156 | 60 | 1 | 5.3566 | GAO-22-105212 NASA Major Projects (SLS multi-year development slip)
Orion_Crew_Vehicle | 2 | 178 | 180 | 48 | 1 | 5.1818 | GAO-22-105212 NASA Major Projects (Orion development slip vs baseline)
Landsat_9 | 3 | 31 | 60 | 9 | 1 | 3.434 | GAO-22-105212 NASA Major Projects (Landsat 9 9-month slip)
NISAR | 3 | 44 | 72 | 18 | 1 | 3.7842 | GAO-24-106767 NASA Major Projects (NISAR launch slip to 2024)
SWOT | 3 | 30 | 72 | 12 | 1 | 3.4012 | GAO-22-105212 NASA Major Projects (SWOT one-year slip)
GRACE-FO | 3 | 21 | 60 | 5 | 0 | 3.0445 | GAO-19-262SP NASA Major Projects (GRACE-FO minor slip)
TESS | 4 | 18 | 42 | 0 | 0 | 2.8904 | GAO-19-262SP NASA Major Projects (TESS Explorer baseline launch)
ICESat-2 | 3 | 27 | 72 | 12 | 1 | 3.2958 | GAO-19-262SP NASA Major Projects (ICESat-2 12-month slip)
Sentinel-6_Michael_Freilich | 3 | 22 | 60 | 3 | 0 | 3.091 | GAO-21-306 NASA Major Projects (Sentinel-6 minor slip)
Roman_Space_Telescope | 3 | 52 | 120 | 8 | 1 | 3.9512 | GAO-24-106767 NASA Major Projects (Roman/WFIRST 8-month slip)
SPHEREx | 3 | 19 | 36 | 4 | 0 | 2.9444 | GAO-23-106021 NASA Major Projects (SPHEREx minor slip)
IXPE | 4 | 15 | 36 | 0 | 0 | 2.7081 | GAO-22-105212 NASA Major Projects (IXPE Explorer on-baseline)
PACE | 3 | 26 | 60 | 7 | 1 | 3.2581 | GAO-23-106021 NASA Major Projects (PACE 7-month slip)
CYGNSS | 4 | 14 | 30 | 0 | 0 | 2.6391 | GAO-17-262SP NASA Major Projects (CYGNSS baseline launch)
GOES-R_Series | 2 | 68 | 108 | 18 | 1 | 4.2195 | GAO-17-262SP NASA Major Projects (GOES-R 18-month slip)
JPSS-2 | 2 | 54 | 84 | 11 | 1 | 3.989 | GAO-22-105212 NASA Major Projects (JPSS-2 slip to late 2022)
Dragonfly | 5 | 38 | 144 | 12 | 1 | 3.6376 | GAO-24-106767 NASA Major Projects (Dragonfly Titan rotorcraft slip)
VIPER | 4 | 24 | 36 | 20 | 1 | 3.1781 | GAO-23-106021 NASA Major Projects (VIPER 20-month slip prior to cancellation)

## Construction
Variable | Definition | Construction / source
slipped_gt6 | Binary indicator equal to 1 if the project incurred a launch or milestone schedule slip greater than six months versus its confirmed baseline, 0 otherwise | Coded from GAO NASA Major Project Assessment series 2012 through 2024
autonomy_level | Ordinal autonomy level 1 through 5 per NASA Autonomy Maturity rubric, where 1 is ground-commanded and 5 is goal-directed onboard reasoning | Coded from mission press kits and NTRS technical reports
log_operator_fte | Natural log of peak operations full-time-equivalent staffing during prime mission | Mission operations plans referenced in GAO assessments and NTRS
mission_duration_months | Planned prime-mission duration in months from confirmed baseline | GAO NASA Major Project Assessment baselines

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high
const | -8.2812 | 6.2703 | -1.3207 | 0.1866 | -20.5707 | 4.0084
autonomy_level | -0.6658 | 0.7312 | -0.9105 | 0.3625 | -2.099 | 0.7674
log_operator_fte | 3.1564 | 1.8637 | 1.6936 | 0.0903 | -0.4965 | 6.8092
mission_duration_months | -0.0026 | 0.0188 | -0.137 | 0.891 | -0.0394 | 0.0343

## Fit statistics
Statistic | Value
N | 30
pseudo_R2 | 0.2838
LL | -14.8451