## README
COLLEGIUM empirical evidence workbook
Does a Documented Architecture Baseline Predict Cost Growth? Evidence from NASA Major Projects
Candidate: Emeka Larsson (1B-MPM-046)
Method: OLS (robust HC1 SE)
Hypothesis: Documented-architecture maturity is hypothesized to carry a negative coefficient (more mature documented baselines, lower cost growth); schedule delay is expected positive and program size negative.
Headline result: months_delay = 1.8711 (p = 4.357e-08)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | year_confirmed | log_dev_cost | conf_to_cdr_months | arch_maturity | months_delay | dev_cost_growth_pct | source
DART | 2018 | 5.5541 | 10 | 1 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Europa Clipper | 2019 | 7.7885 | 12 | 1 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
EGS | 2014 | 7.5194 | 15 | 1 | 28 | 26.3 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
JWST | 2008 | 7.856 | 20 | 0 | 81 | 94.7 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Landsat 9 | 2017 | 6.4524 | 4 | 2 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
LCRD | 2017 | 4.5196 | -4 | 2 | 14 | 40 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
LBFD | 2018 | 4.6102 | 10 | 1 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Lucy | 2018 | 6.4333 | 12 | 1 | 0 | -1.3 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Mars 2020 | 2016 | 7.4247 | 8 | 1 | 0 | 21.4 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
NISAR | 2016 | 6.4938 | 26 | 0 | 0 | -3.1 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Orion | 2015 | 8.82 | 1 | 2 | 0 | 13.6 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
PACE | 2019 | 6.3244 | 6 | 1 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
Psyche | 2019 | 6.5249 | 12 | 1 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
SLS | 2014 | 8.8567 | 11 | 1 | 28 | 24.6 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
SGSS | 2013 | 5.9084 | 2 | 2 | 48 | 160.1 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
SWOT | 2016 | 6.3483 | 24 | 0 | 0 | 0 | GAO-20-405 (2020) project profiles pp.53-86, Table 2 p.13 (cumulative cost growth and launch delay)
MSL | 2006 | 6.8763 | 9 | 1 | 24 | 86 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); 24-month launch slip 2009->2011 and CDR 06/2007 per NASA OIG IG-11-019
SOFIA | 1996 | 5.7236 |  |  | 12 | 268.8 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); +268.8 pct dev cost; launch/IOC delay per GAO-14-338SP [illustrative conf-to-CDR gap: pre-2007 restructuring not cleanly dated]
NPP | 2002 | 6.2403 | 14 | 1 | 30 | 52.1 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); NPP instrument CDRs 2003-2004 (NASA GSFC NPP records); ~30-month slip
Kepler | 2004 | 5.7462 | 11 | 1 | 11 | 24.2 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); Kepler CDR 2005 (NASA Ames records); 2008->2009 launch slip
Dawn | 2004 | 5.2883 | 12 | 1 | 9 | 34.5 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); Dawn CDR 2005 (NASA JPL records); 2006->2007 launch slip
Glory | 2005 | 5.0689 | 16 | 1 | 33 | 112.3 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); Glory CDR 2006 (NASA GSFC records); multi-year slip to 2011
Herschel | 2004 | 4.5539 | 8 | 1 | 12 | 33.4 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); Herschel HIFI CDR 2005 (ESA/NASA records); 2008->2009 launch slip
WISE | 2006 | 5.2575 | 7 | 1 | 0 | -0.1 | GAO-11-239SP Table 3 (gao.gov/assets/a316263.html); WISE CDR 2007 (NASA JPL records); launched on baseline 2009

## Construction
Variable | Definition | Construction / source
dev_cost_growth_pct | Cumulative development cost growth, in percent, measured from a project's original Agency Baseline Commitment development cost to its development cost estimate at the assessment; positive values are overruns, negative values are decreases | GAO-20-405 (2020) project profiles pp.53-86 and Table 2 p.13; GAO-11-239SP (2011) Table 3 (gao.gov/assets/a316263.html); MSL figure cross-checked against NASA OIG IG-11-019
arch_maturity | Documented-design-baseline maturity at commitment, ordinal 0 to 2, derived from the gap in months between project confirmation (Key Decision Point C, the Agency Baseline Commitment) and the critical design review (CDR), the milestone at which the design documentation is judged stable: 2 = CDR at or before commitment or within 5 months (design documented when committed); 1 = 6 to 18 month gap; 0 = committed more than 18 months before CDR (design not yet documented when committed) | GAO-20-405 (2020) project-profile milestone timelines (confirmation and CDR dates); GAO design-stability best practice (stable design demonstrated at CDR); older-cohort CDR dates from named NASA mission records cited per row in data.csv
log_dev_cost | Natural logarithm of original baseline development cost in millions of then-year dollars; controls for project scale, since larger programs may carry different overrun dynamics | GAO-20-405 (2020) project-profile baseline development cost; GAO-11-239SP (2011) Table 3 baseline development cost
months_delay | Cumulative launch-readiness schedule delay in months, measured from the project's original baseline launch-readiness date to its date at assessment | GAO-20-405 (2020) Table 2 p.13 cumulative schedule column; older-cohort launch slips from GAO-11-239SP (2011) and the named mission records cited per row in data.csv

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 29.1261 | 20.6316 | 1.4117 | 0.158 | -11.3111 | 69.5633
arch_maturity | 20.4975 | 10.3108 | 1.988 | 0.0468 | 0.2887 | 40.7063
log_dev_cost | -7.0879 | 3.3797 | -2.0972 | 0.036 | -13.7121 | -0.4637
months_delay | 1.8711 | 0.3417 | 5.4757 | 4.357e-08 | 1.2013 | 2.5408

## Fit statistics
Statistic | Value
N | 23
R2 | 0.7708
R2_adj | 0.7347
F | 10.2955
F_p | 0.0003043