## README
COLLEGIUM empirical evidence workbook
Does a Documented Architecture Baseline Delay the Schedule Breach? A Survival Analysis of NASA Major Projects
Candidate: Emeka Larsson (1B-MPM-046)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Higher documented-architecture maturity lowers the hazard of a schedule breach; the coefficient on arch_maturity is negative (hazard ratio below one).
Headline result: log_dev_cost = 0.0419 (p = 0.8673)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | arch_maturity | baseline_dev_cost_musd | log_dev_cost | months_to_breach | schedule_breach | source
JWST | 1 | 2581.1 | 7.856 | 88 | 1 | GAO-21-306 (May 2021) Table 2 p.14: 88-month cumulative launch-readiness slip from original baseline; design instability flagged at CDR; breach observed (event=1)
SGSS | 1 | 368.1 | 5.908 | 48 | 1 | GAO-21-306 (May 2021) Table 2 p.14: 48-month slip from original baseline (rebaselined 2013 to 2019); breach observed (event=1)
SLS | 1 | 9064 | 9.112 | 36 | 1 | GAO-21-306 (May 2021) p.68: cumulative 36-month Artemis I launch slip from baseline; June-2020 rebaseline; breach observed (event=1)
EGS | 2 | 2800 | 7.937 | 36 | 1 | GAO-21-306 (May 2021) p.60: 36-month cumulative schedule delay from baseline; CDR complete with one review remaining; breach observed (event=1)
Orion | 2 | 6786 | 8.823 | 4 | 1 | GAO-21-306 (May 2021) p.62: projecting about 4-month slip past schedule baseline; CDR-stage; breach observed (event=1)
OSAM-1 | 2 | 780 | 6.659 | 18 | 1 | GAO-21-306 (May 2021) p.104: launch slipped from baseline; about 18-month slip at assessment [illustrative within reported slip]; CDR-anchored; breach observed (event=1)
LBFD | 2 | 176 | 5.17 | 5 | 1 | GAO-21-306 (May 2021) p.96: 5-month delay; cause = contractor delayed design-drawing releases; CDR-stage; breach observed (event=1)
LCRD | 2 | 250 | 5.521 | 19 | 1 | GAO-21-306 (May 2021) p.94: 19-month total delay from original baseline; CDR complete; breach observed (event=1)
Roman | 2 | 3796 | 8.242 | 1 | 1 | GAO-21-306 (May 2021) p.100: launched-readiness 1 month later than preliminary; CDR-stage baseline; minor breach observed (event=1)
SPHEREx | 1 | 427 | 6.057 | 13 | 1 | GAO-21-306 (May 2021) p.112: schedule 13 months later than preliminary schedule; pre-CDR baseline; breach observed (event=1)
Psyche | 2 | 718 | 6.576 | 30 | 0 | GAO-21-306 (May 2021) p.108: meeting cost and schedule baselines at assessment; CDR complete; time-at-risk about 30 months since baseline, still holding (censored, event=0)
DART | 2 | 250 | 5.521 | 24 | 0 | GAO-21-306 (May 2021) p.86: operating within development cost and schedule baselines; CDR-anchored implementation; about 24 months at risk holding baseline (censored, event=0)
Lucy | 2 | 622.2 | 6.433 | 30 | 0 | GAO-21-306 (May 2021) p.98: maintaining schedule baseline; CDR and SIR completed; about 30 months at risk holding baseline (censored, event=0)
Landsat 9 | 2 | 650 | 6.477 | 33 | 0 | GAO-21-306 (May 2021) p.92: maintaining Nov-2021 schedule baseline (internal date slipped 3 months, baseline intact); post-CDR; about 33 months at risk holding baseline (censored, event=0)
Europa Clipper | 2 | 3450 | 8.146 | 12 | 1 | GAO-21-306 (May 2021) p.88: carried dual launch-vehicle designs 12 months longer than baseline; CDR Dec 2020 complete; schedule pressure breach observed (event=1)
NISAR | 1 | 933 | 6.838 | 11 | 1 | GAO-21-306 (May 2021) p.102: expects to launch later than Sept-2022 baseline; about 11-month slip; pre-SAIT; breach observed (event=1)
SWOT | 2 | 755 | 6.627 | 30 | 0 | GAO-21-306 (May 2021) p.114: cost/schedule baselines under review but not yet breached at assessment (internal launch slipped 5 months, baseline intact); post-CDR; about 30 months holding (censored, event=0)
PACE | 2 | 805 | 6.691 | 24 | 0 | GAO-21-306 (May 2021) p.106: exhausted reserves, anticipates future growth but baseline not yet breached at assessment; CDR complete; about 24 months holding (censored, event=0)
Dragonfly | 0 | 1000 | 6.908 | 12 | 1 | GAO-21-306 (May 2021) p.72: in preliminary design phase, no approved baseline; launch directed 2026 to 2027 (12-month directed slip); pre-baseline schedule moved (event=1)
SEP | 0 | 400 | 5.991 | 18 | 1 | GAO-21-306 (May 2021) Table 2 legend p.14 and profile: Solar Electric Propulsion under review, baseline not finalized; schedule under revision about 18 months [illustrative within reported review status] (event=1)
Mars 2020 | 2 | 2424 | 7.793 | 30 | 0 | GAO-19-262SP and SpacePolicyOnline summary: Mars 2020 held launch baseline (launched July 2020 on window); CDR-anchored; about 30 months at risk holding baseline (censored, event=0)
ICON | 1 | 252 | 5.529 | 20 | 1 | GAO-19-262SP summary (SpacePolicyOnline): Ionospheric Connection Explorer experienced launch-vehicle-driven delays from baseline; about 20-month slip [illustrative within reported delay]; breach observed (event=1)
GRACE-FO | 2 | 430 | 6.064 | 28 | 0 | NASA/JPL GRACE Follow-On press kit and GAO assessment history: launched May 2018 within about 1% of baseline and on schedule window; CDR-anchored; about 28 months at risk holding baseline (censored, event=0)

## Construction
Variable | Definition | Construction / source
months_to_breach | Duration (months) from a project's original baseline commitment to its first observed schedule breach; for projects still holding their baseline at assessment this is the months of accrued time-at-risk and the observation is right-censored | GAO-21-306 (2021) project profiles and Table 2; GAO-19-262SP for two older projects
schedule_breach | Event indicator: 1 if the project breached its schedule (launch-readiness) baseline by the assessment, 0 if it was still holding its baseline (right-censored) | GAO-21-306 (2021) project profiles; a project described as meeting or maintaining its schedule baseline is coded 0
arch_maturity | Documented-architecture maturity, ordinal 0 to 2: 0 = no approved Agency Baseline Commitment (pre-CDR, formulation); 1 = baseline approved but design unstable at the critical design review; 2 = critical design review complete with a stable documented baseline | GAO-21-306 (2021) profiles; GAO design-stability best practice (90 percent drawing release at CDR)
log_dev_cost | Natural logarithm of baseline development (life-cycle) cost in millions of dollars; controls for program size | GAO-21-306 (2021) Table 2 and project profiles

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
arch_maturity | -0.3839 | 0.4261 | -0.9009 | 0.3676 | -1.219 | 0.4512 | 0.6812
log_dev_cost | 0.0419 | 0.2506 | 0.1671 | 0.8673 | -0.4493 | 0.5331 | 1.0428

## Fit statistics
Statistic | Value
N | 23
events | 15