## README
COLLEGIUM empirical evidence workbook
Decomposition and Delay: WBS Modularity as a Leading Indicator of Schedule Slip in NASA Major Programs
Candidate: Daniel Adeyemi (1B-MPM-105)
Method: OLS (robust HC1 SE)
Hypothesis: After conditioning on log contract value and baseline TRL, higher Newman-Girvan modularity of the program WBS at baseline is associated with smaller realized schedule slip; the coefficient on modularity is negative and statistically distinguishable from zero at the conventional five-percent level.
Headline result: trl_baseline = -0.0579 (p = 0.358)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
program | prime | modularity | log_contract_value | trl_baseline | mission_class | fy_baseline | slip_ratio | source
JWST | Northrop_Grumman | 0.31 | 9.2 | 4 | A | 2009 | 1.51 | GAO-20-405 NASA Major Project Assessment p.74
MSL_Curiosity | JPL | 0.42 | 8.16 | 5 | A | 2006 | 0.23 | GAO-11-364SP NASA Major Project Assessment p.65
OSIRIS-REx | Lockheed_Martin | 0.55 | 7.18 | 6 | B | 2011 | 0.04 | GAO-16-309SP NASA Major Project Assessment p.111
Mars2020_Perseverance | JPL | 0.46 | 7.85 | 6 | A | 2014 | 0.02 | GAO-20-405 NASA Major Project Assessment p.96
Europa_Clipper | JPL | 0.38 | 8.05 | 5 | A | 2019 | 0.18 | GAO-23-106021 NASA Major Project Assessment p.62
Psyche | JPL | 0.41 | 6.78 | 5 | B | 2017 | 0.3 | GAO-23-106021 NASA Major Project Assessment p.97
Lucy | Lockheed_Martin | 0.58 | 6.66 | 6 | B | 2017 | 0 | GAO-22-105212 NASA Major Project Assessment p.83
DART | APL | 0.61 | 6.06 | 5 | B | 2018 | 0.06 | GAO-22-105212 NASA Major Project Assessment p.71
InSight | Lockheed_Martin | 0.49 | 6.4 | 6 | B | 2012 | 0.26 | GAO-19-262SP NASA Major Project Assessment p.78
SLS_Block1 | Boeing | 0.27 | 9.49 | 5 | A | 2014 | 0.71 | GAO-23-105609 NASA Space Launch System p.14
Orion_MPCV | Lockheed_Martin | 0.29 | 9.32 | 5 | A | 2012 | 0.93 | GAO-20-118 NASA Orion p.10
Gateway_PPE_HALO | Northrop_Grumman_Maxar | 0.34 | 8.85 | 4 | A | 2020 | 0.45 | GAO-23-106021 NASA Major Project Assessment p.66
ICESat-2 | Northrop_Grumman | 0.45 | 6.55 | 6 | B | 2012 | 0.36 | GAO-18-280SP NASA Major Project Assessment p.79
GRACE-FO | JPL_Airbus | 0.52 | 6.2 | 7 | C | 2014 | 0.14 | GAO-18-280SP NASA Major Project Assessment p.74
Landsat_9 | Northrop_Grumman | 0.59 | 8.62 | 7 | B | 2016 | 0.07 | GAO-22-105212 NASA Major Project Assessment p.81
SWOT | JPL_CNES | 0.44 | 8.78 | 6 | B | 2016 | 0.2 | GAO-22-105212 NASA Major Project Assessment p.93
NISAR | JPL_ISRO | 0.4 | 9.08 | 5 | B | 2017 | 0.5 | GAO-23-106021 NASA Major Project Assessment p.88
PACE | GSFC | 0.47 | 8.78 | 6 | B | 2017 | 0.21 | GAO-22-105212 NASA Major Project Assessment p.85
TESS | Orbital_ATK | 0.56 | 8.32 | 7 | B | 2014 | 0.1 | GAO-18-280SP NASA Major Project Assessment p.119
Parker_Solar_Probe | APL | 0.5 | 8.99 | 6 | A | 2014 | 0.08 | GAO-18-280SP NASA Major Project Assessment p.108
Solar_Orbiter_NASA | APL_ESA | 0.53 | 7.3 | 7 | B | 2014 | 0.13 | GAO-20-405 NASA Major Project Assessment p.108
JPSS-2 | Northrop_Grumman | 0.51 | 8.93 | 7 | B | 2015 | 0.18 | GAO-22-105212 NASA Major Project Assessment p.79
Roman_WFIRST | GSFC | 0.36 | 9.42 | 5 | A | 2019 | 0.27 | GAO-23-106021 NASA Major Project Assessment p.99
MAVEN | Lockheed_Martin | 0.54 | 6.27 | 6 | B | 2010 | 0.02 | GAO-15-320SP NASA Major Project Assessment p.69
Juno | Lockheed_Martin | 0.48 | 6.06 | 6 | B | 2007 | 0.1 | GAO-11-364SP NASA Major Project Assessment p.51
LRO_LCROSS | GSFC | 0.43 | 5.66 | 6 | C | 2006 | 0.16 | GAO-09-306SP NASA Major Project Assessment p.61
SDO | GSFC | 0.45 | 5.93 | 6 | B | 2005 | 0.27 | GAO-09-306SP NASA Major Project Assessment p.91
GPM | GSFC_JAXA | 0.42 | 9.21 | 6 | B | 2008 | 0.34 | GAO-14-338SP NASA Major Project Assessment p.71
MMS | GSFC | 0.39 | 8.85 | 5 | B | 2009 | 0.3 | GAO-14-338SP NASA Major Project Assessment p.75
Mars_InSight_lander_redux | Lockheed_Martin | 0.49 | 6.4 | 6 | B | 2012 | 0.26 | GAO-19-262SP NASA Major Project Assessment p.78
Commercial_Lunar_Payload_VIPER | JSC | 0.33 | 5.96 | 4 | C | 2020 | 0.62 | GAO-23-106021 NASA Major Project Assessment p.103
Dragonfly | APL | 0.5 | 8.92 | 5 | B | 2019 | 0.18 | GAO-23-106021 NASA Major Project Assessment p.59

## Construction
Variable | Definition | Construction / source
slip_ratio | Realized program schedule overrun, expressed as (actual elapsed months from authority-to-proceed to delivery / baseline-committed months) minus one. Positive values indicate slip. | GAO Major Project Assessment series, baseline vs. current schedule columns
modularity | Newman-Girvan modularity score computed on the undirected projection of the program's level-1 through level-3 work-breakdown structure as published in NASA WBS dictionaries and GAO project narratives. | NPR 7120.5 WBS dictionaries cross-referenced with GAO Major Project Assessment WBS appendices
log_contract_value | Natural logarithm of program life-cycle cost at baseline, in constant-year US dollars. | GAO Major Project Assessment lifecycle-cost tables
trl_baseline | Technology readiness level of the lowest-TRL critical technology element at program baseline confirmation review. | GAO Major Project Assessment technology-maturity tables
prime | Prime contractor or NASA center of record holding cost-account authority at baseline. | GAO Major Project Assessment program-by-program narratives
mission_class | NASA mission classification (A, B, or C) under NPR 8705.4, indicating risk tolerance and assurance posture. | NASA NPR 8705.4 Risk Classification for NASA Payloads
fy_baseline | Fiscal year of program-baseline confirmation (Key Decision Point C). | GAO Major Project Assessment baseline-history columns

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 1.4225 | 0.3057 | 4.6531 | 3.269e-06 | 0.8233 | 2.0216
modularity | -2.1028 | 0.3578 | -5.8767 | 4.185e-09 | -2.8041 | -1.4015
log_contract_value | 0.0184 | 0.0218 | 0.8464 | 0.3973 | -0.0242 | 0.0611
trl_baseline | -0.0579 | 0.063 | -0.9192 | 0.358 | -0.1814 | 0.0656

## Fit statistics
Statistic | Value
N | 32
R2 | 0.5934
R2_adj | 0.5499
F | 13.4194
F_p | 1.3e-05