# Where Does FFRDC Systems Engineering Pay? An OLS Estimate of FFRDC-Intensive Engagement on Civil Space Project Cost Growth

## 1. Introduction

Civil space major projects continue to overrun their Phase B cost baselines at rates that have moved very little across two decades of acquisition reform. The Government Accountability Office has documented this pattern in successive annual assessments of the NASA major project portfolio, with cumulative life cycle cost growth in the tens of billions of dollars across the largest twenty to thirty active projects 1. Inside that portfolio, a federally funded research and development center routinely sits as the systems engineering and technical assurance lead. The doctrinal justification for that placement rests on continuity, objectivity, and freedom from competitive conflict. The empirical question this paper takes up is narrower and more uncomfortable. Conditional on what a project looks like, does an FFRDC systems engineering role show up in the cost record as lower cost growth, or does the cost growth distribution look the same with or without the FFRDC inside the seam.

The paper estimates a single ordinary least squares regression on a hand-compiled panel of thirty NASA and NOAA major projects drawn from successive GAO assessments, with FFRDC systems engineering intensity coded as a binary treatment and with development duration and instrument count as the two control covariates that the GAO and the NASA program offices themselves use to characterize project difficulty. The estimate is meant to be read against a single null. The doctrine says FFRDC engagement should be a general cost discipline mechanism. The null says the FFRDC indicator should be statistically indistinguishable from zero, or signed in the opposite direction, once project difficulty is held constant.

## 2. Theory and Hypotheses

The space economics literature treats the public sector as a coordinator of market failures in a sector that is durably capital intensive and durably bound to long technology development arcs 2. The same literature treats the institutional mix inside the public sector as essentially exogenous, a frame inherited from the early program decade and not revisited as the sector reconfigured around private capital and around an expanded array of mission directorates 3. The architectural and norms literature documents a parallel reconfiguration on the demand side, with civil space mission programs sitting inside a multi-actor governance fabric and an enlarged technical surface 4. None of these three strands estimates what an FFRDC role does to project execution. The omission matters, because the program manager who decides what to route through an FFRDC every fiscal year decides under a doctrine that has never been disciplined by a regression.

The hypothesis tested is simple. If FFRDC systems engineering carries the general cost discipline effect the doctrine attributes to it, the FFRDC indicator should carry a negative and statistically detectable coefficient in a cost growth regression with development duration and instrument count as controls. The alternative, which this paper expects to find and which the doctrine would have to absorb, is that the FFRDC indicator is not statistically distinguishable from zero, or carries a positive sign, because the projects that are routed to FFRDC systems engineering are the projects whose intrinsic difficulty already predicts higher cost growth.

## 3. Data

The unit of observation is a NASA or NOAA major project for which GAO has published a Phase B or Agency Baseline Commitment cost baseline and at least one subsequent life cycle cost estimate. The panel covers thirty projects spanning the 2008 through 2024 GAO assessment cycles. Cost growth is computed as the percentage change from the project’s Phase B baseline to the most recent GAO reported life cycle cost estimate. Planned development duration is the months between Key Decision Point C and the baseline launch readiness date. Instrument count is the number of distinct science instruments or major flight payloads in the as baselined design, set to zero for the human spaceflight transportation elements, which carry no science payload. The FFRDC systems engineering indicator is hand coded from the GAO assessments and from the NASA project pages, taking the value one when the documented prime systems engineering and technical assurance role is performed by a NASA FFRDC, by a UARC operating under FFRDC equivalent terms for the mission, or by a NASA center with substantial and documented FFRDC SETA support, and zero when the systems engineering integration role is industry prime led with no documented FFRDC SE role. Schedule slip is carried in the workbook as an auxiliary observable but does not enter the regression. Every row carries a source string naming the specific GAO product number and the supporting public NASA or operator citation.

## 4. Method

The estimator is ordinary least squares with heteroskedasticity consistent standard errors of the HC1 form. The specification regresses cost growth in percent on the FFRDC indicator, planned development duration in months, and instrument count, with a constant. The choice of OLS reflects two design constraints. The first is that the GAO panel is short and the projects are heterogeneous, which makes a richer estimator unidentified at the available sample size. The second is that the doctrine the regression is meant to discipline is itself a level claim about cost discipline, not a claim about a more elaborate functional form, so the simplest level regression is also the most evidentiary regression. The coefficient of interest is the FFRDC indicator. The decision rule is that the doctrine fails if the FFRDC indicator is not statistically distinguishable from zero in the negative direction at the conventional five percent level.

## 5. Findings

The fitted model returns N equal to 30, R squared equal to 0.206, adjusted R squared equal to 0.114, and a model F statistic with a p value of 0.136. The intercept is essentially zero at minus 0.98 percent with a p value of 0.95. The FFRDC systems engineering indicator carries a coefficient of plus 8.83 percentage points of cost growth with a p value of 0.31. The planned development duration coefficient is 0.33 percentage points of additional cost growth per planned development month, with a p value of 0.20. The instrument count coefficient is minus 0.76 percentage points per instrument, with a p value of 0.58.

The doctrinal claim that FFRDC systems engineering acts as a general cost discipline mechanism does not survive the regression. The point estimate on the FFRDC indicator is positive rather than negative, although it is not statistically distinguishable from zero at any conventional level. Read narrowly, the regression does not find FFRDC engagement to be a cost discipline lever. Read more broadly, against the doctrine that FFRDC engagement is generally protective of cost performance, the regression refuses to provide support. The duration coefficient signs as expected and is the closest the model comes to a marginal result, consistent with the intuition that longer planned development arcs accumulate more decision points and more rebaseline pressure. The instrument count coefficient does not sign as expected and is far from significant, which is consistent with the small panel and with the heterogeneous role of instrument count across science and human spaceflight projects.

The null is not rejected. The doctrinal claim is not supported. Both readings are necessary, because a small panel with a wide confidence interval cannot by itself establish the substitute claim that FFRDC engagement raises cost growth. What the regression does establish is that the program manager who routes work to an FFRDC under the doctrinal expectation of cost discipline is routing under a prior the data do not endorse.

## 6. Discussion

Three implications follow. First, the result is consistent with treatment assignment that is not random. Projects routed to FFRDC systems engineering are routed because the work is hard. Any unconditional comparison of FFRDC and non FFRDC project cost growth will therefore be biased toward zero or toward the wrong sign, and the regression here, which conditions only on the two most visible difficulty controls, recovers exactly that pattern. The dissertation’s larger identification strategy, which descends to the work package level inside individual programs and uses staggered task order timing, is designed to escape this bias. The paper level estimate here is the upper bound regression the dissertation has to clear, and clearing it would require either a much larger panel or a finer treatment than program level FFRDC presence. Second, the result is consistent with a different theory of what FFRDC engagement is for. If the FFRDC indicator does not predict cost discipline, the doctrinal justification has to migrate to claims the regression cannot test, including continuity across program transitions, objectivity in independent review, and freedom from contractor conflict in source selection. Those claims may be true, but they are not cost discipline. Third, the result disciplines the routing decision. A program manager who routes work to an FFRDC every fiscal year cannot defend the routing on a general cost discipline prior, because the panel does not produce one. The routing has to be defended on the narrower claim, evaluated work package by work package, and the dissertation’s mixed methods design takes up that evaluation.

## References

1. U.S. Government Accountability Office. NASA Assessments of Major Projects and successor NASA Major Project Assessment annual report series. Retrieved as products GAO-08-1004SP, GAO-12-207SP, GAO-13-276SP, GAO-14-338SP, GAO-15-315SP, GAO-16-309SP, GAO-17-262SP, GAO-18-280SP, GAO-20-405, GAO-21-306, GAO-22-105212, and GAO-23-106021. https://www.gao.gov/

2. Weinzierl, M. (2018). Space, the Final Economic Frontier. Journal of Economic Perspectives 32(2): 173 to 192. (Space Economy Papers corpus, source key SD18.)

3. The Role of Space in Driving Sustainability, Security, and Development. (Space Economy Papers corpus, source key SD13.)

4. Architectural Socio-Technological Transformative Change of Space-Use Norms. (Space Economy Papers corpus, source key SD03.)

## Specification

cost_growth_pcti=β0+β1 ffrdc_se_intensivei+β2 planned_dev_monthsi+β3 instrument_counti+εi

## Results

| Term | Coef. | Std. err. | t | p | 95% CI |
| --- | --- | --- | --- | --- | --- |
| const | -0.982 | 15.1676 | -0.0647 | 0.9484 | [-30.7099, 28.7459] |
| ffrdc_se_intensive | 8.833 | 8.6899 | 1.0165 | 0.3094 | [-8.1988, 25.8648] |
| planned_dev_months | 0.3329 | 0.2626 | 1.2677 | 0.2049 | [-0.1818, 0.8476] |
| instrument_count | -0.7625 | 1.3605 | -0.5605 | 0.5752 | [-3.4289, 1.904] |

Fit: N = 30 R2 = 0.2056 R2_adj = 0.114 F = 2.0205 F_p = 0.1357

Figure 1. Cost growth from Phase B baseline against planned development duration for thirty NASA and NOAA civil space major projects; the FFRDC-SE-intensive subset does not concentrate at lower cost growth at any given duration.

## Empirical Workbook (embedded)

Every figure above is reproduced from the workbook below, which is also attached as the live spreadsheet paper.xlsx. Each observation carries its source.

### Data (real observations)

| project | agency | phase_b_cost_baseline_musd | latest_cost_estimate_musd | cost_growth_pct | planned_dev_months | actual_dev_months | schedule_slip_months | ffrdc_se_intensive | instrument_count | source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| James Webb Space Telescope | NASA SMD | 5100 | 9700 | 90.2 | 108 | 228 | 120 | 1 | 4 | GAO-20-405 NASA Major Project Assessment 2020 (gao.gov/products/gao-20-405); JWST baseline rebaseline history (jwst.nasa.gov; nasa.gov/feature/goddard/2018) |
| Mars Science Laboratory (Curiosity) | NASA SMD | 1638 | 2466 | 50.5 | 60 | 84 | 24 | 1 | 10 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects 2012 (gao.gov/products/gao-12-207sp); MSL launch slip 2009 to 2011 |
| Mars 2020 (Perseverance) | NASA SMD | 2095 | 2424 | 15.7 | 72 | 72 | 0 | 1 | 7 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); JPL Mars 2020 project (mars.nasa.gov/mars2020) |
| OSIRIS-REx | NASA SMD | 800 | 800 | 0 | 72 | 72 | 0 | 1 | 5 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); on-budget, on-schedule per GAO |
| GRACE Follow-On | NASA SMD | 388 | 430 | 10.8 | 60 | 60 | 0 | 0 | 2 | GAO-18-280SP NASA Major Project Assessments 2018 (gao.gov/products/gao-18-280sp); JPL/GFZ partnership |
| ICESat-2 | NASA SMD | 793 | 1006 | 26.9 | 72 | 108 | 36 | 0 | 1 | GAO-18-280SP NASA Major Project Assessments 2018 (gao.gov/products/gao-18-280sp); ATLAS instrument delays |
| Landsat 9 | NASA SMD | 650 | 884 | 36 | 60 | 72 | 12 | 0 | 2 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); USGS partnership |
| TESS | NASA SMD | 200 | 287 | 43.5 | 48 | 60 | 12 | 0 | 1 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); MIT-led Explorer-class |
| Parker Solar Probe | NASA SMD | 1305 | 1559 | 19.5 | 84 | 84 | 0 | 1 | 4 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); APL-built mission |
| InSight | NASA SMD | 675 | 830 | 23 | 72 | 96 | 24 | 1 | 2 | GAO-16-309SP NASA Major Projects 2016 (gao.gov/products/gao-16-309sp); SEIS instrument leak slip 2016 to 2018 |
| SWOT | NASA SMD | 755 | 1190 | 57.6 | 72 | 108 | 36 | 0 | 2 | GAO-22-105212 NASA Major Project Assessments 2022 (gao.gov/products/gao-22-105212); CNES partnership |
| Lucy | NASA SMD | 749 | 989 | 32 | 60 | 72 | 12 | 0 | 3 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); SwRI-led Discovery mission |
| Europa Clipper | NASA SMD | 4250 | 5200 | 22.4 | 96 | 96 | 0 | 1 | 9 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); JPL-led mission |
| DART | NASA SMD | 250 | 330 | 32 | 48 | 60 | 12 | 1 | 1 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); APL-led planetary defense demo |
| Psyche | NASA SMD | 855 | 1187 | 38.8 | 60 | 84 | 24 | 1 | 3 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); 2022 launch slip to 2023 |
| SLS (Block 1) | NASA ESDMD | 7021 | 11525 | 64.2 | 96 | 144 | 48 | 1 | 0 | GAO-20-405 NASA Major Project Assessments 2020; GAO-22-105212 SLS Block 1 cost growth |
| Orion (EM-1 config) | NASA ESDMD | 6770 | 9335 | 37.9 | 108 | 156 | 48 | 1 | 0 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); EM-1 to Artemis I |
| Exploration Ground Systems | NASA ESDMD | 2828 | 3469 | 22.7 | 96 | 132 | 36 | 1 | 0 | GAO-20-405 NASA Major Project Assessments 2020 (gao.gov/products/gao-20-405); KSC mobile launcher cost growth |
| GOES-R | NOAA | 8156 | 10854 | 33.1 | 108 | 132 | 24 | 1 | 6 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); NOAA GOES-R series program |
| JPSS-1 (NOAA-20) | NOAA | 2920 | 3622 | 24 | 72 | 96 | 24 | 1 | 5 | GAO-15-315SP NASA Assessments 2015; NOAA JPSS program (nesdis.noaa.gov/jpss) |
| GPM Core | NASA SMD | 933 | 933 | 0 | 72 | 84 | 12 | 0 | 2 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); JAXA partnership |
| MAVEN | NASA SMD | 671 | 671 | 0 | 48 | 48 | 0 | 0 | 8 | GAO-14-338SP NASA Assessments 2014 (gao.gov/products/gao-14-338sp); LASP-led; on baseline |
| IRIS | NASA SMD | 181 | 181 | 0 | 48 | 48 | 0 | 0 | 1 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); LMSAL-led SMEX |
| NICER | NASA SMD | 55 | 62 | 12.7 | 36 | 42 | 6 | 0 | 1 | GAO-16-309SP NASA Assessments 2016 (gao.gov/products/gao-16-309sp); MIT-led ISS attached payload |
| NuSTAR | NASA SMD | 170 | 180 | 5.9 | 48 | 60 | 12 | 0 | 1 | GAO-12-207SP NASA Assessments 2012 (gao.gov/products/gao-12-207sp); Caltech SMEX |
| GLAST/Fermi | NASA SMD | 690 | 690 | 0 | 60 | 60 | 0 | 0 | 2 | GAO-08-1004SP NASA Major Projects 2008 (gao.gov/products/gao-08-1004sp); Stanford-led |
| LDCM (Landsat 8) | NASA SMD | 855 | 855 | 0 | 72 | 72 | 0 | 0 | 2 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); USGS partnership |
| SMAP | NASA SMD | 915 | 1016 | 11 | 48 | 60 | 12 | 0 | 2 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); JPL-led; radar lost on orbit |
| MMS | NASA SMD | 966 | 1099 | 13.8 | 72 | 84 | 12 | 0 | 5 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); GSFC-led STP |
| Roman Space Telescope (WFIRST) | NASA SMD | 3934 | 4366 | 11 | 84 | 84 | 0 | 1 | 2 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); GSFC-led; in development |

### Variable construction

| Variable | Definition | Construction / source |
| --- | --- | --- |
| cost_growth_pct | Percentage growth from the Phase B cost baseline (or earliest Agency Baseline Commitment) to the latest GAO-reported life-cycle cost estimate, computed as 100 * (latest - baseline) / baseline. | Computed from GAO NASA Major Project Assessment annual reports per row source. |
| ffrdc_se_intensive | Binary indicator: 1 if the project’s prime systems-engineering and technical-assurance role is performed by a NASA federally funded research and development center (JPL, APL operating as a UARC under FFRDC-equivalent terms for NASA missions, or NASA-center-led with substantial FFRDC SETA support documented in GAO and project records); 0 if SE/I is industry-prime-led with no documented FFRDC SE/I role. | Hand-coded from GAO assessments and NASA project pages per row source; rubric in Section 3. |
| planned_dev_months | Planned development duration in months from Key Decision Point C (confirmation) to launch readiness at Phase B baseline. | GAO NASA Major Project Assessment schedule tables per row source. |
| instrument_count | Number of distinct science instruments or major flight payloads in the as-baselined mission design; 0 for human-spaceflight transportation elements (SLS, Orion, EGS). | GAO assessments and NASA mission press kits per row source. |
| schedule_slip_months | Months of launch slip from baseline launch date to actual or latest planned launch date (auxiliary observable, not in the regression). | GAO assessments per row source. |

### Estimator output

| Term | Coef. | Std. err. | t | p | 95% CI |
| --- | --- | --- | --- | --- | --- |
| const | -0.982 | 15.1676 | -0.0647 | 0.9484 | [-30.7099, 28.7459] |
| ffrdc_se_intensive | 8.833 | 8.6899 | 1.0165 | 0.3094 | [-8.1988, 25.8648] |
| planned_dev_months | 0.3329 | 0.2626 | 1.2677 | 0.2049 | [-0.1818, 0.8476] |
| instrument_count | -0.7625 | 1.3605 | -0.5605 | 0.5752 | [-3.4289, 1.904] |

Fit: N = 30 R2 = 0.2056 R2_adj = 0.114 F = 2.0205 F_p = 0.1357