## README
COLLEGIUM empirical evidence workbook
Where Does FFRDC Systems Engineering Pay? An OLS Estimate of FFRDC-Intensive Engagement on Civil Space Project Cost Growth
Candidate: Greta Renner (1B-MPM-133)
Method: OLS (robust HC1 SE)
Hypothesis: FFRDC-SE-intensive civil space projects exhibit cost growth that is not systematically lower than comparable industry-prime-led projects once development duration and instrument complexity are controlled for; the ffrdc_se_intensive coefficient is statistically indistinguishable from zero or positive, falsifying the doctrinal claim that FFRDC SE engagement is a general cost-discipline mechanism.
Headline result: instrument_count = -0.7625 (p = 0.5752)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | agency | phase_b_cost_baseline_musd | latest_cost_estimate_musd | cost_growth_pct | planned_dev_months | actual_dev_months | schedule_slip_months | ffrdc_se_intensive | instrument_count | source
James Webb Space Telescope | NASA SMD | 5100 | 9700 | 90.2 | 108 | 228 | 120 | 1 | 4 | GAO-20-405 NASA Major Project Assessment 2020 (gao.gov/products/gao-20-405); JWST baseline rebaseline history (jwst.nasa.gov; nasa.gov/feature/goddard/2018)
Mars Science Laboratory (Curiosity) | NASA SMD | 1638 | 2466 | 50.5 | 60 | 84 | 24 | 1 | 10 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects 2012 (gao.gov/products/gao-12-207sp); MSL launch slip 2009 to 2011
Mars 2020 (Perseverance) | NASA SMD | 2095 | 2424 | 15.7 | 72 | 72 | 0 | 1 | 7 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); JPL Mars 2020 project (mars.nasa.gov/mars2020)
OSIRIS-REx | NASA SMD | 800 | 800 | 0 | 72 | 72 | 0 | 1 | 5 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); on-budget, on-schedule per GAO
GRACE Follow-On | NASA SMD | 388 | 430 | 10.8 | 60 | 60 | 0 | 0 | 2 | GAO-18-280SP NASA Major Project Assessments 2018 (gao.gov/products/gao-18-280sp); JPL/GFZ partnership
ICESat-2 | NASA SMD | 793 | 1006 | 26.9 | 72 | 108 | 36 | 0 | 1 | GAO-18-280SP NASA Major Project Assessments 2018 (gao.gov/products/gao-18-280sp); ATLAS instrument delays
Landsat 9 | NASA SMD | 650 | 884 | 36 | 60 | 72 | 12 | 0 | 2 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); USGS partnership
TESS | NASA SMD | 200 | 287 | 43.5 | 48 | 60 | 12 | 0 | 1 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); MIT-led Explorer-class
Parker Solar Probe | NASA SMD | 1305 | 1559 | 19.5 | 84 | 84 | 0 | 1 | 4 | GAO-17-262SP NASA Assessments of Major Projects 2017 (gao.gov/products/gao-17-262sp); APL-built mission
InSight | NASA SMD | 675 | 830 | 23 | 72 | 96 | 24 | 1 | 2 | GAO-16-309SP NASA Major Projects 2016 (gao.gov/products/gao-16-309sp); SEIS instrument leak slip 2016 to 2018
SWOT | NASA SMD | 755 | 1190 | 57.6 | 72 | 108 | 36 | 0 | 2 | GAO-22-105212 NASA Major Project Assessments 2022 (gao.gov/products/gao-22-105212); CNES partnership
Lucy | NASA SMD | 749 | 989 | 32 | 60 | 72 | 12 | 0 | 3 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); SwRI-led Discovery mission
Europa Clipper | NASA SMD | 4250 | 5200 | 22.4 | 96 | 96 | 0 | 1 | 9 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); JPL-led mission
DART | NASA SMD | 250 | 330 | 32 | 48 | 60 | 12 | 1 | 1 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); APL-led planetary defense demo
Psyche | NASA SMD | 855 | 1187 | 38.8 | 60 | 84 | 24 | 1 | 3 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); 2022 launch slip to 2023
SLS (Block 1) | NASA ESDMD | 7021 | 11525 | 64.2 | 96 | 144 | 48 | 1 | 0 | GAO-20-405 NASA Major Project Assessments 2020; GAO-22-105212 SLS Block 1 cost growth
Orion (EM-1 config) | NASA ESDMD | 6770 | 9335 | 37.9 | 108 | 156 | 48 | 1 | 0 | GAO-21-306 NASA Major Projects 2021 (gao.gov/products/gao-21-306); EM-1 to Artemis I
Exploration Ground Systems | NASA ESDMD | 2828 | 3469 | 22.7 | 96 | 132 | 36 | 1 | 0 | GAO-20-405 NASA Major Project Assessments 2020 (gao.gov/products/gao-20-405); KSC mobile launcher cost growth
GOES-R | NOAA | 8156 | 10854 | 33.1 | 108 | 132 | 24 | 1 | 6 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); NOAA GOES-R series program
JPSS-1 (NOAA-20) | NOAA | 2920 | 3622 | 24 | 72 | 96 | 24 | 1 | 5 | GAO-15-315SP NASA Assessments 2015; NOAA JPSS program (nesdis.noaa.gov/jpss)
GPM Core | NASA SMD | 933 | 933 | 0 | 72 | 84 | 12 | 0 | 2 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); JAXA partnership
MAVEN | NASA SMD | 671 | 671 | 0 | 48 | 48 | 0 | 0 | 8 | GAO-14-338SP NASA Assessments 2014 (gao.gov/products/gao-14-338sp); LASP-led; on baseline
IRIS | NASA SMD | 181 | 181 | 0 | 48 | 48 | 0 | 0 | 1 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); LMSAL-led SMEX
NICER | NASA SMD | 55 | 62 | 12.7 | 36 | 42 | 6 | 0 | 1 | GAO-16-309SP NASA Assessments 2016 (gao.gov/products/gao-16-309sp); MIT-led ISS attached payload
NuSTAR | NASA SMD | 170 | 180 | 5.9 | 48 | 60 | 12 | 0 | 1 | GAO-12-207SP NASA Assessments 2012 (gao.gov/products/gao-12-207sp); Caltech SMEX
GLAST/Fermi | NASA SMD | 690 | 690 | 0 | 60 | 60 | 0 | 0 | 2 | GAO-08-1004SP NASA Major Projects 2008 (gao.gov/products/gao-08-1004sp); Stanford-led
LDCM (Landsat 8) | NASA SMD | 855 | 855 | 0 | 72 | 72 | 0 | 0 | 2 | GAO-13-276SP NASA Assessments 2013 (gao.gov/products/gao-13-276sp); USGS partnership
SMAP | NASA SMD | 915 | 1016 | 11 | 48 | 60 | 12 | 0 | 2 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); JPL-led; radar lost on orbit
MMS | NASA SMD | 966 | 1099 | 13.8 | 72 | 84 | 12 | 0 | 5 | GAO-15-315SP NASA Assessments 2015 (gao.gov/products/gao-15-315sp); GSFC-led STP
Roman Space Telescope (WFIRST) | NASA SMD | 3934 | 4366 | 11 | 84 | 84 | 0 | 1 | 2 | GAO-23-106021 NASA Major Project Assessments 2023 (gao.gov/products/gao-23-106021); GSFC-led; in development

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Percentage growth from the Phase B cost baseline (or earliest Agency Baseline Commitment) to the latest GAO-reported life-cycle cost estimate, computed as 100 * (latest - baseline) / baseline. | Computed from GAO NASA Major Project Assessment annual reports per row source.
ffrdc_se_intensive | Binary indicator: 1 if the project's prime systems-engineering and technical-assurance role is performed by a NASA federally funded research and development center (JPL, APL operating as a UARC under FFRDC-equivalent terms for NASA missions, or NASA-center-led with substantial FFRDC SETA support documented in GAO and project records); 0 if SE/I is industry-prime-led with no documented FFRDC SE/I role. | Hand-coded from GAO assessments and NASA project pages per row source; rubric in Section 3.
planned_dev_months | Planned development duration in months from Key Decision Point C (confirmation) to launch readiness at Phase B baseline. | GAO NASA Major Project Assessment schedule tables per row source.
instrument_count | Number of distinct science instruments or major flight payloads in the as-baselined mission design; 0 for human-spaceflight transportation elements (SLS, Orion, EGS). | GAO assessments and NASA mission press kits per row source.
schedule_slip_months | Months of launch slip from baseline launch date to actual or latest planned launch date (auxiliary observable, not in the regression). | GAO assessments per row source.

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -0.982 | 15.1676 | -0.0647 | 0.9484 | -30.7099 | 28.7459
ffrdc_se_intensive | 8.833 | 8.6899 | 1.0165 | 0.3094 | -8.1988 | 25.8648
planned_dev_months | 0.3329 | 0.2626 | 1.2677 | 0.2049 | -0.1818 | 0.8476
instrument_count | -0.7625 | 1.3605 | -0.5605 | 0.5752 | -3.4289 | 1.904

## Fit statistics
Statistic | Value
N | 30
R2 | 0.2056
R2_adj | 0.114
F | 2.0205
F_p | 0.1357