## README
COLLEGIUM empirical evidence workbook
Does Reorganization Hasten the Breach? A Survival Analysis of Major Cost Overruns in NASA's Space Acquisition Portfolio
Candidate: Nia Frost (1B-MPM-047)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H0: a major reorganization of the managing directorate does not change the hazard of a major cost breach (Cox coefficient on reorg = 0, hazard ratio = 1). H1: reorganization changes the breach hazard (coefficient on reorg distinguishable from 0).
Headline result: ln_baseline_cost = -0.8735 (p = 0.0082)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | reorg | crewed | ln_baseline_cost | confirm_year | duration_yrs | event | dev_cost_growth_pct | source
SLS | 1 | 1 | 8.762 | 2014 | 7.4 | 1 | 42.5 | GAO-22-105212 Table 6 (cost growth 42.5%, baseline dev cost $6390.0M); KDP-C Aug 2014 (NASA, americaspace/SLS KDP-C 2014); HEOMD->ESDMD reorg Sep 2021 (SpaceNews, NASA leadership reorg). Event=1 at >=15% breach; breach observed by GAO-19; duration confirm-2014 to first-breach-assessment ~7.4 yr.
Orion | 1 | 1 | 8.82 | 2015 | 6.4 | 1 | 37.4 | GAO-22-105212 Table 6 (37.4%, baseline $6768.4M); Orion KDP-C Sep 2015 (americaspace 2015); HEOMD->ESDMD reorg Sep 2021 (space.com). Breach >=15% by GAO-21 (13.1%) crossing later; first >=15% assessment GAO-22; duration to breach ~6.4 yr.
EGS | 1 | 1 | 7.52 | 2014 | 6.5 | 1 | 40.6 | GAO-22-105212 Table 6 (40.6%, baseline $1843.5M); EGS baseline ~2014 with SLS/Orion (GAO-21 Table 2 35.4%); HEOMD->ESDMD reorg Sep 2021. Breach >=15% by GAO-21; duration ~6.5 yr.
JWST | 0 | 0 | 7.856 | 2009 | 12.5 | 1 | 175.7 | GAO-22-105212 Table 6 (175.7%, baseline $2581.1M); JWST baseline 2009 (GAO/NASA, JWST baseline 2009); SMD-managed (unchanged in 2021 reorg). Breach long-standing; duration to first-breach ~12.5 yr (replanned 2011).
SGSS | 0 | 0 | 5.908 | 2014 | 5 | 1 | 160.1 | GAO-22-105212 Table 6 (160.1%, baseline $368.1M); SGSS SMD/SCaN-managed; GAO-21 Table 2 listed overrunning. Duration confirm to >=15% breach ~5.0 yr [confirm year illustrative].
SEP | 1 | 1 | 5.049 | 2019 | 2.5 | 1 | 30.3 | GAO-22-105212 Table 6 (30.3%, baseline $155.9M); Solar Electric Propulsion supports Gateway/Artemis, ESDMD portfolio after Sep 2021 reorg; GAO-22 rebaseline. Duration to breach ~2.5 yr.
LCRD | 0 | 0 | 4.52 | 2016 | 5.5 | 1 | 58.1 | GAO-22-105212 Table 6 (58.1%, baseline $91.8M); GAO-21 Table 2 40.1% already breached; SMD/SCaN technology demo. Duration to >=15% breach ~5.5 yr [confirm year illustrative].
OSAM-1 | 0 | 0 | 6.882 | 2019 | 2.8 | 1 | 15 | GAO-22-105212 Table 6 (15.0% growth, baseline $974.4M); GAO computed 15% to capture pending replan (Table 6 note a); SMD/STMD-managed. Duration to breach ~2.8 yr.
NISAR | 0 | 0 | 6.494 | 2014 | 7.5 | 1 | 17.1 | GAO-22-105212 Table 6 (17.1%, baseline $661.0M); NISAR IA signed Sep 2014 (NASA-ISRO), SMD Earth-science. Crossed >=15% by GAO-22. Duration confirm-2014 to breach ~7.5 yr.
LBFD | 0 | 0 | 6.148 | 2018 | 3.8 | 1 | 22.3 | GAO-22-105212 Table 6 (22.3%, baseline $467.7M); X-59 LBFD ARMD-managed (Aeronautics, not reorganized). GAO-21 Table 2 13.8% then crossed; duration to >=15% breach ~3.8 yr.
SWOT | 0 | 0 | 6.348 | 2016 | 6 | 1 | 11.8 | GAO-22-105212 Table 6 (11.8%, baseline $571.5M); SWOT implementation/Phase C 2016 (JPL SWOT mission overview); SMD Earth-science. Event=0 (<15% at last obs Jan 2022); launch Dec 2022; censored duration confirm-2016 to Jan-2022 ~6.0 yr.
Roman | 0 | 0 | 7.972 | 2020 | 1.8 | 0 | 12.8 | GAO-22-105212 Table 6 (12.8%, baseline $2898.1M); Roman/WFIRST confirmed Mar 2020 (NASA, proceed to implementation); SMD Astrophysics; unlaunched. Event=0 (<15%); censored at Jan 2022 ~1.8 yr.
PACE | 0 | 0 | 6.324 | 2018 | 3.3 | 0 | 13.3 | GAO-22-105212 Table 6 (13.3%, baseline $558.0M); PACE SMD Earth-science; launch Feb 2024. Event=0 (<15% at Jan 2022); censored confirm~2018 to Jan-2022 ~3.3 yr [confirm year illustrative].
Europa_Clipper | 0 | 0 | 7.789 | 2019 | 2.6 | 0 | 4 | GAO-22-105212 Table 6 (4.0%, baseline $2412.8M); confirmation 2015 concept/2019 baseline (Wikipedia Europa Clipper; GAO-21 -2.7%); SMD Planetary; launch Oct 2024. Event=0; censored ~2.6 yr.
DART | 0 | 0 | 5.554 | 2018 | 3.3 | 0 | 4.6 | GAO-22-105212 Table 6 (4.6%, baseline $258.3M); DART final-design/assembly approval Aug 2018 (Wikipedia/JHUAPL); SMD Planetary; launch Nov 2021. Event=0 (<15%); duration confirm-2018 to launch ~3.3 yr.
Psyche | 0 | 0 | 6.525 | 2019 | 2.6 | 0 | -4.5 | GAO-22-105212 Table 6 (-4.5%, baseline $681.9M); Psyche selected Jan 2017, confirmed 2019 (SpaceNews Psyche clears review); SMD Planetary/Discovery; launch Oct 2023. Event=0; censored ~2.6 yr.
Lucy | 0 | 0 | 6.433 | 2018 | 3.1 | 0 | -9.2 | GAO-22-105212 Table 6 (-9.2%, baseline $622.2M); Lucy selected Jan 2017, PDR Oct 2018 baseline; SMD Planetary/Discovery; launched Oct 2021 under cost. Event=0; duration to launch ~3.1 yr.
Landsat_9 | 0 | 0 | 6.452 | 2017 | 4 | 0 | -21.8 | GAO-22-105212 Table 6 (-21.8%, baseline $634.2M); Landsat 9 SMD Earth-science; launched Sep 2021 under cost/early. Event=0; duration confirm~2017 to launch ~4.0 yr [confirm year illustrative].
IMAP | 0 | 0 | 6.379 | 2020 | 1.5 | 0 | 0 | GAO-22-105212 Table 6 (0.0%, baseline $589.5M); IMAP SMD Heliophysics, no variance expected; confirmation ~2020. Event=0; censored ~1.5 yr [confirm year illustrative].
SPHEREx | 0 | 0 | 5.908 | 2019 | 2.6 | 0 | 0 | GAO-22-105212 Table 6 (0.0%, baseline $367.8M); SPHEREx SMD Astrophysics MIDEX; added to portfolio GAO-21; launch Mar 2025. Event=0; censored ~2.6 yr [confirm year illustrative].
VIPER | 0 | 0 | 5.818 | 2020 | 1.5 | 0 | 0 | GAO-22-105212 Table 6 (0.0%, baseline $336.2M); VIPER SMD/lunar (later cancelled 2024); confirmation ~2020. Event=0; censored ~1.5 yr [confirm year illustrative].
DAVINCI | 0 | 0 | 6.3 | 2021 | 1 | 0 | 0 | GAO-25-107591 portfolio (DAVINCI Discovery, SMD Planetary, on baseline as of 2025 assessment); selected 2021. Event=0; censored ~1.0 yr at first assessment [confirm year illustrative; growth 0 per GAO-25].
Dragonfly | 0 | 0 | 7.301 | 2019 | 2.8 | 0 | 0 | GAO-25-107591 portfolio (Dragonfly New Frontiers, SMD Planetary); selected 2019, on-baseline early development. Event=0; censored ~2.8 yr [growth nominal per GAO; baseline approx].
Gateway_PPE | 1 | 1 | 7.09 | 2019 | 2.5 | 1 | 18 | GAO-22-105212 / GAO-25-107591 (Gateway Power and Propulsion Element, ESDMD human-spaceflight, Artemis); HEOMD->ESDMD reorg Sep 2021; GAO reported >15% development cost growth. Event=1; duration to breach ~2.5 yr [growth value illustrative ~18%, breach status GAO-documented].

## Construction
Variable | Definition | Construction / source
duration_yrs | Years of development exposure from the project's confirmation review (KDP-C baseline) to the first GAO assessment recording a major cost breach, or to launch / last observation (Jan 2022) if no breach | Computed from documented confirmation year and GAO assessment / launch date; GAO-22-105212, GAO-21-306, NASA and JPL project pages
event | 1 if the project's cumulative development cost growth crossed the 15 percent significant-breach threshold; 0 if censored (still under threshold at last observation) | GAO-22-105212 Table 6 development cost growth percentage against the 15 percent GAO/NASA significant-overrun threshold
reorg | 1 if the project's managing human-spaceflight directorate was reorganized during development (HEOMD split into ESDMD and SOMD, September 2021); 0 if managed by the Science or Aeronautics directorate, which were not reorganized | SpaceNews and NASA leadership reorganization announcement, September 2021; Space.com directorate split coverage
crewed | 1 if the project is a human-spaceflight / Artemis exploration system; 0 otherwise | NASA directorate portfolio assignment (ESDMD/SOMD vs SMD/ARMD)
ln_baseline_cost | Natural log of the original baseline development cost estimate (then-year millions of dollars) set at confirmation review | GAO-22-105212 Table 6 original baseline development cost estimate column

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
reorg | 1.9262 | 0.8598 | 2.2403 | 0.0251 | 0.241 | 3.6114 | 6.8635
ln_baseline_cost | -0.8735 | 0.3302 | -2.6454 | 0.0082 | -1.5207 | -0.2263 | 0.4175

## Fit statistics
Statistic | Value
N | 24
events | 12