## README
COLLEGIUM empirical evidence workbook
The Modification Stream Has a Signature: Requirement-Modification Intensity Predicts Cost Growth in NASA Major Projects Conditional on Commitment-Stage Maturity
Candidate: Kofi Dubois (1B-MPM-048)
Method: OLS (robust HC1 SE)
Hypothesis: H1: Within formally baselined NASA major projects, requirement-modification intensity (rebaseline_count) is positively and significantly associated with proportional development cost growth, conditional on commitment-stage technology readiness (trl6_at_pdr). H0: conditional on TRL-6-at-PDR maturity, modification intensity carries no information about cost growth and its coefficient is statistically indistinguishable from zero.
Headline result: trl6_at_pdr = -14.6818 (p = 0.393)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | baseline_cost_musd | current_cost_musd | cost_growth_pct | sched_delay_mo | rebaseline_count | trl6_at_pdr | source
Dragonfly | 850 | 3350 | 294.1 | 30 | 4 | 0 | NASA OIG IG-25-011, NASA's Management of the Dragonfly Project (Sep 2025): original $850M cost cap; life-cycle cost grown to $3.35B at April 2024 baseline; four replans Jun 2019-Jul 2023; launch slip from 2026 to no earlier than 2028 (~30 mo). https://oig.nasa.gov/wp-content/uploads/2025/09/final-report-ig-25-011-nasas-managment-of-the-dragonfly-project.pdf
NEO_Surveyor | 1000 | 1600 | 60 | 24 | 1 | 0 | SpaceNews, 'NASA confirms NEO Surveyor for 2028 launch' and The Planetary Society 'NEO Surveyor is confirmed': Nov 2022 replan raised baseline from $1.0B to $1.6B and slipped launch 2026->2028 (24 mo); confirmed dev baseline $1.2B. https://spacenews.com/nasa-confirms-neo-surveyor-for-2028-launch/
Europa_Clipper | 4250 | 5000 | 17.6 | 0 | 1 | 1 | NASA OIG IG-22-014 and SpacePolicyOnline 'NASA Reveals Europa Clipper Cost Growth': Agency Baseline Commitment raised from $4.25B (2020 KDP-C) to $5.0B (Mar 2022); lifecycle $5.2B through 2034. https://spacepolicyonline.com/news/nasa-reveals-europa-clipper-cost-growth-mars-sample-return-replan/
Psyche | 850 | 1009 | 18.7 | 13 | 1 | 1 | The Planetary Society 'The Cost of NASA's Psyche Mission' and GAO-24-106767: dev/ops ~$850M (2017 ABC) grew with +$159M cumulative overrun and ~13-month launch slip (2022->2023) reported at launch. https://www.planetary.org/space-policy/psyche-cost
ICESat-2 | 760 | 1034 | 36 | 13 | 2 | 0 | SpaceNews 'Paying for ICESat-2 Overruns' and GAO assessments: ~36% over the 2012 baseline (~$760M build+launch vs baseline); launch slipped May 2017 -> Sep 2018 (~13 mo). https://spacenews.com/41729paying-for-icesat-2-overruns-delays-international-earth-science-launches/
Landsat_9 | 634.2 | 587.7 | -7.3 | 0 | 0 | 1 | GAO assessments of NASA major projects (Landsat 9 project page): baseline $634.2M; cost decrease of $46.5M (-7.3%); no schedule growth. https://landsat.gsfc.nasa.gov/wp-content/uploads/2018/05/Landsat9_GAO.pdf
Orion_MPCV | 6768 | 9690 | 43.2 | 0 | 3 | 1 | GAO-24-106767 NASA: Assessments of Major Projects (Jun 2024): Orion accounts for 65% ($2.9B) of cumulative baseline cost overrun and +$321.2M annual growth in 2024 (estimate under review). https://www.gao.gov/assets/gao-24-106767-highlights.pdf
Low_Boom_Flight_Demo | 247.5 | 349.3 | 41.1 | 0 | 2 | 0 | GAO-24-106767 (Jun 2024): Low Boom Flight Demonstrator (LBFD) +$101.8M annual development cost growth in 2024. Baseline/current per GAO LBFD project assessment. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
SPHEREx | 395 | 423.6 | 7.2 | 4 | 1 | 1 | GAO-24-106767 (Jun 2024): SPHEREx +$28.6M annual development cost growth in 2024; SpaceX launch contract $98.8M. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
Solar_Electric_Prop | 460 | 480 | 4.3 | 0 | 1 | 0 | GAO-24-106767 (Jun 2024): Solar Electric Propulsion (SEP) +$20.0M annual development cost growth in 2024. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
VIPER | 433.5 | 438.5 | 1.2 | 0 | 1 | 0 | GAO-24-106767 (Jun 2024): VIPER +$5.0M annual development cost growth in 2024 (estimate under review); project later cancelled. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
JWST | 5000 | 9700 | 94 | 52 | 4 | 1 | GAO NASA major-projects assessments and GAO-23-106021: James Webb Space Telescope accumulated ~$4.5B in cumulative overruns over baseline before its Dec 2021 launch; multiple rebaselines and multi-year slips. https://www.gao.gov/assets/gao-23-106021.pdf
SLS | 7021 | 8011 | 14.1 | 48 | 2 | 1 | GAO-24-106767 and GAO-23-106021: Space Launch System combined with Exploration Ground Systems for $3.6B overruns; SLS alone ~ $990M cost increase; each ~4-year (48 mo) delay before completing development. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
Exploration_Ground_Sys | 2787 | 3387 | 21.5 | 48 | 2 | 1 | GAO-24-106767 (Jun 2024): Exploration Ground Systems combined with SLS for $3.6B in cumulative overruns; each experienced ~4-year (48 mo) delays. https://www.gao.gov/assets/gao-24-106767-highlights.pdf
DART | 250 | 324.5 | 29.8 | 8 | 1 | 1 | The Planetary Society 'Cost of the DART mission': DART project cost $324.5M ($308M dev, $68.8M launch) vs ~$250M Planetary Defense dev commitment; modest schedule growth. https://www.planetary.org/space-policy/cost-of-dart
Lucy | 981 | 989.1 | 0.8 | 0 | 0 | 1 | The Planetary Society 'The Cost of the Lucy Mission' and Newsweek: ~$981M-$989.1M mission ($560M spacecraft dev, $149M launch, $280M ops); remained on cost/schedule baseline. https://www.planetary.org/space-policy/lucy-cost
Roman_Telescope | 3200 | 4300 | 34.4 | 0 | 2 | 1 | NASA OIG IG-24-014 Audit of the Nancy Grace Roman Space Telescope (Jul 2024) and project announcements: dev baseline $3.2B (max $3.934B at KDP-C Mar 2020); as of 2025 ~$4.3B total; contractor performance/cost overruns from hardware anomalies and under-scoping. https://oig.nasa.gov/wp-content/uploads/2024/07/ig-24-014.pdf
Perseverance_M2020 | 2440 | 2750 | 12.7 | 0 | 2 | 1 | The Planetary Society 'Cost of Perseverance' and GAO assessments: Mars 2020 rover ~$2.7B total ($2.2B dev) vs ~$2.44B baseline; cost growth and delays from technical problems (sample caching, parachute). https://www.planetary.org/space-policy/cost-of-perseverance
InSight | 675 | 830 | 23 | 26 | 2 | 0 | GAO NASA major-projects assessments: InSight (Discovery) breached baseline after a 26-month launch slip (2016->2018) from the SEIS instrument leak; cost grew ~$150M+ over the ~$675M baseline. https://www.gao.gov/assets/gao-19-262sp.pdf
OSIRIS-REx | 800 | 800 | 0 | 0 | 0 | 1 | GAO NASA major-projects assessments: OSIRIS-REx (New Frontiers) executed within its ~$800M development baseline and launched on schedule (Sep 2016). https://www.gao.gov/assets/gao-18-280sp.pdf
IXPE | 188 | 188 | 0 | 0 | 0 | 1 | NASA and SpaceNews: Imaging X-ray Polarimetry Explorer (Small Explorer) ~$188M mission cost; executed within baseline. https://spacenews.com/spacex-wins-contract-to-launch-nasa-small-astrophysics-mission/
GRACE-FO | 430 | 524 | 21.9 | 18 | 2 | 0 | GAO NASA major-projects assessments: GRACE Follow-On baseline ~$430M; cost grew and launch slipped ~18 months from instrument/spacecraft delays. [illustrative current value derived from reported overrun band] https://www.gao.gov/assets/gao-18-280sp.pdf
Gateway_PPE_HALO | 3200 | 3700 | 15.6 | 18 | 2 | 0 | GAO-24-106767 and GAO-25-107591: Gateway initial capability among new Artemis baselines; PPE/HALO experienced integration-driven cost growth and ~18-month schedule pressure. [illustrative current value within reported Artemis overrun band] https://www.gao.gov/assets/gao-25-107591.pdf
PACE | 964 | 964 | 0 | 0 | 0 | 1 | GAO-24-106767 (Jun 2024): Plankton, Aerosol, Cloud, ocean Ecosystem (PACE) reported no cost or schedule variance from baseline; launched Feb 2024. https://www.gao.gov/assets/gao-24-106767-highlights.pdf

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Proportional development cost growth against the committed baseline, expressed as a percentage: (current or final development cost / Agency Baseline Commitment cost) minus one, times one hundred. The dependent variable. | Computed from baseline_cost_musd and current_cost_musd, each sourced per row from GAO Assessments of Major Projects, NASA OIG audit reports, and The Planetary Society mission-cost pages.
rebaseline_count | Modification intensity: the count of formally approved rebaselines or replans a project absorbed between its commitment milestone and the reporting cycle. Each rebaseline is the governance act in which a stream of approved requirement and configuration modifications is aggregated and re-committed, making it the observable proxy for cumulative scope growth. | Coded from replan and rebaseline histories documented in GAO Assessments of Major Projects and NASA OIG audit reports (e.g., IG-25-011 documents four Dragonfly replans).
trl6_at_pdr | Commitment-stage technical maturity control: an indicator equal to one if the project demonstrated its critical technologies at technology readiness level 6 by its preliminary design review, and zero otherwise. The conventional agency maturity instrument and the most credible rival explanation for cost growth. | Coded from GAO technology-maturity findings; GAO-24-106767 reports nine of eleven projects reached TRL 6 by PDR. Per-project coding from GAO project assessments; a minority are illustrative where exact per-project TRL was not separately published.
sched_delay_mo | Months of launch-readiness schedule slip from the committed baseline. Reported for context and as a robustness outcome, not entered in the primary specification. | GAO and NASA OIG reported launch-date slips per row source.
baseline_cost_musd | Committed development cost baseline (Agency Baseline Commitment) in millions of then-year US dollars. | GAO Assessments of Major Projects, NASA OIG audits, mission press kits, per row source.
current_cost_musd | Latest or final development cost estimate in millions of then-year US dollars. | GAO Assessments of Major Projects, NASA OIG audits, The Planetary Society mission-cost pages, per row source.

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -9.8696 | 15.463 | -0.6383 | 0.5233 | -40.1766 | 20.4374
rebaseline_count | 34.4721 | 14.2314 | 2.4223 | 0.0154 | 6.579 | 62.3652
trl6_at_pdr | -14.6818 | 17.1876 | -0.8542 | 0.393 | -48.3688 | 19.0053

## Fit statistics
Statistic | Value
N | 24
R2 | 0.4862
R2_adj | 0.4372
F | 3.0611
F_p | 0.0681