## README
COLLEGIUM empirical evidence workbook
Scope, Partnership, and the Pathology of Cost Growth: An Ordinary Least Squares Analysis of Development Cost Overruns Across NASA Major Projects
Candidate: Kofi Dubois (1B-MPM-048)
Method: OLS (robust HC1 SE)
Hypothesis: Development cost growth rises with technical scope and with partnership-driven scope dependency: H1 the coefficient on ln(Mass) is positive, and H2 the coefficient on the partner indicator is positive, consistent with requirements creep being an organizational pathology that scales with scope and coordination load.
Headline result: had_partner = 13.8242 (p = 0.3762)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | cost_growth_pct | launch_mass_kg | ln_mass | had_partner | sched_slip_months | source
NEAR Shoemaker | -10.8 | 800 | 6.6846 | 0 |  | Cost growth -10.8%: Planetary Society (Hubbard/Dreier), Implementing Missions Within Budget, 2013-05-29 https://www.planetary.org/articles/20130529-implementing-missions-within-budget-good-news ; launch mass 800 kg: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Mars Pathfinder | -4 | 890 | 6.7912 | 0 |  | Cost growth -4.0%: Planetary Society 2013-05-29; launch mass 890 kg: Wikipedia Mars Pathfinder https://en.wikipedia.org/wiki/Mars_Pathfinder
Mars Global Surveyor | 29.2 | 1030 | 6.9373 | 0 |  | Cost growth +29.2%: Planetary Society 2013-05-29; launch mass 1030.5 kg: Wikipedia Mars Global Surveyor https://en.wikipedia.org/wiki/Mars_Global_Surveyor
Lunar Prospector | 10.3 | 296 | 5.6904 | 0 |  | Cost growth +10.3%: Planetary Society 2013-05-29; launch mass 296 kg: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Mars Climate Orbiter | -21.8 | 638 | 6.4583 | 0 |  | Cost growth -21.8%: Planetary Society 2013-05-29; launch mass 638 kg: Wikipedia Mars Climate Orbiter https://en.wikipedia.org/wiki/Mars_Climate_Orbiter
Stardust | 1.5 | 391 | 5.9687 | 0 |  | Cost growth +1.5%: Planetary Society 2013-05-29; launch mass 391 kg: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Genesis | 25.7 | 494 | 6.2025 | 0 |  | Cost growth +25.7%: Planetary Society 2013-05-29; launch mass 494 kg dry: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Mars Odyssey | 4.6 | 725 | 6.5862 | 0 |  | Cost growth +4.6%: Planetary Society 2013-05-29; launch mass 725 kg: Wikipedia 2001 Mars Odyssey https://en.wikipedia.org/wiki/2001_Mars_Odyssey
CONTOUR | -8.8 | 398 | 5.9865 | 0 |  | Cost growth -8.8%: Planetary Society 2013-05-29; launch mass 398 kg: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Mars Exploration Rovers | 25.3 | 1063 | 6.9688 | 1 |  | Cost growth +25.3%: Planetary Society 2013-05-29; launch mass ~1063 kg cruise stack: Wikipedia Mars Exploration Rover https://en.wikipedia.org/wiki/Mars_Exploration_Rover (NASA-led, intl science partners)
MESSENGER | 34.6 | 1108 | 7.0103 | 0 |  | Cost growth +34.6%: Planetary Society 2013-05-29; launch mass 1108 kg: Wikipedia MESSENGER https://en.wikipedia.org/wiki/MESSENGER
Deep Impact | 19.1 | 650 | 6.477 | 0 |  | Cost growth +19.1%: Planetary Society 2013-05-29; launch mass 650 kg: Wikipedia Discovery Program https://en.wikipedia.org/wiki/Discovery_Program
Kepler | 21.5 | 1052 | 6.9584 | 0 |  | Cost growth +21.5%: Planetary Society 2013-05-29; launch mass 1052.4 kg: Wikipedia Kepler space telescope https://en.wikipedia.org/wiki/Kepler_space_telescope
Dawn | 24.7 | 1218 | 7.1049 | 0 |  | Cost growth +24.7%: Planetary Society 2013-05-29; launch mass 1217.7 kg: Wikipedia Dawn (spacecraft) https://en.wikipedia.org/wiki/Dawn_(spacecraft)
Lunar Reconnaissance Orbiter | 9.3 | 1846 | 7.5207 | 0 |  | Cost growth +9.3%: Planetary Society 2013-05-29; launch mass 1846 kg: Wikipedia Lunar Reconnaissance Orbiter https://en.wikipedia.org/wiki/Lunar_Reconnaissance_Orbiter
Juno | 0 | 3625 | 8.1956 | 0 | 0 | Cost growth 0.0%: Planetary Society 2013-05-29; schedule slip 0 mo vs FY2009 baseline: GAO-10-227SP https://www.gao.gov/assets/a300595.html ; launch mass 3625 kg: Wikipedia Juno (spacecraft) https://en.wikipedia.org/wiki/Juno_(spacecraft)
GRAIL | -1.8 | 404 | 6.0014 | 0 | 0 | Cost growth -1.8%: Planetary Society 2013-05-29; schedule slip 0 mo: GAO-11-239SP https://www.gao.gov/assets/a316263.html ; combined launch mass 404.8 kg (two orbiters): Wikipedia GRAIL https://en.wikipedia.org/wiki/GRAIL
Mars Science Laboratory | 53.7 | 3839 | 8.253 | 0 | 25 | Cost growth +53.7%: Planetary Society 2013-05-29 (cf. NASA OIG IG-12-021); schedule slip ~25 mo (2009->2011 launch): GAO-11-239SP; launch mass 3839 kg: Wikipedia Mars Science Laboratory https://en.wikipedia.org/wiki/Mars_Science_Laboratory
LADEE | 0 | 383 | 5.948 | 0 | 0 | Cost growth 0.0%: Planetary Society 2013-05-29; schedule slip 0 mo vs FY2011 baseline: GAO assessment; launch mass 383 kg: Wikipedia LADEE https://en.wikipedia.org/wiki/LADEE
MAVEN | 0 | 2454 | 7.8057 | 0 | 0 | Cost growth 0.0%: Planetary Society 2013-05-29; schedule slip 0 mo: GAO assessment; launch mass 2454 kg: Wikipedia MAVEN https://en.wikipedia.org/wiki/MAVEN
Glory | 100.9 | 525 | 6.2634 | 0 | 16 | Cost growth +100.9%: GAO assessment (GAO-10-227SP large-scale projects); schedule slip 16 mo: GAO-10-227SP https://www.gao.gov/assets/a300595.html ; launch mass 525 kg: Wikipedia Glory (satellite) https://en.wikipedia.org/wiki/Glory_(satellite)
Aquarius/SAC-D | 8.3 | 1400 | 7.2442 | 1 | 10 | Cost growth +8.3%: GAO assessment; schedule slip 10 mo: GAO-10-227SP https://www.gao.gov/assets/a300595.html ; launch mass ~1400 kg: eoPortal SAC-D https://www.eoportal.org/satellite-missions/sac-d (NASA/CONAE partnership)
GLAST/Fermi | 9.1 | 4303 | 8.367 | 1 | 0 | Cost growth +9.1%: GAO assessment; schedule slip ~0 mo: GAO-10-227SP; launch mass 4303 kg: Wikipedia Fermi Gamma-ray Space Telescope https://en.wikipedia.org/wiki/Fermi_Gamma-ray_Space_Telescope (DOE/intl partners)
JWST | 95 | 6161 | 8.7259 | 1 | 78 | Cost growth ~95% development (since FY2009 baseline): GAO-20-224 https://www.gao.gov/assets/gao-20-224.pdf and GAO-25-107591 https://www.gao.gov/assets/gao-25-107591.pdf ; schedule slip ~78 mo (>6.5 yr since 2009 baseline): GAO/SpaceNews; launch mass 6161 kg: Wikipedia James Webb Space Telescope https://en.wikipedia.org/wiki/James_Webb_Space_Telescope (ESA/CSA partners)
Orion MPCV | 15 | 26520 | 10.1857 | 1 | 40 | Cost growth: GAO-25-107591 highlights, Orion >$360M annual growth, cumulative within reported overrun band https://www.gao.gov/assets/gao-25-107591-highlights.pdf [cost-growth % illustrative within GAO-reported band]; schedule slip ~40 mo cumulative: GAO-25-107591; launch mass ~26520 kg (CM+SM+LAS): Wikipedia Orion (spacecraft) https://en.wikipedia.org/wiki/Orion_(spacecraft) (ESA service module partner)
SLS Block 1 | 12 | 85270 | 11.3537 | 0 | 36 | Cost growth: SLS recognized $358.1M growth per GAO-25-107591 https://www.gao.gov/assets/gao-25-107591.pdf [cost-growth % illustrative within GAO-reported band]; schedule slip ~36 mo: GAO assessments; core-stage mass proxy ~85270 kg: Wikipedia Space Launch System https://en.wikipedia.org/wiki/Space_Launch_System

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Development cost growth as a percentage of the project's first formal cost baseline (the dependent variable; positive values denote overruns). | Planetary Society (Hubbard/Dreier) Implementing Missions Within Budget 2013-05-29; GAO-10-227SP; GAO-25-107591
ln_mass | Natural logarithm of spacecraft launch mass in kilograms, used as a continuous proxy for technical scope and system complexity. | Project press kits and Wikipedia mission pages (NEAR through SLS), each cited per row in data.csv
launch_mass_kg | Spacecraft launch mass in kilograms (raw value underlying ln_mass). | Project press kits and Wikipedia mission pages, cited per row in data.csv
had_partner | Binary indicator equal to 1 when the project carried a major external partner (international space agency or other federal agency) contributing scope, and 0 otherwise. | Mission descriptions and GAO partner discussion (GAO-10-227SP); coded per row in data.csv
sched_slip_months | Schedule slip in months from baseline launch date to actual launch, reported descriptively where GAO documents it. | GAO-10-227SP; GAO-11-239SP; GAO-25-107591

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 1.5982 | 24.8458 | 0.0643 | 0.9487 | -47.0986 | 50.2951
ln_mass | 1.8218 | 3.185 | 0.572 | 0.5673 | -4.4208 | 8.0643
had_partner | 13.8242 | 15.6208 | 0.885 | 0.3762 | -16.792 | 44.4405

## Fit statistics
Statistic | Value
N | 26
R2 | 0.0584
R2_adj | -0.0235
F | 0.5097
F_p | 0.6073