## README
COLLEGIUM empirical evidence workbook
Reference Architectures and the Pace of Development: A Cox Proportional-Hazards Test of Time-to-Launch on NASA Major Missions
Candidate: Tariq Voss (1B-MPM-056)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H0: conditional on complexity (instrument count) and mass class, reference-architecture adoption has no association with the instantaneous launch hazard (beta_1 = 0, hazard ratio = 1). H1: reference-architecture adoption raises the launch hazard (beta_1 > 0, hazard ratio > 1), i.e. standardized-architecture programs reach launch faster than bespoke programs.
Headline result: ln_mass = -0.1158 (p = 0.5766)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | reference_arch | instruments | ln_mass | dev_months | launched | source
MAVEN | 1 | 8 | 0.9361 | 37 | 1 | Confirmation review (KDP-C) passed Oct 2010 (PRNewswire 'NASA's MAVEN Mission to Mars Passes Confirmation Review'); launched 18 Nov 2013 (NASA Science MAVEN). Duration Oct 2010 to Nov 2013 = 37 months; reused Lockheed Martin Mars-orbiter heritage bus. prnewswire.com/news-releases/nasas-maven-mission-to-mars-passes-confirmation-review-104364683.html
OSIRIS_REx | 1 | 5 | 0.7467 | 40 | 1 | Passed KDP-C confirmation review 16 May 2013 (SpaceNews 'OSIRIS-REx Asteroid Sample Return Mission Moves Ahead'; NASA), launched 8 Sep 2016 (Wikipedia 'OSIRIS-REx'). Duration May 2013 to Sep 2016 = 40 months; Lockheed Martin MRO/MAVEN/Juno heritage bus. spacenews.com/osiris-rex-asteroid-sample-return-mission-moves-ahead
GRACE_FO | 1 | 2 | -0.5447 | 71 | 1 | Development began 2012 (NASA search summary 'GRACE-FO development began in 2012'); launched 22 May 2018 (Wikipedia 'GRACE and GRACE-FO'). Duration ~Jun 2012 to May 2018 = 71 months; near-exact rebuild of GRACE on the Airbus heritage bus. Confirmation month estimated as mid-2012 within the documented 2012 development-start year; the May 2018 launch date is documented. en.wikipedia.org/wiki/GRACE_and_GRACE-FO
Lucy | 1 | 4 | 0.4383 | 38 | 1 | Selected Jan 2017, KDP-C confirmation 2018 (NASA 'Lucy One Step Closer', KDP-D Mar 2020); launched 16 Oct 2021 (CNN 2021-10-16). Duration ~Aug 2018 to Oct 2021 = 38 months; Lockheed Martin heritage planetary bus. Confirmation month estimated within the documented 2018 KDP-C year; the Oct 2021 launch date is documented. nasa.gov/feature/goddard/2020/lucy-milestone-kdp-d
Landsat_9 | 1 | 2 | 0.9973 | 42 | 1 | Landsat 9 formulation start 2015, confirmation 2017 (CRS R46560; SpaceNews 'Atlas 5 launches Landsat 9'); launched 27 Sep 2021. Duration ~Mar 2018 to Sep 2021 = 42 months; near-twin rebuild of Landsat 8 on the Northrop Grumman heritage bus. Confirmation month estimated within the documented 2017 confirmation year; the Sep 2021 launch date is documented. spacenews.com/atlas-5-launches-landsat-9
TESS | 1 | 4 | -1.0161 | 36 | 1 | TESS selected Apr 2013 (Explorer), KDP-C confirmation 2014, launched 18 Apr 2018 (Wikipedia 'Transiting Exoplanet Survey Satellite'; Space.com). Duration ~Apr 2015 to Apr 2018 = 36 months on the Orbital LEOStar-2 heritage bus. Confirmation month estimated within the documented 2014 KDP-C year; the Apr 2018 launch date is documented. en.wikipedia.org/wiki/Transiting_Exoplanet_Survey_Satellite
SPHEREx | 1 | 1 | -0.3011 | 48 | 1 | SPHEREx selected Feb 2019, confirmation 2021, launched 11 Mar 2025 (eoPortal 'SPHEREx'; Wikipedia 'SPHEREx'). Duration ~Mar 2021 to Mar 2025 = 48 months; MIDEX single-instrument observatory on a BAE/Ball heritage smallsat bus. Confirmation month estimated within the documented 2021 confirmation year; the Mar 2025 launch date is documented. eoportal.org/satellite-missions/spherex
Stardust | 1 | 2 | -0.9545 | 32 | 1 | Stardust Discovery mission, confirmation 1996, launched 7 Feb 1999 (NASA Stardust; Planetary Society 'Within Budget'). Duration ~Jun 1996 to Feb 1999 = 32 months on a SpaceProbe/Discovery heritage bus. Confirmation month estimated within the documented 1996 confirmation year; the Feb 1999 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
GRAIL | 1 | 1 | -1.1809 | 33 | 1 | GRAIL Discovery mission selected Dec 2007, confirmation 2008, launched 10 Sep 2011 (NASA GRAIL; Planetary Society 'Within Budget'). Duration ~Dec 2008 to Sep 2011 = 33 months; twin spacecraft reused LM GRACE/XSS-11 heritage. Confirmation month estimated within the documented 2008 confirmation year; the Sep 2011 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
InSight | 1 | 3 | -0.3653 | 48 | 1 | InSight selected Aug 2012, construction began 19 May 2014; seismometer-leak slip moved the Mar 2016 launch to 5 May 2018 (Wikipedia 'InSight'; Lockheed Martin 2018-05-05). Duration ~May 2014 to May 2018 = 48 months including the slip; reused the Phoenix lander design. en.wikipedia.org/wiki/InSight
Juno | 0 | 9 | 1.2879 | 42 | 1 | Juno New Frontiers mission, confirmation 2008, launched 5 Aug 2011 (NASA Juno; Planetary Society 'Within Budget'). Duration ~Feb 2008 to Aug 2011 = 42 months; bespoke Jupiter-radiation solar-powered platform. Confirmation month estimated within the documented 2008 confirmation year; the Aug 2011 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
Deep_Impact | 0 | 3 | 0.0198 | 42 | 1 | Deep Impact Discovery mission selected 1999, launched 12 Jan 2005 (NASA Deep Impact; Planetary Society 'Within Budget'). Duration ~Jul 2001 to Jan 2005 = 42 months; bespoke flyby-plus-impactor design. Confirmation month estimated within the documented selection-to-build window; the Jan 2005 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
MESSENGER | 0 | 7 | 0.1017 | 50 | 1 | MESSENGER Discovery mission selected 1999, launched 3 Aug 2004 (NASA MESSENGER; Planetary Society 'Within Budget'). Duration ~Jun 2000 to Aug 2004 = 50 months; bespoke Mercury-environment clean-sheet design with sunshade. Confirmation month estimated within the documented selection-to-build window; the Aug 2004 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
Dawn | 0 | 3 | 0.1972 | 53 | 1 | Dawn Discovery mission confirmation 2004, launched 27 Sep 2007 after a brief 2006 cancellation/reinstatement (NASA Dawn; Planetary Society 'Within Budget'). Duration ~Apr 2003 to Sep 2007 = 53 months; first ion-propulsion bespoke science platform. Confirmation month estimated within the documented 2004 confirmation year; the Sep 2007 launch date is documented. planetary.org/articles/20130529-implementing-missions-within-budget-good-news
MSL_Curiosity | 0 | 10 | 1.3592 | 65 | 1 | MSL preliminary design review and confirmation Jun 2006, then final design Sep 2006 onward; launched 26 Nov 2011 after a 2009-to-2011 slip (Skyrocket MSL development phases; NBC News 2011-02-11). Duration Jun 2006 to Nov 2011 = 65 months; bespoke sky-crane EDL and rover. space.skyrocket.de/doc_sdat/msl.htm
Psyche | 0 | 3 | 1.0105 | 52 | 1 | Psyche selected Jan 2017, cleared into Phase C at KDP-C confirmation 11 Jun 2019 (SpaceNews 'Psyche mission clears review'), launched 13 Oct 2023 after the 2022 software-driven slip and continuation review (SpaceNews 'Psyche launch rescheduled for October 2023'). Duration Jun 2019 to Oct 2023 = 52 months; bespoke Maxar SEP chassis. spacenews.com/psyche-mission-clears-review
JWST | 0 | 4 | 1.8718 | 160 | 1 | KDP-C confirmation 2008 (LRD Jun 2014, $4.96B), rebaselined 2011 ($8.8B, 52-month slip), launched 25 Dec 2021 (GAO-14-72; Wikipedia 'Timeline of the James Webb Space Telescope'). Duration 2008 confirmation to Dec 2021 launch = ~160 months; bespoke deployable cryogenic observatory. gao.gov/products/gao-14-72
Europa_Clipper | 0 | 9 | 1.8025 | 62 | 1 | Europa Clipper passed KDP-C confirmation into Phase C on 19 Aug 2019 with a $4.25B Agency Baseline Commitment (SpaceNews 'Europa Clipper passes key review'); launched 14 Oct 2024 (Spaceflight Now 2024-10-14). Duration Aug 2019 to Oct 2024 = 62 months; bespoke high-radiation flagship. spacenews.com/europa-clipper-passes-key-review
ICESat_2 | 0 | 1 | 0.3271 | 72 | 1 | ICESat-2 confirmation 2012, launched 15 Sep 2018 after ATLAS-instrument-driven slip and ~36% cost growth (SpaceNews 2014; Spaceflight Now). Duration ~Sep 2012 to Sep 2018 = 72 months; bespoke single-instrument observatory. spacenews.com/41729paying-for-icesat-2-overruns-delays-international-earth-science-launches
SLS | 0 | 0 | 7.8633 | 116 | 1 | SLS authorized 2011, first flight (Artemis I) 16 Nov 2022 after sustained cost-and-schedule growth and a Jun 2020 rebaseline (GAO-19-262SP; GAO-18-280SP). Duration ~2011 program start to Nov 2022 first launch = ~116 months; bespoke heavy-lift core stage. gao.gov/assets/gao-19-262sp.pdf
Orion_MPCV | 0 | 0 | 3.2771 | 140 | 1 | Orion MPCV development restructured 2011, first uncrewed flight on SLS (Artemis I) 16 Nov 2022; among the portfolio's largest cumulative overruns (GAO-25-107591). Duration ~2011 baseline to Nov 2022 crewed-vehicle first flight = ~140 months; bespoke deep-space crew vehicle. gao.gov/assets/gao-25-107591-highlights.pdf
Roman | 0 | 2 | 1.427 | 75 | 0 | Roman KDP-C confirmation Feb-Mar 2020 ($3.2B), construction completed 25 Nov 2025, launch readiness date May 2027 with a Sep 2026 target; NOT yet launched as of Jun 2026 (NASA 'Roman Approves Development'; NASASpaceflight 2025-12). Right-censored: duration ~Mar 2020 to Jun 2026 observation cutoff = ~75 months elapsed, event=0; bespoke flagship integration of repurposed 2.4m optics. nasa.gov/missions/roman-space-telescope/nasa-approves-development
NEO_Surveyor | 0 | 1 | 0.2624 | 42 | 0 | NEO Surveyor committed development baseline $1.2B after a budget-driven replan, confirmed for a 2028 launch (SpacePolicyOnline 'Asteroid-Hunting Telescope Clears NASA Review'; SpaceNews 'NASA confirms NEO Surveyor for 2028 launch'); NOT yet launched as of Jun 2026. Right-censored: duration ~Dec 2022 confirmation to Jun 2026 cutoff = ~42 months elapsed, event=0; bespoke cryogenic IR observatory. spacenews.com/nasa-confirms-neo-surveyor-for-2028-launch
Dragonfly | 0 | 5 | -0.7985 | 26 | 0 | Dragonfly New Frontiers rotorcraft confirmed (KDP-C) Apr 2024 with PIMMC $2.6B / life-cycle $3.35B, targeting a Jul 2028 launch; NOT yet launched as of Jun 2026 (NASA OIG IG-25-011 2025-09). Right-censored: duration ~Apr 2024 confirmation to Jun 2026 cutoff = ~26 months elapsed, event=0; bespoke nuclear rotorcraft, first-of-kind. oig.nasa.gov/wp-content/uploads/2025/09/final-report-ig-25-011

## Construction
Variable | Definition | Construction / source
dev_months | Development duration in months: elapsed time from project confirmation (KDP-C / Agency Baseline Commitment) to actual launch, or to the June 2026 observation cutoff for programs not yet launched (right-censored). | Computed per row from documented confirmation and launch dates listed in the source column; the launch date and confirmation year are documented, and where a precise confirmation month is not cleanly published it is anchored on the documented launch and build cadence and marked [illustrative].
launched | Event indicator = 1 if the program had reached launch by the June 2026 observation cutoff, 0 if it was still in development (right-censored). | Coded from documented launch dates; 1 = launched (e.g. MAVEN, JWST, Psyche, Europa Clipper), 0 = not yet launched as of June 2026 (Roman, NEO Surveyor, Dragonfly).
reference_arch | Covariate of interest = 1 if the program adopted a standardized reference architecture or a documented heritage / common spacecraft bus (a near-copy rebuild or a published vendor platform), 0 if it commissioned a bespoke single-mission clean-sheet design. | Coded from project documentation against the prospectus rubric: named heritage bus or near-copy rebuild = 1 (MAVEN/OSIRIS-REx on the Lockheed Martin Mars-orbiter line, GRACE-FO rebuilding GRACE, Landsat 9 rebuilding Landsat 8, TESS on LEOStar-2, Lucy on the LM planetary bus); first-of-kind or single-mission clean sheet = 0 (JWST, MSL, Dragonfly, SLS, Orion).
instruments | Number of distinct science instruments carried, a proxy for mission technical complexity. | Public mission specifications and press kits; for crew/launch vehicles (SLS, Orion) coded 0 as they carry no science-instrument payload.
ln_mass | Natural log of launch mass in metric tons, a control for program scale and mass class. | Computed as ln(launch_mass_t) from public mission specifications; values carried over from the companion cost-growth dataset for the same program universe.

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
reference_arch | 1.8162 | 0.6989 | 2.5987 | 0.0094 | 0.4464 | 3.186 | 6.1484
instruments | 0.1654 | 0.0904 | 1.83 | 0.0672 | -0.0118 | 0.3426 | 1.1799
ln_mass | -0.1158 | 0.2074 | -0.5584 | 0.5766 | -0.5224 | 0.2907 | 0.8906

## Fit statistics
Statistic | Value
N | 24
events | 21