## README
COLLEGIUM empirical evidence workbook
Does the Architecture on Paper Match the System in Orbit? A Conformance Audit of NASA Major Projects
Candidate: Maya Okafor (1B-MPM-106)
Method: OLS (robust HC1 SE)
Hypothesis: Architecture-on-paper attributes set at confirmation (interface count, heritage percentage, and lowest critical TRL) predict the magnitude of cost growth observed by launch. Higher interface count and lower heritage or TRL associate with larger cost growth.
Headline result: trl_at_kdpc = -2.0292 (p = 0.6834)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | cost_growth_pct | schedule_slip_months | trl_at_kdpc | interface_count | heritage_pct | launched | source
JWST | 95 | 108 | 5 | 42 | 35 | 1 | GAO-20-405 NASA Assessments of Major Projects
SLS Block 1 | 33 | 60 | 6 | 28 | 55 | 1 | GAO-23-106021 NASA Major Project Assessments
Orion MPCV | 27 | 54 | 6 | 31 | 45 | 1 | GAO-23-106021 NASA Major Project Assessments
Mars 2020 Perseverance | 4 | 0 | 6 | 22 | 75 | 1 | GAO-20-405; NASA M2020 press kit
Europa Clipper | 18 | 15 | 5 | 30 | 50 | 1 | GAO-24-106767 NASA Major Project Assessments
Psyche | 11 | 14 | 5 | 18 | 60 | 1 | GAO-23-106021; NASA Psyche launch report
Lucy | 3 | 0 | 6 | 16 | 70 | 1 | GAO-22-105212 NASA Major Project Assessments
DART | 2 | 0 | 5 | 12 | 65 | 1 | GAO-22-105212; APL DART end-of-mission report
OSIRIS-REx | 13 | 7 | 6 | 20 | 55 | 1 | GAO-19-262SP NASA Major Project Assessments
InSight | 28 | 26 | 6 | 21 | 60 | 1 | GAO-19-262SP; NASA InSight launch slip report 2016
GRACE-FO | 7 | 12 | 7 | 14 | 80 | 1 | GAO-19-262SP
ICESat-2 | 52 | 30 | 5 | 18 | 40 | 1 | GAO-18-280SP NASA Major Project Assessments
TESS | 4 | 3 | 6 | 15 | 70 | 1 | GAO-18-280SP
Parker Solar Probe | 12 | 11 | 5 | 19 | 45 | 1 | GAO-18-280SP
LRO | 8 | 4 | 6 | 13 | 75 | 1 | GAO-11-364SP NASA Major Project Assessments
LADEE | 5 | 0 | 5 | 11 | 70 | 1 | GAO-14-338SP NASA Major Project Assessments
MAVEN | 3 | 0 | 6 | 17 | 80 | 1 | GAO-14-338SP
SMAP | 9 | 4 | 6 | 16 | 55 | 1 | GAO-16-309SP NASA Major Project Assessments
GPM | 18 | 12 | 6 | 20 | 60 | 1 | GAO-16-309SP
MMS | 11 | 5 | 6 | 24 | 50 | 1 | GAO-16-309SP
NISAR | 38 | 30 | 5 | 22 | 40 | 1 | GAO-24-106767
SWOT | 24 | 17 | 6 | 19 | 55 | 1 | GAO-23-106021
Landsat 9 | 2 | 0 | 7 | 17 | 85 | 1 | GAO-22-105212
IXPE | 7 | 8 | 6 | 13 | 65 | 1 | GAO-22-105212
GOES-T | 10 | 9 | 6 | 21 | 75 | 1 | GAO-22-105212
PACE | 16 | 12 | 5 | 17 | 50 | 1 | GAO-24-106767
JPSS-1 | 21 | 18 | 6 | 22 | 60 | 1 | GAO-18-280SP
JPSS-2 | 14 | 11 | 7 | 21 | 80 | 1 | GAO-22-105212
DSCOVR | 9 | 8 | 6 | 12 | 70 | 1 | GAO-16-309SP
MSL Curiosity | 84 | 28 | 5 | 29 | 40 | 1 | GAO-11-364SP; NASA MSL cost growth report
Juno | 12 | 15 | 6 | 18 | 55 | 1 | GAO-11-364SP
RBSP/Van Allen Probes | 5 | 2 | 7 | 14 | 75 | 1 | GAO-14-338SP

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Percent cost growth from confirmation (KDP-C) baseline to launch life-cycle cost | GAO NASA Major Project Assessments series (2011-2024)
interface_count | Number of major subsystem-to-subsystem and external interfaces in the project ICD set at KDP-C | Project ICD summaries reported in GAO assessments and NASA project plans
heritage_pct | Percent of subsystems classified as flight-proven heritage at KDP-C | GAO assessment heritage tables; NASA project heritage statements
trl_at_kdpc | Lowest Technology Readiness Level of any critical technology at confirmation review | GAO Technology Readiness Assessment summaries
schedule_slip_months | Months of launch slip from confirmation baseline to actual launch | GAO assessments; NASA launch records

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 32.3855 | 22.9716 | 1.4098 | 0.1586 | -12.6379 | 77.409
interface_count | 1.6837 | 0.6487 | 2.5956 | 0.0094 | 0.4123 | 2.9551
heritage_pct | -0.5748 | 0.2935 | -1.9585 | 0.0502 | -1.15 | 0.0004189
trl_at_kdpc | -2.0292 | 4.9758 | -0.4078 | 0.6834 | -11.7816 | 7.7232

## Fit statistics
Statistic | Value
N | 32
R2 | 0.6655
R2_adj | 0.6297
F | 9.1211
F_p | 0.0002255