## README
COLLEGIUM empirical evidence workbook
Time-to-Launch Under Architectural Stress: A Cox Proportional-Hazards Audit of NASA Major Projects
Candidate: Maya Okafor (1B-MPM-106)
Method: Cox proportional-hazards (PHReg)
Hypothesis: The hazard of reaching launch is lower for NASA major projects whose paper architecture exhibits higher interface count and lower heritage or critical TRL at confirmation. Architecturally stressed projects are slower to leave development.
Headline result: trl_at_kdpc = 0.1584 (p = 0.7921)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | duration_months | launched | interface_count | heritage_pct | trl_at_kdpc | cost_growth_pct | source
JWST | 228 | 1 | 42 | 35 | 5 | 95 | GAO-20-405 NASA Assessments of Major Projects (2020)
SLS Block 1 | 144 | 1 | 28 | 55 | 6 | 33 | GAO-23-106021 NASA Major Project Assessments (2023)
Orion MPCV | 180 | 1 | 31 | 45 | 6 | 27 | GAO-23-106021 NASA Major Project Assessments (2023)
Mars 2020 Perseverance | 72 | 1 | 22 | 75 | 6 | 4 | GAO-20-405; NASA Mars 2020 press kit
OSIRIS-REx | 84 | 1 | 18 | 70 | 6 | 7 | GAO-16-309SP NASA Assessments of Major Projects (2016)
InSight | 96 | 1 | 16 | 80 | 6 | 29 | GAO-19-262SP NASA Assessments of Major Projects (2019)
Parker Solar Probe | 84 | 1 | 20 | 40 | 5 | 15 | GAO-19-262SP NASA Assessments of Major Projects (2019)
ICESat-2 | 108 | 1 | 14 | 60 | 5 | 40 | GAO-19-262SP NASA Assessments of Major Projects (2019)
GRACE-FO | 72 | 1 | 12 | 85 | 6 | 12 | GAO-18-280SP NASA Assessments of Major Projects (2018)
TESS | 60 | 1 | 15 | 70 | 5 | 6 | GAO-18-280SP NASA Assessments of Major Projects (2018)
Landsat 9 | 72 | 1 | 17 | 80 | 6 | 3 | GAO-22-105212 NASA Major Project Assessments (2022)
Lucy | 72 | 1 | 19 | 65 | 6 | 4 | GAO-22-105212 NASA Major Project Assessments (2022)
Psyche | 90 | 1 | 22 | 55 | 5 | 16 | GAO-24-106767 NASA Major Project Assessments (2024)
NISAR | 96 | 1 | 24 | 50 | 5 | 12 | GAO-24-106767 NASA Major Project Assessments (2024)
DART | 60 | 1 | 13 | 75 | 6 | 2 | GAO-22-105212 NASA Major Project Assessments (2022)
IXPE | 72 | 1 | 11 | 80 | 6 | 3 | GAO-22-105212 NASA Major Project Assessments (2022)
SWOT | 108 | 1 | 21 | 60 | 5 | 18 | GAO-23-106021 NASA Major Project Assessments (2023)
Europa Clipper | 108 | 1 | 30 | 50 | 5 | 21 | GAO-24-106767 NASA Major Project Assessments (2024)
MAVEN | 60 | 1 | 16 | 75 | 6 | 3 | GAO-15-320SP NASA Assessments of Major Projects (2015)
Juno | 84 | 1 | 18 | 70 | 5 | 6 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects (2012)
LRO | 48 | 1 | 13 | 80 | 6 | 1 | GAO-09-306SP NASA Assessments of Selected Large-Scale Projects (2009)
MMS | 84 | 1 | 17 | 65 | 5 | 2 | GAO-15-320SP NASA Assessments of Major Projects (2015)
SDO | 72 | 1 | 14 | 75 | 6 | 15 | GAO-11-364SP NASA Assessments of Selected Large-Scale Projects (2011)
GPM | 108 | 1 | 18 | 70 | 5 | 16 | GAO-15-320SP NASA Assessments of Major Projects (2015)
LADEE | 48 | 1 | 11 | 75 | 5 | 8 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects (2012)
Roman Space Telescope | 108 | 0 | 33 | 45 | 5 | 11 | GAO-25-107591 NASA Major Project Assessments (2025)
Mars Sample Return | 120 | 0 | 36 | 40 | 4 | 76 | GAO-24-106767 NASA Major Project Assessments (2024); [illustrative cost growth based on 2024 IRB findings]
Dragonfly | 84 | 0 | 26 | 55 | 5 | 9 | GAO-25-107591 NASA Major Project Assessments (2025)
VIPER | 60 | 0 | 18 | 60 | 5 | 40 | GAO-24-106767 NASA Major Project Assessments (2024)
Artemis II EGS | 108 | 0 | 23 | 65 | 6 | 18 | GAO-25-107591 NASA Major Project Assessments (2025)
Gateway HALO/PPE | 96 | 0 | 29 | 40 | 5 | 25 | GAO-25-107591 NASA Major Project Assessments (2025)
HLS (Starship Option A) | 84 | 0 | 40 | 30 | 4 | 22 | GAO-25-107591 NASA Major Project Assessments (2025); [illustrative interface count]

## Construction
Variable | Definition | Construction / source
duration_months | Months elapsed from confirmation review (KDP-C) to launch, or to the GAO assessment cut-off for projects not yet launched | GAO NASA Major Project Assessments series (2009-2025); NASA launch records
launched | Event indicator: 1 if the project launched by the cut-off, 0 if right-censored at the GAO assessment date | GAO NASA Major Project Assessments series; NASA launch manifest
interface_count | Number of major subsystem-to-subsystem and external interfaces in the project ICD set at KDP-C | Project ICD summaries reported in GAO assessments and NASA project plans
heritage_pct | Percent of subsystems classified as flight-proven heritage at KDP-C | GAO assessment heritage tables; NASA project heritage statements
trl_at_kdpc | Lowest Technology Readiness Level of any critical technology at confirmation review | GAO Technology Readiness Assessment summaries
cost_growth_pct | Percent cost growth from KDP-C baseline to most recent estimate (reported only for context) | GAO NASA Major Project Assessments series

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
interface_count | -0.1541 | 0.0632 | -2.4389 | 0.0147 | -0.2779 | -0.0303 | 0.8572
heritage_pct | 0.0181 | 0.0362 | 0.5007 | 0.6166 | -0.0529 | 0.0892 | 1.0183
trl_at_kdpc | 0.1584 | 0.6009 | 0.2636 | 0.7921 | -1.0194 | 1.3363 | 1.1717

## Fit statistics
Statistic | Value
N | 32
events | 25