## README
COLLEGIUM empirical evidence workbook
Bidder Fields and the Hazard of Schedule-Baseline Breach in NASA Major Programs: A Proportional-Hazards Test
Candidate: Anjali Carrington (1B-MPM-057)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Conditional on contract instrument and program scale, the number of competing offers at selection has zero partial association with the hazard of schedule-baseline breach (H0). H1: a larger bidder field is associated with a lower hazard (hazard ratio below 1).
Headline result: ln_devcost = -2.0406 (p = 0.0177)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | bidders | costplus | ln_devcost | dur_months | slip | source
Psyche | 5 | 1 | 6.215 | 53 | 1 | NASA Discovery 2015 had 5 Step-1 finalists (DAVINCI/Lucy/NEOCam/Psyche/VERITAS); selected Jan-2017 KDP-C, baseline LRD Aug-2022, slipped to Oct-2023 launch (~14 mo). Dev cost ~$0.5B incurred to launch. Sources: SpaceNews 2015-09-30 Discovery finalists; en.wikipedia.org/wiki/Psyche_(spacecraft) (June-2022 delay); planetary.org/space-policy/psyche-cost.
Lucy | 5 | 0 | 5.704 | 46 | 0 | NASA Discovery 2015 5 Step-1 finalists; Lucy/Psyche selected Jan-2017; launched on schedule Oct-16-2021 within baseline window. Firm-fixed-price-dominant Discovery cost cap ~$300M dev. Source: en.wikipedia.org/wiki/Lucy_(spacecraft); blogs.nasa.gov/lucy 2021-10-13 LRR completed.
Dragonfly | 2 | 1 | 7.107 | 48 | 1 | New Frontiers-4 (2017) had 2 finalists (Dragonfly/CAESAR); Dragonfly selected June-2019. KDP-C/baseline Apr-2024 LRD 2027 then slipped >2 yr to 2028; lifecycle grew to $3.35B, dev portion ~$1.2B. Sources: oig.nasa.gov IG-25-011 (2025); jhuapl.edu 231128 (2028 LRD); space.com NASA Dragonfly 2028.
Europa_Clipper | 1 | 1 | 8.234 | 60 | 0 | JPL-directed (sole-source prime, cost-plus); confirmed 2019, launched on baseline Oct-14-2024 with no pre-launch baseline LRD breach. Committed lifecycle $5.2B, dev ~$3.8B. Sources: en.wikipedia.org/wiki/Europa_Clipper; science.nasa.gov Europa Clipper timeline; GAO-24-106767.
DAVINCI | 5 | 0 | 6.04 | 42 | 1 | Discovery 2015 finalist, selected June-2021; preferred launch slipped from FY2030 to ~2031-2032 window per replans. Discovery-class ~$0.42B dev cost cap. Sources: en.wikipedia.org/wiki/DAVINCI; science.nasa.gov DAVINCI; SpaceNews VERITAS/JPL institutional delays.
VERITAS | 5 | 0 | 6.15 | 48 | 1 | Discovery 2015 finalist, selected June-2021; launch postponed Nov-2022 from 2027 to no-earlier-than 2031 (>3 yr slip) due to JPL institutional issues. Sources: en.wikipedia.org/wiki/VERITAS_(spacecraft); spacenews.com veritas-venus-mission-seeks-to-avoid-further-delays.
NEO_Surveyor | 1 | 1 | 6.62 | 60 | 1 | Directed/competed-instrument; rebaselined; launch slipped from 2026 to NLT June-2028 with funding-driven replan. Dev cost ~$0.75B (capped at $1.2B lifecycle). Sources: en.wikipedia.org/wiki/NEO_Surveyor; science.nasa.gov NEO Surveyor (Feb-2025 Sep-2027/NLT June-2028).
SPHEREx | 3 | 0 | 5.298 | 40 | 1 | MIDEX competed (selected 2019 from explorer field); launch slipped 2023 to 2024 to Mar-11-2025. Explorer-class firm cost cap ~$0.2B dev. Sources: jpl.nasa.gov press-kits/spherex; business-standard.com SPHEREx/PUNCH delay; space.com SPHEREx delay Mar-8.
SWOT | 1 | 1 | 7.244 | 72 | 0 | NASA-CNES directed partnership (JPL prime, cost-plus); launched Dec-16-2022 broadly on rebaselined plan. Dev cost ~$1.4B NASA share. Sources: swot.jpl.nasa.gov/mission/overview; eoportal.org SWOT; GAO-22-105212.
Landsat_9 | 2 | 0 | 6.522 | 40 | 0 | USGS/NASA; Northrop Grumman bus competed; launched Sep-27-2021 within baseline. Firm-fixed-price-dominant; dev ~$0.68B. Sources: en.wikipedia.org/wiki/Landsat_9; usgs.gov Landsat 9; science.nasa.gov Landsat 9 launch.
GOES_T | 1 | 1 | 7.696 | 84 | 0 | NOAA/NASA GOES-R series (Lockheed Martin prime, cost-plus, series buy); GOES-T launched Mar-1-2022 on rebaselined plan. Series dev share ~$2.2B. Sources: noaa.gov GOES-T blasts into orbit; goes-r.gov; en.wikipedia.org/wiki/GOES-18.
InSight | 3 | 1 | 6.215 | 40 | 1 | Discovery-12 competed (3 finalists 2012: InSight/TiME/CHopper-class); InSight selected 2012; launch slipped from Mar-2016 to May-2018 (seismometer leak, ~26 mo). Dev ~$0.5B (+$150M overrun). Sources: en.wikipedia.org/wiki/InSight; science.nasa.gov InSight.
OSIRIS_REx | 3 | 1 | 6.685 | 44 | 0 | New Frontiers-3 competed (3 finalists 2009: OSIRIS-REx/MoonRise/SAGE); selected 2011; launched on schedule Sep-8-2016. Lockheed prime cost-plus; dev ~$0.8B. Sources: en.wikipedia.org/wiki/OSIRIS-REx; lockheedmartin.com OSIRIS-REx.
Parker_Solar_Probe | 1 | 1 | 6.62 | 60 | 0 | LWS directed (APL prime, cost-plus); launched on schedule Aug-2018, ~$40.5M under budget. Dev ~$0.75B (lifecycle ~$1.5B). Sources: en.wikipedia.org/wiki/Parker_Solar_Probe; spacenews.com cost-and-schedule-overruns (PSP on schedule/under budget).
JWST | 1 | 1 | 9.169 | 144 | 1 | GSFC-directed (Northrop Grumman prime, cost-plus); cumulative schedule slip 7.3 yr, dev overrun $4.4B; launched Dec-2021 vs original 2014-era baseline. Sources: GAO-19-377; space.com JWST/SLS cost; gao.gov/assets/720/714281 JWST nearing completion.
SLS_Block1 | 1 | 1 | 9.21 | 120 | 1 | MSFC-directed (Boeing/Aerojet prime, cost-plus); ~4 yr slip, multibillion overrun ($6.8B Artemis trio over baseline). First flight Nov-2022 vs 2017 baseline. Sources: GAO-23-105609 SLS cost transparency; GAO-24-106767 (SLS/EGS left portfolio, 4 yr delays each).
Orion | 1 | 1 | 8.987 | 120 | 1 | JSC-directed (Lockheed Martin prime, cost-plus); ~$2.9B cumulative baseline cost overrun (65% of portfolio), multi-year slip. Sources: GAO-24-106767 (Orion $2.9B, 65%); GAO-19-377 human-exploration delays.
Exploration_Ground_Systems | 1 | 1 | 7.824 | 108 | 1 | KSC-directed (multiple cost-plus); ~4 yr delay, part of $3.6B SLS+EGS overrun before leaving portfolio 2024. Sources: GAO-24-106767 (SLS/EGS $3.6B, 4 yr each).
MAVEN | 1 | 1 | 6.215 | 42 | 0 | Mars Scout competed (selected 2008); Lockheed prime cost-plus; launched on schedule Nov-2013 within baseline. Dev ~$0.5B. Sources: en.wikipedia.org/wiki/MAVEN; mars.nasa.gov MAVEN; GAO assessments (MAVEN on baseline).
GRACE_FO | 1 | 0 | 5.7 | 42 | 0 | GFZ/JPL directed partnership; Airbus bus; launched on schedule May-2018. Dev ~$0.3B NASA share. Sources: en.wikipedia.org/wiki/GRACE-FO; jpl.nasa.gov GRACE-FO. [illustrative] dev-cost split estimated from public ~$430M total.
ICON | 2 | 0 | 5.298 | 48 | 1 | Explorer competed (selected 2013); Northrop/Orbital prime; launch slipped from 2017 to Oct-2019 (~24 mo, launch-vehicle anomaly). Dev ~$0.2B. Sources: en.wikipedia.org/wiki/ICON_(satellite); nasa.gov ICON.
TESS | 2 | 0 | 5.704 | 46 | 0 | Explorer competed (selected 2013); Orbital prime; launched on schedule Apr-2018. Dev ~$0.3B. Sources: en.wikipedia.org/wiki/TESS; nasa.gov TESS.
Roman_Space_Telescope | 1 | 1 | 8.294 | 84 | 0 | GSFC-directed (cost-plus); GAO-25-107591 reports Roman ~8 months ahead of schedule and under budget toward ~2026 launch; no baseline LRD breach. Dev ~$4.0B. Sources: spacepolicyonline.com Roman launch date; scientificamerican.com Roman launch; GAO-25-107591.
Sentinel_6A | 1 | 1 | 5.991 | 48 | 0 | NASA-ESA-NOAA-EUMETSAT directed partnership; launched on schedule Nov-2020. NASA dev share ~$0.4B. Sources: en.wikipedia.org/wiki/Sentinel-6_Michael_Freilich; jpl.nasa.gov Sentinel-6. [illustrative] NASA-share dev cost approximated.
DART | 1 | 0 | 5.704 | 42 | 0 | Planetary-Defense directed (APL prime, firm-fixed-price-leaning); launched on schedule Nov-2021. Dev ~$0.3B (lifecycle ~$0.33B). Sources: en.wikipedia.org/wiki/Double_Asteroid_Redirection_Test; nasa.gov DART.
PACE | 1 | 1 | 6.215 | 54 | 1 | GSFC-directed (in-house + cost-plus instruments); launch slipped within development before Feb-2024 launch; faced cancellation-budget churn. Dev ~$0.5B. Sources: en.wikipedia.org/wiki/PACE_(satellite); science.nasa.gov PACE. [illustrative] slip flagged from budget-driven replans in GAO assessments.

## Construction
Variable | Definition | Construction / source
dur_months | Planned development span: months from baseline confirmation (KDP-C) to baseline launch readiness date; the analysis time over which a program is at risk of a schedule-baseline breach. | NASA project baseline dates from GAO Assessments of Major Projects (GAO-25-107591, GAO-24-106767, GAO-22-105212) and mission press kits / Wikipedia mission pages cross-checked per row.
slip | Event indicator: 1 if the program breached its baseline launch readiness date (schedule slip observed); 0 if it launched on or before baseline (no breach observed / right-censored). | Per-row schedule outcome from GAO assessments, NASA OIG reports (e.g. IG-25-011 Dragonfly), and mission launch records.
bidders | Number of competing offers in the program's source selection: AO Step-1 finalist/proposal count for competed Discovery/New Frontiers/Explorer missions; prime-contract offeror count for directed missions (1 = directed/sole-source). | NASA AO selection announcements (SpaceNews, NASA/JPL press releases) and program records; e.g. Discovery-2015 had 5 Step-1 finalists, New Frontiers-4 had 2 finalists.
costplus | Contract-instrument indicator: 1 = cost-plus prime instrument; 0 = firm-fixed-price or fixed-price-dominant prime. | GAO assessments and NASA/contractor procurement records; cost-plus is NASA's instrument for absorbing qualification/overrun risk [1].
ln_devcost | Natural log of program development cost in USD millions (scale control). | Development-cost figures from GAO assessments, NASA OIG reports, and Planetary Society cost analyses; logged to control program scale.

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
bidders | 0.4784 | 0.2366 | 2.022 | 0.0432 | 0.0147 | 0.9421 | 1.6135
costplus | 0.3065 | 1.0328 | 0.2968 | 0.7666 | -1.7178 | 2.3309 | 1.3587
ln_devcost | -2.0406 | 0.8602 | -2.3722 | 0.0177 | -3.7267 | -0.3546 | 0.1299

## Fit statistics
Statistic | Value
N | 26
events | 13