## README
COLLEGIUM empirical evidence workbook
Estimating Cost-Growth Magnitude in NASA Major Projects: An OLS Test of Governance Density, Complexity, and Acquisition Mode
Candidate: Saskia Farouk (1B-MPM-107)
Method: OLS (robust HC1 SE)
Hypothesis: H1: Cost-growth magnitude rises with the count of standing oversight committees, with technical complexity, and with cumulative schedule slip, consistent with the garbage-can prediction that decision arenas accumulate problem-solution-participant streams that resolve without convergence on the cost objective. H2: Fixed-price commercial services acquisition shifts the conditional mean of cost growth relative to traditional cost-plus.
Headline result: schedule_slip_months = 1.0153 (p = 5.631e-05)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | cost_growth_pct | complexity | n_oversight_committees | prime_contractors | new_space | schedule_slip_months | source
JWST | 95 | 3 | 6 | 3 | 0 | 52 | GAO-12-207SP NASA Major Project Annual Assessment 2012; gao.gov/products/gao-12-207sp
SLS Block 1 | 33 | 3 | 5 | 3 | 0 | 28 | GAO-20-405 NASA Major Projects 2020; gao.gov/products/gao-20-405
Orion MPCV | 11 | 2 | 5 | 2 | 0 | 18 | GAO-21-306 NASA Major Projects 2021; gao.gov/products/gao-21-306
Europa Clipper | 15 | 3 | 5 | 2 | 0 | 0 | GAO-23-106021 NASA Major Project Assessment 2023; gao.gov/products/gao-23-106021
Mars 2020 Perseverance | 2 | 2 | 4 | 2 | 0 | 0 | GAO-20-405; gao.gov/products/gao-20-405
Psyche | 9 | 2 | 4 | 2 | 0 | 14 | GAO-24-106767 NASA Major Project Assessment 2024; gao.gov/products/gao-24-106767
Lucy | 0 | 2 | 4 | 2 | 0 | 0 | GAO-21-306; gao.gov/products/gao-21-306
DART | 18 | 2 | 3 | 1 | 0 | 4 | GAO-22-105212 NASA Major Project Assessment 2022; gao.gov/products/gao-22-105212
Space Fence | 22 | 3 | 4 | 1 | 0 | 18 | GAO-18-385SP Defense Acquisitions 2018; gao.gov/products/gao-18-385sp
GOES-R | 33 | 3 | 5 | 2 | 0 | 36 | GAO-17-291 NOAA Geostationary Weather Satellites 2017; gao.gov/products/gao-17-291
Landsat 9 | 0 | 2 | 3 | 1 | 0 | 0 | GAO-21-306; gao.gov/products/gao-21-306
NISAR | 6 | 2 | 5 | 2 | 0 | 12 | GAO-24-106767; gao.gov/products/gao-24-106767
Commercial Crew Dragon | 0 | 2 | 3 | 1 | 1 | 30 | GAO-18-317 NASA Commercial Crew Program 2018; gao.gov/products/gao-18-317
Commercial Crew Starliner | 0 | 2 | 3 | 1 | 1 | 48 | GAO-20-121 NASA Commercial Crew 2020; gao.gov/products/gao-20-121
CLPS IM-1 | 0 | 2 | 2 | 1 | 1 | 12 | NASA OIG IG-22-003 CLPS Initiative 2021; oig.nasa.gov/docs/IG-22-003.pdf
CLPS Peregrine | 0 | 2 | 2 | 1 | 1 | 18 | NASA OIG IG-22-003; oig.nasa.gov/docs/IG-22-003.pdf
HLS Starship | 0 | 3 | 4 | 1 | 1 | 24 | GAO-24-107249 NASA Human Landing System 2024; gao.gov/products/gao-24-107249
Gateway PPE-HALO | 16 | 3 | 5 | 2 | 1 | 18 | GAO-25-107591 NASA Major Project Assessment 2025; gao.gov/products/gao-25-107591
Roman Space Telescope | 8 | 3 | 5 | 2 | 0 | 7 | GAO-25-107591; gao.gov/products/gao-25-107591
VIPER | 30 | 2 | 4 | 1 | 0 | 24 | NASA OIG IG-24-006 VIPER 2024; oig.nasa.gov/docs/IG-24-006.pdf
MSR SRL | 55 | 3 | 6 | 3 | 0 | 36 | GAO-25-107591 Mars Sample Return assessment; gao.gov/products/gao-25-107591
SWOT | 4 | 2 | 4 | 2 | 0 | 12 | GAO-22-105212; gao.gov/products/gao-22-105212
MSL Curiosity | 86 | 3 | 5 | 2 | 0 | 28 | GAO-12-207SP NASA Major Project Annual Assessment 2012; gao.gov/products/gao-12-207sp
OSIRIS-REx | 4 | 2 | 4 | 2 | 0 | 0 | GAO-16-309SP NASA Major Project Assessment 2016; gao.gov/products/gao-16-309sp
InSight | 30 | 2 | 4 | 2 | 0 | 26 | GAO-18-280SP NASA Major Project Assessment 2018; gao.gov/products/gao-18-280sp
MAVEN | 3 | 2 | 3 | 2 | 0 | 0 | GAO-14-338SP NASA Major Project Assessment 2014; gao.gov/products/gao-14-338sp
Juno | 28 | 3 | 4 | 2 | 0 | 18 | GAO-12-207SP NASA Major Project Annual Assessment 2012; gao.gov/products/gao-12-207sp
SMAP | 3 | 2 | 3 | 1 | 0 | 0 | GAO-15-320SP NASA Major Project Assessment 2015; gao.gov/products/gao-15-320sp
ICESat-2 | 40 | 3 | 4 | 1 | 0 | 24 | GAO-19-189 NASA Major Project Assessment 2019; gao.gov/products/gao-19-189
JPSS-1 | 35 | 3 | 5 | 2 | 0 | 30 | GAO-18-280SP NASA Major Project Assessment 2018; gao.gov/products/gao-18-280sp
TESS | 7 | 2 | 3 | 1 | 0 | 8 | GAO-18-280SP; gao.gov/products/gao-18-280sp
PACE | 11 | 2 | 3 | 1 | 0 | 8 | GAO-24-106767; gao.gov/products/gao-24-106767
MMS | 5 | 2 | 3 | 1 | 0 | 6 | GAO-15-320SP; gao.gov/products/gao-15-320sp
GRAIL | 0 | 2 | 3 | 1 | 0 | 0 | GAO-12-207SP; gao.gov/products/gao-12-207sp
LADEE | 0 | 2 | 2 | 1 | 0 | 2 | GAO-13-276SP NASA Major Project Assessment 2013; gao.gov/products/gao-13-276sp
OCO-2 | 2 | 2 | 3 | 1 | 0 | 4 | GAO-14-338SP; gao.gov/products/gao-14-338sp
TDRS-K | 0 | 2 | 3 | 1 | 0 | 3 | GAO-13-276SP; gao.gov/products/gao-13-276sp

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Cumulative life-cycle cost growth in percent from KDP-C confirmation baseline to most recent GAO assessment | GAO Major Project Annual Assessment series 2012 through 2025; NASA OIG audit reports for CLPS, Commercial Crew, HLS, and VIPER
complexity | Ordinal complexity tier from 1 (low) to 3 (high), reflecting element count and TRL spread at KDP-C | GAO complexity tier reported in GAO-25-107591, GAO-24-106767, GAO-23-106021
n_oversight_committees | Count of distinct standing governance bodies with formal approval authority over the program at KDP-C (mission directorate review, agency program management council, independent review board, congressional appropriations subcommittee, external advisory panel, interagency review) | Coded from GAO assessment narratives and NASA program directives
prime_contractors | Count of distinct prime contractors holding cost-type or fixed-price contracts above 100M USD at KDP-C | GAO Major Project Assessments procurement summaries
new_space | 1 if program executed under a fixed-price commercial services acquisition (CLPS, Commercial Crew, HLS, Gateway public-private), 0 if traditional cost-plus or in-house build | Acquisition strategy field of GAO and OIG assessments
schedule_slip_months | Months between baseline launch readiness date at KDP-C and most recent or actual launch | GAO Major Project Annual Assessment series, current launch baseline columns

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -30.0299 | 10.887 | -2.7583 | 0.0058 | -51.3681 | -8.6918
complexity | 15.3449 | 5.6507 | 2.7156 | 0.0066 | 4.2697 | 26.42
n_oversight_committees | -2.0594 | 3.3459 | -0.6155 | 0.5382 | -8.6172 | 4.4984
prime_contractors | 4.5524 | 4.8971 | 0.9296 | 0.3526 | -5.0457 | 14.1505
new_space | -27.2802 | 6.5373 | -4.173 | 3.006e-05 | -40.0932 | -14.4673
schedule_slip_months | 1.0153 | 0.2521 | 4.0278 | 5.631e-05 | 0.5212 | 1.5094

## Fit statistics
Statistic | Value
N | 37
R2 | 0.7396
R2_adj | 0.6976
F | 7.8806
F_p | 6.97e-05