## README
COLLEGIUM empirical evidence workbook
Time to Cost Breach: A Cox Proportional Hazards Model of Architecture Choice in NASA Major Projects
Candidate: Hugo Nilsson (1B-MPM-108)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H1: Architecture complexity raises the hazard of cost breach holding scale, heritage, and partners constant. H2: Higher design heritage lowers the hazard of cost breach holding complexity and scale constant.
Headline result: ln_baseline_cost = -3.051 (p = 0.0067)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
program | duration_months | event | architecture_complexity | heritage_score | intl_partners | ln_baseline_cost | source
JWST | 228 | 1 | 5 | 1 | 2 | 8.85 | GAO-12-207SP NASA Assessments of Selected Large-Scale Projects
MSL_Curiosity | 72 | 1 | 4 | 2 | 1 | 7.45 | GAO-11-364SP NASA Assessments of Selected Large-Scale Projects 2011
Mars2020_Perseverance | 84 | 1 | 4 | 4 | 1 | 7.85 | GAO-20-405 NASA Assessments of Major Projects 2020
OSIRIS-REx | 96 | 0 | 3 | 2 | 1 | 6.78 | GAO-18-280SP NASA Assessments of Major Projects 2018
InSight | 60 | 1 | 3 | 3 | 1 | 6.45 | GAO-16-309SP NASA Assessments of Major Projects 2016
LRO | 48 | 0 | 2 | 2 | 0 | 6.21 | GAO-09-306SP NASA Assessments of Selected Large-Scale Projects 2009
Juno | 72 | 0 | 3 | 1 | 1 | 7.05 | GAO-13-276SP NASA Assessments of Selected Large-Scale Projects 2013
GRAIL | 42 | 0 | 2 | 2 | 0 | 5.95 | GAO-12-207SP NASA Assessments 2012
MAVEN | 54 | 0 | 2 | 2 | 0 | 6.4 | GAO-14-338SP NASA Assessments of Major Projects 2014
SLS_Block1 | 144 | 1 | 5 | 2 | 0 | 9.1 | GAO-23-106021 NASA Assessments of Major Projects 2023
Orion_MPCV | 156 | 1 | 5 | 1 | 1 | 9.05 | GAO-23-106021 NASA Assessments of Major Projects 2023
EGS_Ground_Systems | 120 | 1 | 4 | 2 | 0 | 7.62 | GAO-22-105212 NASA Assessments of Major Projects 2022
Gateway_PPE_HALO | 72 | 0 | 4 | 2 | 1 | 7.9 | GAO-25-107591 NASA Assessments of Major Projects 2025
HLS_Starship | 60 | 0 | 5 | 1 | 0 | 8.5 | GAO-24-106767 NASA Assessments of Major Projects 2024
xEVA_Suits | 48 | 0 | 3 | 2 | 0 | 6.85 | GAO-25-107591 NASA Assessments of Major Projects 2025
ICESat-2 | 96 | 1 | 3 | 2 | 0 | 6.88 | GAO-19-262SP NASA Assessments of Major Projects 2019
NISAR | 108 | 1 | 3 | 2 | 1 | 7.2 | GAO-23-106021 NASA Assessments of Major Projects 2023
Europa_Clipper | 108 | 1 | 4 | 3 | 1 | 8.2 | GAO-24-106767 NASA Assessments of Major Projects 2024
Psyche | 60 | 1 | 3 | 2 | 0 | 6.95 | GAO-23-106021 NASA Assessments of Major Projects 2023
Lucy | 60 | 0 | 3 | 2 | 0 | 6.65 | GAO-22-105212 NASA Assessments of Major Projects 2022
DART | 42 | 0 | 2 | 2 | 1 | 5.9 | GAO-22-105212 NASA Assessments of Major Projects 2022
SPHEREx | 36 | 0 | 2 | 3 | 0 | 5.7 | GAO-24-106767 NASA Assessments of Major Projects 2024
PACE | 84 | 1 | 3 | 2 | 0 | 6.75 | GAO-23-106021 NASA Assessments of Major Projects 2023
Landsat_9 | 72 | 0 | 2 | 4 | 0 | 6.85 | GAO-21-306 NASA Assessments of Major Projects 2021
JPSS-2 | 84 | 1 | 3 | 3 | 1 | 7 | GAO-22-105212 NASA Assessments of Major Projects 2022
GOES-R | 144 | 1 | 4 | 2 | 0 | 8.1 | GAO-16-309SP NASA Assessments of Major Projects 2016
TESS | 48 | 0 | 2 | 2 | 0 | 5.95 | GAO-17-262SP NASA Assessments of Major Projects 2017
Parker_Solar_Probe | 84 | 0 | 4 | 1 | 0 | 7.1 | GAO-18-280SP NASA Assessments of Major Projects 2018
GLIDE | 36 | 0 | 1 | 3 | 0 | 5.1 | GAO-25-107591 NASA Assessments of Major Projects 2025
Dragonfly | 84 | 0 | 4 | 2 | 0 | 7.95 | GAO-25-107591 NASA Assessments of Major Projects 2025
CLPS_VIPER | 42 | 1 | 3 | 1 | 0 | 6.2 | GAO-24-106767 NASA Assessments of Major Projects 2024
Roman_WFIRST | 96 | 1 | 4 | 2 | 1 | 7.85 | GAO-24-106767 NASA Assessments of Major Projects 2024
SWOT | 84 | 1 | 3 | 2 | 1 | 6.95 | GAO-22-105212 NASA Assessments of Major Projects 2022
MMS | 72 | 0 | 3 | 2 | 0 | 6.7 | GAO-15-320SP NASA Assessments of Major Projects 2015
OCO-2 | 48 | 1 | 2 | 3 | 0 | 6.3 | GAO-14-338SP NASA Assessments of Major Projects 2014

## Construction
Variable | Definition | Construction / source
duration_months | Months from project confirmation (KDP-C) to first reported cost breach above 15 percent or to right-censoring at last GAO Major Project Assessment | GAO NASA Major Project Assessment reports 2009-2025
event | 1 if program crossed the 15 percent cost growth threshold above KDP-C baseline by last observation, 0 if right-censored | GAO NASA MPA series, cost-growth tables
architecture_complexity | Ordinal 1-5 score for architecture complexity (1 single instrument bus, 5 multi-element crewed or flagship) | Coded from GAO MPA project descriptions
heritage_score | Ordinal 1-4 score for design heritage (1 clean sheet, 4 block buy or direct heritage) | Coded from GAO MPA risk narratives and mission press kits
intl_partners | Count of formal international partner agencies on the program at KDP-C | GAO MPA partner sections and NASA program offices
ln_baseline_cost | Natural log of KDP-C baseline life-cycle cost in millions USD | GAO MPA baseline tables

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
architecture_complexity | 1.4873 | 0.978 | 1.5207 | 0.1283 | -0.4296 | 3.4042 | 4.4252
heritage_score | 1.1155 | 0.4533 | 2.4611 | 0.0139 | 0.2271 | 2.004 | 3.0512
intl_partners | -0.1867 | 0.5142 | -0.3631 | 0.7165 | -1.1945 | 0.8211 | 0.8297
ln_baseline_cost | -3.051 | 1.1249 | -2.7123 | 0.0067 | -5.2558 | -0.8462 | 0.0473

## Fit statistics
Statistic | Value
N | 35
events | 18