## README
COLLEGIUM empirical evidence workbook
Time to Flight: A Cox Survival Analysis of Architecture Choice and Development Duration in NASA Major Projects
Candidate: Hugo Nilsson (1B-MPM-108)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Holding scale, heritage, and instrument count constant, monolithic architecture is associated with a lower hazard of reaching launch (longer time to flight) than distributed architecture.
Headline result: instrument_count = 0.1303 (p = 0.1535)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | monolithic | log_dev_cost | heritage_pct | instrument_count | duration_months | launched | source
JWST | 1 | 9.3 | 30 | 4 | 180 | 1 | GAO-19-262SP NASA Major Project Assessment 2019; JWST launched Dec 2021
MSL_Curiosity | 1 | 8.32 | 40 | 10 | 96 | 1 | GAO-12-207SP NASA MPA 2012; Curiosity launched Nov 2011
Mars2020_Perseverance | 1 | 7.83 | 70 | 7 | 72 | 1 | GAO-20-405 NASA MPA 2020; Perseverance launched Jul 2020
OSIRIS_REx | 1 | 7.04 | 60 | 5 | 72 | 1 | GAO-16-309SP NASA MPA 2016; OSIRIS-REx launched Sep 2016
Parker_Solar_Probe | 1 | 7.24 | 30 | 4 | 84 | 1 | GAO-18-280SP NASA MPA 2018; launched Aug 2018
Europa_Clipper | 1 | 8.55 | 45 | 9 | 96 | 1 | GAO-23-106021 NASA MPA 2023; launched Oct 2024
Psyche | 1 | 7.2 | 55 | 3 | 84 | 1 | GAO-22-105212 NASA MPA 2022; launched Oct 2023
Lucy | 1 | 6.94 | 65 | 3 | 60 | 1 | GAO-21-306 NASA MPA 2021; launched Oct 2021
InSight | 1 | 7.13 | 75 | 2 | 84 | 1 | GAO-19-262SP NASA MPA 2019; launched May 2018
MAVEN | 1 | 6.96 | 55 | 8 | 60 | 1 | GAO-14-338SP NASA MPA 2014; launched Nov 2013
GRAIL | 1 | 6.85 | 70 | 2 | 48 | 1 | GAO-12-207SP NASA MPA 2012; launched Sep 2011
LADEE | 1 | 6.39 | 40 | 3 | 48 | 1 | GAO-13-276SP NASA MPA 2013; launched Sep 2013
SLS_Block1 | 1 | 9.95 | 50 | 1 | 156 | 1 | GAO-23-106021 NASA MPA 2023; Artemis I Nov 2022
Orion_MPCV | 1 | 9.4 | 45 | 2 | 168 | 1 | GAO-23-106021 NASA MPA 2023; Artemis I 2022
EGS_Artemis | 1 | 8.85 | 30 | 1 | 144 | 1 | GAO-22-105212 NASA MPA 2022; Artemis I 2022
Gateway_PPE_HALO | 1 | 8.48 | 40 | 2 | 84 | 0 | GAO-24-106767 NASA MPA 2024; launch NET 2027 [illustrative]
MSR_SRL | 1 | 9.3 | 35 | 3 | 120 | 0 | GAO-23-106021 NASA MPA 2023; replan ongoing
NEO_Surveyor | 1 | 7.78 | 50 | 1 | 72 | 0 | GAO-24-106767 NASA MPA 2024; launch NET 2027
Dragonfly | 1 | 8.18 | 40 | 5 | 96 | 0 | GAO-24-106767 NASA MPA 2024; launch NET 2028
VIPER | 1 | 7 | 55 | 4 | 60 | 0 | GAO-24-106767 NASA MPA 2024; cancelled Jul 2024
TESS | 0 | 6.4 | 60 | 4 | 48 | 1 | GAO-18-280SP NASA MPA 2018; launched Apr 2018
ICESat2 | 0 | 7.04 | 55 | 1 | 72 | 1 | GAO-19-262SP NASA MPA 2019; launched Sep 2018
SWOT | 0 | 7.39 | 60 | 4 | 84 | 1 | GAO-23-106021 NASA MPA 2023; launched Dec 2022
NISAR | 0 | 7.78 | 50 | 2 | 108 | 1 | GAO-24-106767 NASA MPA 2024; launched Jul 2025
Landsat9 | 0 | 7.2 | 80 | 2 | 60 | 1 | GAO-21-306 NASA MPA 2021; launched Sep 2021
GOES_R | 0 | 8.85 | 40 | 6 | 108 | 1 | GAO-16-309SP NASA MPA 2016; GOES-R launched Nov 2016
JPSS2 | 0 | 7.85 | 75 | 5 | 72 | 1 | GAO-22-105212 NASA MPA 2022; launched Nov 2022
SPHEREx | 0 | 6.61 | 50 | 1 | 60 | 1 | GAO-23-106021 NASA MPA 2023; launched Mar 2025
PACE | 0 | 7.13 | 55 | 3 | 72 | 1 | GAO-22-105212 NASA MPA 2022; launched Feb 2024
IXPE | 0 | 5.99 | 60 | 3 | 60 | 1 | GAO-21-306 NASA MPA 2021; launched Dec 2021
TROPICS | 0 | 4.61 | 55 | 6 | 36 | 1 | GAO-22-105212 NASA MPA 2022; constellation 2023
CYGNSS | 0 | 5.3 | 70 | 8 | 48 | 1 | GAO-16-309SP NASA MPA 2016; launched Dec 2016
Roman | 0 | 8.1 | 45 | 2 | 108 | 0 | GAO-24-106767 NASA MPA 2024; launch NET 2027
AOS_Storm | 0 | 7.6 | 40 | 3 | 84 | 0 | GAO-24-106767 NASA MPA 2024; launch NET 2028 [illustrative]
GeoCarb | 0 | 5.99 | 55 | 1 | 60 | 0 | GAO-22-105212 NASA MPA 2022; cancelled 2022
CLPS_CP11 | 0 | 5.3 | 60 | 4 | 36 | 1 | GAO-23-106021 NASA MPA 2023; CLPS deliveries 2024

## Construction
Variable | Definition | Construction / source
duration_months | Months elapsed from Preliminary Design Review baseline to launch or to most recent GAO assessment if not yet launched | GAO NASA Major Project Assessment reports 2012-2024
launched | Event indicator equal to 1 if the project achieved launch by the observation window close, 0 if still in development or cancelled (right censored) | GAO MPA series and NASA mission press kits
monolithic | Indicator equal to 1 if the architecture is a single integrated flight element, 0 if distributed or disaggregated across multiple platforms | Mission press kits and project architecture documents
log_dev_cost | Natural log of baseline development cost in millions USD at PDR | GAO NASA MPA series
heritage_pct | Percent of subsystems flown previously on a comparable mission | NASA cost estimating documents and project websites
instrument_count | Number of distinct science or operational instruments planned at PDR baseline | Mission press kits and NASA project pages

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
monolithic | 0.2116 | 0.5083 | 0.4164 | 0.6771 | -0.7846 | 1.2078 | 1.2357
log_dev_cost | -1.5931 | 0.3645 | -4.371 | 1.237e-05 | -2.3074 | -0.8787 | 0.2033
heritage_pct | 0.0342 | 0.0195 | 1.75 | 0.0801 | -0.0041 | 0.0725 | 1.0348
instrument_count | 0.1303 | 0.0913 | 1.4273 | 0.1535 | -0.0486 | 0.3093 | 1.1392

## Fit statistics
Statistic | Value
N | 36
events | 28