## README
COLLEGIUM empirical evidence workbook
Imperial Overstretch on Orbit: Space Spending Relative to Economic Base and Program Performance
Candidate: Mateo Mercer (1B-GST-233)
Method: OLS (robust HC1 SE)
Hypothesis: H0: Effort disproportionate to the economic base carries no association with program cost performance; beta_1 = beta_2 = 0, so neither national space spending relative to GDP at the moment of commitment nor the project's share of the agency's committed development base predicts cumulative development cost growth. H1: Kennedy's overstretch mechanism operates on space acquisition, so beta_1 > 0 and beta_2 > 0, with disproportionate effort predicting larger cost overruns once exposure and mission class are held constant.
Headline result: human_spaceflight = -35.5434 (p = 0.1954)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
program | agency | baseline_year | baseline_dev_cost_musd | space_spend_pct_gdp | space_effort_ratio_pct | years_in_development | human_spaceflight | schedule_slip_months | cost_overrun_musd | cost_overrun_pct | baseline_year_analyst_coded | source
James Webb Space Telescope | NASA | 2008 | 2581.1 | 0.1172 | 8.538 | 14 | 0 | 90 | 4536 | 175.7 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Space Network Ground Segment Sustainment | NASA | 2013 | 368.1 | 0.0999 | 1.218 | 9 | 0 | 48 | 589.2 | 160.1 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Exploration Ground Systems | NASA | 2014 | 1843.5 | 0.1002 | 6.098 | 8 | 1 | 42 | 749 | 40.6 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Space Launch System | NASA | 2014 | 6390 | 0.1002 | 21.136 | 8 | 1 | 42 | 2718.3 | 42.5 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Orion Multi-Purpose Crew Vehicle | NASA | 2015 | 6768.4 | 0.0984 | 22.388 | 7 | 1 | 13 | 2532.8 | 37.4 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Surface Water and Ocean Topography | NASA | 2016 | 571.5 | 0.1026 | 1.89 | 6 | 0 | 14 | 67.5 | 11.8 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
NISAR | NASA | 2016 | 661 | 0.1026 | 2.186 | 6 | 0 | 12 | 113.3 | 17.1 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Mars 2020 (Perseverance) | NASA | 2016 | 1676.9 | 0.1026 | 5.412 | 5 | 0 | 0 | 356.2 | 21.2 | 0 | GAO-21-306 (May 2021) Table 2; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Landsat 9 | NASA | 2017 | 634.2 | 0.1002 | 2.098 | 5 | 0 | -2 | -138.5 | -21.8 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Laser Communications Relay Demonstration | NASA | 2017 | 91.8 | 0.1002 | 0.304 | 5 | 0 | 25 | 53.3 | 58.1 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Lucy | NASA | 2018 | 622.2 | 0.1004 | 2.058 | 4 | 0 | -1 | -57.2 | -9.2 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Low Boom Flight Demonstrator | NASA | 2018 | 467.7 | 0.1004 | 1.547 | 4 | 0 | 11 | 104.5 | 22.3 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Double Asteroid Redirection Test | NASA | 2018 | 258.3 | 0.1004 | 0.854 | 4 | 0 | -3 | 11.8 | 4.6 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-19-262SP Table 2 confirmation-year column; NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Psyche | NASA | 2019 | 681.9 | 0.0998 | 2.256 | 3 | 0 | 0 | -30.8 | -4.5 | 1 | GAO-22-105212 (July 2022) Table 6; baseline year bounded by GAO-19-262SP Table 1 (in formulation) and GAO-21-306 Table 2 (baselined); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD ¦ analyst-coded (not directly reported): baseline_year
Europa Clipper | NASA | 2019 | 2412.8 | 0.0998 | 7.981 | 3 | 0 | -11 | 96.2 | 4 | 1 | GAO-22-105212 (July 2022) Table 6; baseline year bounded by GAO-19-262SP Table 1 (in formulation) and GAO-21-306 Table 2 (baselined); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD ¦ analyst-coded (not directly reported): baseline_year
PACE | NASA | 2019 | 558 | 0.0998 | 1.846 | 3 | 0 | 4 | 74.3 | 13.3 | 1 | GAO-22-105212 (July 2022) Table 6; baseline year bounded by GAO-19-262SP Table 1 (in formulation) and GAO-21-306 Table 2 (baselined); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD ¦ analyst-coded (not directly reported): baseline_year
Solar Electric Propulsion | NASA | 2019 | 155.9 | 0.0998 | 0.516 | 3 | 0 | 46 | 47.3 | 30.3 | 1 | GAO-22-105212 (July 2022) Table 6; baseline year bounded by GAO-19-262SP Table 1 (in formulation) and GAO-21-306 Table 2 (baselined); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD ¦ analyst-coded (not directly reported): baseline_year
Nancy Grace Roman Space Telescope | NASA | 2020 | 2898.1 | 0.1059 | 9.586 | 2 | 0 | 7 | 371.9 | 12.8 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-21-306 Table 3 (first-year estimate reported); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
OSAM-1 | NASA | 2020 | 974.4 | 0.1059 | 3.223 | 2 | 0 | 0 | 146.1 | 15 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-21-306 Table 3 (first-year estimate reported); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
SPHEREx | NASA | 2020 | 367.8 | 0.1059 | 1.217 | 2 | 0 | 0 | 0 | 0 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-21-306 Table 3 (first-year estimate reported); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
Interstellar Mapping and Acceleration Probe | NASA | 2021 | 589.5 | 0.0981 | 1.95 | 1 | 0 | 0 | 0 | 0 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-22-105212 App. V (moved to implementation in review period); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD
VIPER | NASA | 2021 | 336.2 | 0.0981 | 1.112 | 1 | 0 | 0 | 0 | 0 | 0 | GAO-22-105212 (July 2022) Table 6; baseline year: GAO-21-306 (NASA approved VIPER to enter implementation, March 2021); NASA budget: Budget of NASA fiscal-year appropriations series; GDP: World Bank WDI NY.GDP.MKTP.CD

## Construction
Variable | Definition | Construction / source
cost_overrun_pct | Cumulative development cost growth of the project measured against the original development cost baseline approved at its confirmation review, expressed as a percentage. Negative values denote underruns. Values are taken verbatim from GAO's portfolio tables and were independently re-derived as cost_overrun_musd divided by baseline_dev_cost_musd; all twenty-two rows reproduce GAO's published percentage to within 0.1 percentage point. | GAO-22-105212 (July 2022) Table 6; GAO-21-306 (May 2021) Table 2 for Mars 2020
space_spend_pct_gdp | The sponsoring nation's civil space effort relative to its economic base in the year the project's cost baseline was committed: NASA enacted budget authority for that fiscal year divided by United States gross domestic product for the same year, expressed as a percentage. This is the direct empirical analogue of Kennedy's ratio of commitment to productive base. | NASA fiscal-year appropriations series (FY2008 to FY2022); World Bank World Development Indicators NY.GDP.MKTP.CD (United States, current USD)
space_effort_ratio_pct | The project's own claim on the agency's committed development base: original baseline development cost divided by the total original baseline development cost of the entire major-project portfolio assessed in the same GAO cycle (30,232.4 million dollars in the 2022 assessment; 30,983.6 million dollars in the 2021 assessment), expressed as a percentage. This operationalizes overstretch at the portfolio rather than the national level. | Computed by the author from GAO-22-105212 Table 6 and GAO-21-306 Table 2 baseline and portfolio-total columns
years_in_development | Elapsed years of exposure under the approved baseline: the GAO assessment year minus the year in which the project set its original cost and schedule baseline. Captures how long a commitment has been carried, as distinct from how large it is. | Derived from baseline_year and the GAO assessment vintage (2022 for twenty-one rows, 2021 for Mars 2020)
baseline_year | Calendar year in which the project's original cost and schedule baseline was approved. Thirteen values are read directly from the confirmation-year column of GAO-19-262SP Table 2; three (Roman, OSAM-1, SPHEREx) from GAO-21-306 Table 3, which identifies them as first-year baseline reporters; two (IMAP, VIPER) from GAO-22-105212 Appendix V and GAO-21-306 narrative. Four values (Psyche, Europa Clipper, PACE, Solar Electric Propulsion) are bracketed as illustrative: GAO documents place each in formulation as of the 2019 assessment and baselined as of the 2021 assessment, which bounds but does not fix the year. | GAO-19-262SP Tables 1 and 2; GAO-21-306 Tables 2 and 3; GAO-22-105212 Appendix V
human_spaceflight | Binary indicator equal to 1 if GAO assigns the project to the Deep Space Exploration budget portfolio, that is, the crewed Artemis architecture (Orion, Space Launch System, Exploration Ground Systems), and 0 otherwise. | Budget Portfolio designations on the individual project pages of GAO-22-105212
baseline_dev_cost_musd | Original baseline development cost estimate in then-year millions of United States dollars, set at the project's confirmation review. | GAO-22-105212 Table 6; GAO-21-306 Table 2
cost_overrun_musd | Cumulative development cost overrun against the original baseline, in then-year millions of United States dollars. Negative values denote underruns. | GAO-22-105212 Table 6; GAO-21-306 Table 2
schedule_slip_months | Cumulative launch or milestone delay against the original baseline schedule, in months. Negative values denote earlier than baselined dates. | GAO-22-105212 Table 6; GAO-21-306 Table 2
program | Name of the NASA major project (life-cycle cost above 250 million dollars) as reported by GAO. | GAO-22-105212; GAO-21-306
agency | Sponsoring agency for the project. All twenty-two observations are NASA major projects, so the national space-effort measure varies only through the year of baseline commitment. | GAO-22-105212; GAO-21-306
source | Provenance string naming, for each row, the specific GAO table supplying the cost and schedule values, the specific GAO document supplying the baseline year, and the macroeconomic series supplying budget and GDP. | Compiled by the author from [6][7][8][10][11]

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -69.4687 | 253.6716 | -0.2739 | 0.7842 | -566.6558 | 427.7185
space_spend_pct_gdp | 347.5327 | 2621.8217 | 0.1326 | 0.8945 | -4791.1435 | 5486.2089
space_effort_ratio_pct | 0.2141 | 0.564 | 0.3795 | 0.7043 | -0.8914 | 1.3196
years_in_development | 13.9596 | 4.6125 | 3.0265 | 0.0025 | 4.9192 | 23
human_spaceflight | -35.5434 | 27.4524 | -1.2947 | 0.1954 | -89.349 | 18.2623

## Fit statistics
Statistic | Value
N | 22
R2 | 0.7003
R2_adj | 0.6298
F | 31.9122
F_p | 1.061e-07