## README
COLLEGIUM empirical evidence workbook
Cost-Growth Hazard in Flagship Astrophysics and Earth-Science Missions: A Cox Proportional-Hazards Analysis of the NASA Major-Project Portfolio
Candidate: Liv Renner (1B-AST-049)
Method: Cox proportional-hazards (PHReg)
Hypothesis: The instantaneous hazard of a flagship mission breaching the 15 percent cost-growth threshold rises with the count of immature technologies carried into confirmation and with directed (non-competed) acquisition, while larger baseline budgets and international partnerships do not by themselves protect against breach.
Headline result: directed_flag = -1.0173 (p = 0.2676)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | baseline_cost_b | immature_tech | intl_partners | directed_flag | dev_months | cost_breach | source
James Webb Space Telescope | 9.66 | 10 | 1 | 1 | 141 | 1 | GAO/NASA 2009 rebaseline 9.66B life-cycle (Mar 2021 LRD), 8.8B dev spent, launched 25 Dec 2021; en.wikipedia.org/wiki/James_Webb_Space_Telescope citing GAO and NASA
Mars Science Laboratory (Curiosity) | 1.6 | 6 | 1 | 1 | 80 | 1 | NASA confirmation ~1.6B, final 2.5B (84% overrun per GAO), planned 2009 launch, launched 26 Nov 2011; en.wikipedia.org/wiki/Mars_Science_Laboratory
SOFIA | 0.185 | 4 | 1 | 1 | 96 | 1 | NASA cost grew 185M to 330M (GAO 2006 review), multi-year slide to first light May 2010; en.wikipedia.org/wiki/Stratospheric_Observatory_for_Infrared_Astronomy
InSight | 0.675 | 3 | 2 | 0 | 60 | 1 | NASA cost 675M to 830M after SEIS leak, planned Mar 2016, launched 5 May 2018 (26-mo slip); en.wikipedia.org/wiki/InSight
ICESat-2 | 0.731 | 4 | 0 | 0 | 72 | 1 | NASA reported >15% overrun to Congress (2014 60-day report), planned 2015, launched 15 Sep 2018; en.wikipedia.org/wiki/ICESat-2
Psyche | 0.985 | 3 | 0 | 0 | 54 | 1 | NASA baseline 985M, planned Jul/Aug 2022, launched 13 Oct 2023 (software-driven slip, cost growth per JPL/IRB); en.wikipedia.org/wiki/Psyche_(spacecraft)
Europa Clipper | 4.25 | 5 | 0 | 1 | 55 | 1 | NASA agency baseline commitment raised 4.25B to 5.0B (cost growth disclosed 2022), launched 14 Oct 2024; spacepolicyonline.com Europa Clipper cost growth; planetary.org/charts/europa-clipper-cost-chart
NEO Surveyor | 0.6 | 4 | 0 | 0 | 72 | 1 | NASA Phase C confirmation raised estimate from ~600M to 1.2B, launch slipped 2026 to 2027/2028; spacenews.com NEO Surveyor launch delayed; spacepolicyonline.com asteroid-hunting telescope clears review
NASA-ESA Mars Sample Return | 4 | 8 | 1 | 1 | 84 | 1 | Independent Review Board 2023: NASA share grew from ~4B baseline to 8-11B, launch no earlier than 2030 (2-yr slip); spacenews.com MSR budget unrealistic; science.org MSR new price tag
Nancy Grace Roman Space Telescope | 3.2 | 4 | 2 | 1 | 87 | 0 | NASA confirmation Feb 2020 expected dev cost 3.2B, cost cap 3.934B; within life-cycle estimate per GAO Mar 2024 (reserves cover growth); LRD May 2027; en.wikipedia.org/wiki/Nancy_Grace_Roman_Space_Telescope
OSIRIS-REx | 0.8 | 2 | 0 | 0 | 54 | 0 | NASA ~800M (excl launch), planned 2016, launched on schedule 8 Sep 2016; en.wikipedia.org/wiki/OSIRIS-REx
Lucy | 0.981 | 2 | 0 | 0 | 57 | 0 | NASA Discovery cost ~981M, launched at open of window 16 Oct 2021 on schedule; GAO 2024 noted 8M reduction; en.wikipedia.org/wiki/Lucy_(spacecraft); spacepolicyonline.com GAO 2019 assessment
MAVEN | 0.367 | 2 | 0 | 0 | 46 | 0 | NASA dev 366.8M, total 582.5M (came in ~100M under estimate), launched on plan 18 Nov 2013; en.wikipedia.org/wiki/MAVEN
Parker Solar Probe | 1.5 | 5 | 0 | 1 | 90 | 0 | NASA ~1.5B, launched 12 Aug 2018; APL/NASA reported on-schedule delivery; en.wikipedia.org/wiki/Parker_Solar_Probe
Fermi Gamma-ray Space Telescope | 0.69 | 3 | 2 | 0 | 72 | 0 | NASA/GLAST launched on retargeted date 11 Jun 2008; en.wikipedia.org/wiki/Fermi_Gamma-ray_Space_Telescope; NASA NTRS flagship-mission funding presentation 20190001461
TESS | 0.2 | 1 | 0 | 0 | 44 | 0 | NASA Explorer 200M (+87M launch), planned Aug 2017, launched 18 Apr 2018 (~8-mo slip, within Explorer cost); en.wikipedia.org/wiki/Transiting_Exoplanet_Survey_Satellite
GRACE-FO | 0.43 | 2 | 1 | 0 | 60 | 0 | NASA-GFZ Earth science mission, ~430M, launched on schedule 22 May 2018; en.wikipedia.org/wiki/GRACE-FO; jpl.nasa.gov/missions/grace-fo
SWOT | 1.1 | 3 | 2 | 0 | 84 | 0 | NASA-CNES ~1.1B joint investment, launched 16 Dec 2022; swot.jpl.nasa.gov; spacenews/NASA SWOT 1.1B; en.wikipedia.org/wiki/Surface_Water_and_Ocean_Topography
NISAR | 1.12 | 4 | 1 | 1 | 108 | 1 | NASA share ~1.118B of ~1.5B total, multiple slips incl reflector thermal rework, launched 30 Jul 2025; en.wikipedia.org/wiki/NISAR_(satellite); GAO-24-106767
SPHEREx | 0.49 | 2 | 1 | 0 | 60 | 0 | NASA MIDEX 488M total design/build/launch/ops, launched 11/12 Mar 2025; en.wikipedia.org/wiki/SPHEREx; NASA SPHEREx Press Kit Feb 2025
Dragonfly | 0.85 | 6 | 0 | 1 | 109 | 1 | NASA New Frontiers PI cost cap 850M; life-cycle grew to 3.35B, launch slipped Apr 2026 to Jul 2028 (4 directed replans); spacenews.com NASA confirms Dragonfly doubled costs; NASA OIG IG-25-011
Solar Dynamics Observatory | 0.85 | 3 | 0 | 1 | 72 | 0 | NASA LWS ~850M incl 5-yr ops, launched 11 Feb 2010; scientificamerican.com SDO; sdo.gsfc.nasa.gov factsheet
GOES-R (GOES-16) | 1.1 | 5 | 0 | 1 | 96 | 1 | NOAA/NASA GOES-R first satellite experienced cost growth and a six-month launch slip to Nov 2016; spacenews.com GOES-R delayed six months; nesdis.noaa.gov GOES-R baseline report to Congress
Landsat 9 | 0.885 | 2 | 0 | 0 | 60 | 0 | NASA-USGS Landsat 9 life-cycle baseline 885M, launched 27 Sep 2021 on track per GAO; landsat.gsfc.nasa.gov Landsat9_GAO.pdf; congress.gov R46560
Swift (MIDEX Explorer) | 0.25 | 2 | 2 | 0 | 48 | 0 | NASA MIDEX ~250M incl UK/Italy participation, launched 20 Nov 2004; explorers.gsfc.nasa.gov; en.wikipedia.org/wiki/Neil_Gehrels_Swift_Observatory
Mars 2020 (Perseverance) | 2.2 | 5 | 1 | 1 | 72 | 1 | NASA dev cost grew 310M per GAO 2020 assessment, launched 30 Jul 2020; spacepolicyonline.com GAO 2020 NASA assessment; baseline ~2.2B; en.wikipedia.org/wiki/Mars_2020

## Construction
Variable | Definition | Construction / source
dev_months | Development duration in months from project confirmation (KDP-C) to launch readiness; the survival time at risk of a cost breach | Computed from baseline and actual launch dates in GAO and NASA mission records
cost_breach | Event indicator equal to 1 if development or life-cycle cost grew at least 15 percent above the initial baseline commitment (the statutory NASA rebaseline threshold), 0 if censored within threshold | GAO Assessments of Major Projects (GAO-24-106767, GAO-25-107591); NASA OIG audits; mission press kits
baseline_cost_b | Initial baseline development or life-cycle cost commitment at confirmation, in billions of constant-year US dollars | NASA KDP-C confirmation records and GAO project snapshots
immature_tech | Count of low-TRL or heritage-gap technologies and major new development elements at confirmation; a technical-complexity proxy | GAO technology-readiness assessments; NASA mission descriptions; NASA OIG audits
intl_partners | Number of international or inter-agency partners contributing flight hardware or instruments | Mission descriptions in NASA and partner-agency records (CNES, ISRO, ESA, GFZ, NOAA, USGS)
directed_flag | Indicator equal to 1 for a directed strategic or flagship mission and 0 for a competed PI-led mission (Discovery, New Frontiers, Explorer) | NASA program classification and Announcement of Opportunity records

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
baseline_cost_b | -0.126 | 0.2738 | -0.4603 | 0.6453 | -0.6626 | 0.4106 | 0.8816
immature_tech | 0.0337 | 0.382 | 0.0883 | 0.9296 | -0.715 | 0.7824 | 1.0343
intl_partners | -0.3068 | 0.4983 | -0.6158 | 0.538 | -1.2835 | 0.6698 | 0.7358
directed_flag | -1.0173 | 0.9176 | -1.1087 | 0.2676 | -2.8158 | 0.7812 | 0.3616

## Fit statistics
Statistic | Value
N | 26
events | 13