## README
COLLEGIUM empirical evidence workbook
Cost-Growth Hazard in Flagship Astrophysics and Strategic Science Missions: A Cox Proportional-Hazards Analysis of Time-to-Breach
Candidate: Liv Renner (1B-AST-049)
Method: Cox proportional-hazards (PHReg)
Hypothesis: The instantaneous hazard of breaching the 15 percent development cost-growth threshold rises with first-of-kind technology content and instrument complexity, and is shaped by baseline mission scale, so that technologically novel and instrument-dense flagships breach earlier in their development.
Headline result: instr_complexity = 0.0222 (p = 0.7846)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | confirm_year | launch_year | dev_months | breach | baseline_cost_b | ln_base_cost | new_tech | instr_complexity | cost_growth_pct | source
Hubble Space Telescope | 1978 | 1990 | 144 | 1 | 1.18 | 0.1655 | 1 | 5 | 298 | Wikipedia, Hubble Space Telescope (en.wikipedia.org/wiki/Hubble_Space_Telescope); planned 1983 vs launched 1990; ~$4.7B 2010-USD at launch; baseline ~$1.18B 2010-USD [baseline value illustrative]
James Webb Space Telescope | 2008 | 2021 | 156 | 1 | 4.96 | 1.6014 | 1 | 4 | 77 | Planetary Society, Cost of the JWST (planetary.org/articles/cost-of-the-jwst); $4.96B original vs $8.8B final development, ~77% overrun, 2014 planned vs 2021 launch
Chandra X-ray Observatory | 1992 | 1999 | 84 | 1 | 1.2 | 0.1823 | 1 | 4 | 38 | Wikipedia, Chandra X-ray Observatory (en.wikipedia.org/wiki/Chandra_X-ray_Observatory); ~$1.65B at launch after 1992 redesign; baseline ~$1.2B [baseline value illustrative]
Spitzer Space Telescope | 1996 | 2003 | 84 | 1 | 0.72 | -0.3285 | 1 | 3 | 89 | Wikipedia, Spitzer Space Telescope (en.wikipedia.org/wiki/Spitzer_Space_Telescope); rescoped to $720M, total ~$1.36B through ops
Cassini-Huygens | 1990 | 1997 | 84 | 0 | 3.3 | 1.1939 | 1 | 12 | 0 | Powering Science: NASA's Large Strategic Science Missions, NAP 24857 ch.4 (nationalacademies.org/read/24857/chapter/4); came in at cost
Galileo | 1977 | 1989 | 144 | 1 | 0.892 | -0.1143 | 1 | 11 | 56 | Wikipedia / NASA Galileo synthesis; total ~$1.39B of which $892M spacecraft development; launch slipped post-Challenger 1986
Mars Science Laboratory (Curiosity) | 2008 | 2011 | 42 | 1 | 1.1 | 0.0953 | 1 | 10 | 56 | Planetary Society, Cost of MSL Curiosity (planetary.org/space-policy/cost-of-msl-curiosity); $1.1B baseline (2007) vs $2.53B final, ~56% growth, 2009 slip to 2011
Mars 2020 (Perseverance) | 2016 | 2020 | 52 | 1 | 2.04 | 0.7129 | 0 | 7 | 21 | Planetary Society, Cost of Perseverance (planetary.org/space-policy/cost-of-perseverance); $2.04B FY21 estimate, +21.4% over 2017 baseline
Europa Clipper | 2019 | 2024 | 63 | 1 | 4.25 | 1.4469 | 1 | 9 | 18 | SpacePolicyOnline, Europa Clipper Cost Growth (spacepolicyonline.com); KDP-C 2019 baseline $4.25B, agency baseline raised to ~$5B; launched Oct 2024
Psyche | 2019 | 2023 | 48 | 0 | 0.9964 | -0.0036 | 0 | 3 | 0 | GAO Assessments of Major Projects synthesis (gao.gov/products/gao-24-106767); $965.6M actual vs $996.4M baseline (3.1% below) at 2022 assessment; software-driven 2022 to 2023 launch slip (schedule, not dev-cost breach)
Dragonfly | 2024 | 2028 | 48 | 1 | 0.85 | -0.1625 | 1 | 5 | 206 | NASA OIG IG-25-011, NASA's Management of the Dragonfly Project (oig.nasa.gov); ~$850M dev cap vs ~$2.6B dev by 2024, $3.35B lifecycle; April 2026 slip to July 2028
SPHEREx | 2019 | 2025 | 72 | 0 | 0.488 | -0.7174 | 0 | 1 | 0 | Wikipedia, SPHEREx (en.wikipedia.org/wiki/SPHEREx); total $488M design-build-launch-ops; launched March 2025 cost-controlled
Nancy Grace Roman Space Telescope | 2020 | 2027 | 84 | 0 | 3.2 | 1.1632 | 1 | 2 | 0 | Wikipedia, Nancy Grace Roman Space Telescope (en.wikipedia.org/wiki/Nancy_Grace_Roman_Space_Telescope); $3.2B dev / $3.934B cap at 2020 confirmation; pandemic impact absorbed, cost-controlled
SOFIA | 1996 | 2014 | 216 | 1 | 0.23 | -1.4697 | 1 | 3 | 335 | Wikipedia, Stratospheric Observatory for Infrared Astronomy (en.wikipedia.org/wiki/Stratospheric_Observatory_for_Infrared_Astronomy); $230M initial to over $1B development
Kepler Space Telescope | 2001 | 2009 | 96 | 1 | 0.3 | -1.204 | 1 | 1 | 83 | Wikipedia, Kepler space telescope (en.wikipedia.org/wiki/Kepler_space_telescope); $300M cap to ~$550M+, 21% increase accepted 2006
NEO Surveyor | 2022 | 2028 | 72 | 0 | 1.2 | 0.1823 | 1 | 1 | 0 | NEO Surveyor (en.wikipedia.org/wiki/NEO_Surveyor); $1.2B dev baseline, LRD no later than June 2028, at baseline in latest assessment
ICESat-2 | 2014 | 2018 | 48 | 1 | 1 | 0 | 0 | 1 | 8 | GAO Assessments of Major Projects synthesis (gao.gov/products/gao-23-106021); +$84M added 2012 for own launch vehicle; ~$1.0B lifecycle; 70% JCL confirmation
Landsat 9 | 2018 | 2021 | 36 | 1 | 0.885 | -0.1222 | 0 | 2 | 12 | Landsat 9 GAO project sheet (landsat.gsfc.nasa.gov/wp-content/uploads/2018/05/Landsat9_GAO.pdf); $885.0M baseline; 47% JCL for earlier Dec 2020 date, slipped to Sept 2021
GRACE-FO | 2012 | 2018 | 72 | 1 | 0.43 | -0.844 | 0 | 2 | 15 | GAO Assessments of Major Projects (gao.gov/products/gao-23-106021) + GRACE and GRACE-FO (en.wikipedia.org/wiki/GRACE_and_GRACE-FO); $430M NASA cost; external factors drove cost/schedule growth
Mars Observer | 1985 | 1992 | 84 | 1 | 0.813 | -0.2071 | 1 | 7 | 18 | Wikipedia, Mars Observer (en.wikipedia.org/wiki/Mars_Observer); total program ~$813M, grew from lower Observer-class baseline
Magellan | 1984 | 1989 | 60 | 1 | 0.68 | -0.3857 | 0 | 1 | 12 | Astronautix / GAO NSIAD-88-130FS, Magellan (gao.gov/assets/nsiad-88-130fs.pdf); overall ~$680M Venus radar mapper
Gravity Probe B | 2003 | 2004 | 18 | 1 | 0.75 | -0.2877 | 1 | 1 | 40 | Wikipedia, Gravity Probe B (en.wikipedia.org/wiki/Gravity_Probe_B); total project ~$750M after repeated growth and delay
WISE | 2009 | 2009 | 18 | 0 | 0.208 | -1.5702 | 0 | 1 | 0 | JPL, Wide-Field Infrared Survey Explorer (jpl.nasa.gov/missions/wide-field-infrared-survey-explorer-wise); ~$208M JPL cost, delivered near baseline
Juno | 2008 | 2011 | 40 | 0 | 1.13 | 0.1222 | 0 | 9 | 3 | Wikipedia, Juno (en.wikipedia.org/wiki/Juno_(spacecraft)) + JPL press kit; ~$1.13B total New Frontiers, modest growth
OSIRIS-REx | 2013 | 2016 | 40 | 0 | 0.8 | -0.2231 | 0 | 5 | 6 | Wikipedia, OSIRIS-REx (en.wikipedia.org/wiki/OSIRIS-REx); ~$800M excluding launch vehicle, near baseline
NISAR | 2018 | 2024 | 72 | 1 | 0.9 | -0.1054 | 1 | 2 | 20 | GAO Assessments of Major Projects (gao.gov/products/gao-25-107591); external requests + launch-vehicle delays drove cost/schedule growth
ICON | 2017 | 2019 | 30 | 1 | 0.252 | -1.3783 | 0 | 4 | 18 | GAO Assessments of Major Projects (gao.gov/products/gao-24-106767); Explorer-class; external factors drove cost increase / schedule delay

## Construction
Variable | Definition | Construction / source
dev_months | Development duration in months from project confirmation (KDP-C or equivalent baseline commitment) to launch readiness; the survival time. Censored at last assessment for missions not yet launched. | Mission confirmation and launch dates from NASA, GAO Assessments of Major Projects, and mission Wikipedia entries
breach | Event indicator: 1 if the mission's development cost grew beyond the 15 percent rebaseline threshold (the canonical NASA Major-Program cost-growth trigger), 0 if cost-controlled (censored) at last observation. | Cost-growth figures from Planetary Society mission cost pages, NASA OIG, GAO Assessments of Major Projects, and National Academies Powering Science (NAP 24857)
ln_base_cost | Natural logarithm of the baseline development cost commitment in real-year USD billions. | Baseline cost commitments from NASA budget documents, GAO, JPL press kits, and mission Wikipedia entries
new_tech | First-of-kind technology flag: 1 if the mission required novel, low-TRL technology or instrument development at confirmation, 0 if built on established heritage designs. | Mission technology descriptions from NASA mission pages and National Academies Powering Science (NAP 24857)
instr_complexity | Number of distinct science instruments carried, a proxy for integration and interface complexity. | Mission instrument complements from NASA mission pages and mission Wikipedia entries

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
ln_base_cost | 0.0008484 | 0.2834 | 0.003 | 0.9976 | -0.5545 | 0.5562 | 1.0008
new_tech | -1.3449 | 0.6716 | -2.0025 | 0.0452 | -2.6612 | -0.0285 | 0.2606
instr_complexity | 0.0222 | 0.0813 | 0.2734 | 0.7846 | -0.1371 | 0.1815 | 1.0225

## Fit statistics
Statistic | Value
N | 27
events | 19