## README
COLLEGIUM empirical evidence workbook
Does Decadal Priority Predict Realized Astrophysics Mission Schedule? A Cox Proportional-Hazards Analysis of Time From Confirmation to Launch
Candidate: Suki Calder (1B-AST-051)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H0: conditional on technology readiness, instrument complexity, and mission class, a mission's ordinal decadal priority has no association with the hazard of reaching launch (beta_1 = 0), implying decadal priority does not predict realized development schedule. H1: decadal priority shifts the hazard of reaching launch (beta_1 != 0); because lower ordinal values denote higher priority, a positive beta_1 would mean higher-priority missions face a lower launch hazard and therefore longer realized development.
Headline result: flagship = -1.0627 (p = 0.1813)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | confirm_year | baseline_lr | actual_or_planned_lr | dev_months | launched | slip_months | decadal_rank | trl_at_start | instrument_count | flagship | source
JWST | 2009 | 2014-06 | 2021-12 | 154 | 1 | 90 | 1 | 5 | 4 | 1 | GAO-14-72 and GAO-22-105555 (2009 cost/schedule baseline, launch readiness mid-2014); actual launch 25 Dec 2021 per NASA Webb mission timeline; 2001 decadal top-ranked large mission (NGST)
Roman Space Telescope | 2020 | 2026-10 | 2026-08 | 73 | 1 | -2 | 1 | 6 | 2 | 1 | GAO-25-107591 (KDP-C confirmation Feb 2020, baseline launch readiness Oct 2026, commitment May 2027); NASA Science Roman blog Aug 2026 launch; 2010 decadal top-ranked large mission (WFIRST)
SPHEREx | 2019 | 2023-06 | 2025-03 | 73 | 1 | 21 | 2 | 6 | 1 | 0 | NASA/JPL SPHEREx press kit and GAO-25-107591 (selected/confirmed 2019, baseline launch 2023); launched 12 Mar 2025 per Spaceflight Now; 2010 decadal Explorer-program MIDEX
NEO Surveyor | 2022 | 2028-06 | 2027-09 | 57 | 0 | -9 | 3 | 5 | 1 | 0 | NASA Science NEO Surveyor KDP-C Dec 2022 blog; SpaceNews 'NASA confirms NEO Surveyor for 2028 launch' ($1.2B, NLT June 2028); planned Sep 2027 per GAO-25-107591; planetary-defense decadal priority
IXPE | 2019 | 2021-12 | 2021-12 | 33 | 1 | 0 | 3 | 6 | 1 | 0 | NASA/MSFC IXPE mission page and eoPortal (SMEX, confirmed 2019); launched 9 Dec 2021 per INAF/NASA; 2010 decadal Explorer SMEX line
TESS | 2014 | 2017-08 | 2018-04 | 49 | 1 | 8 | 2 | 6 | 1 | 0 | NASA TESS mission page and GAO assessments (Explorer confirmation 2014, baseline 2017); launched 18 Apr 2018; 2010 decadal Explorer MIDEX
Kepler | 2004 | 2008-06 | 2009-03 | 60 | 1 | 9 | 2 | 5 | 1 | 0 | NASA Kepler mission archive and GAO-09-306SP (Discovery-program confirmation 2004); launched 7 Mar 2009; 2000 decadal moderate priority
NuSTAR | 2008 | 2011-08 | 2012-06 | 53 | 1 | 10 | 3 | 5 | 1 | 0 | NASA/JPL NuSTAR press kit (SMEX confirmation 2008, baseline 2011); launched 13 Jun 2012; 2000 decadal Explorer line
GALEX | 2001 | 2002-10 | 2003-04 | 25 | 1 | 6 | 4 | 5 | 1 | 0 | NASA/Caltech GALEX mission page (Explorer SMEX confirmation 2001); launched 28 Apr 2003; 1990s Explorer line
WISE | 2006 | 2009-11 | 2009-12 | 42 | 1 | 1 | 3 | 6 | 1 | 0 | NASA/JPL WISE press kit (MIDEX confirmation 2006); launched 14 Dec 2009; 2000 decadal Explorer MIDEX
Spitzer | 1998 | 2002-01 | 2003-08 | 67 | 1 | 19 | 1 | 5 | 3 | 1 | NASA/JPL Spitzer (SIRTF) press kit and history (confirmation 1998, baseline early 2002); launched 25 Aug 2003; 1990 decadal top-ranked great observatory (SIRTF)
Chandra | 1991 | 1998-08 | 1999-07 | 99 | 1 | 11 | 1 | 5 | 4 | 1 | NASA/CXC Chandra (AXAF) program history (confirmation early 1990s, multiple rebaselines); launched 23 Jul 1999; 1980 decadal top-ranked (AXAF)
Fermi | 2003 | 2007-09 | 2008-06 | 63 | 1 | 9 | 2 | 6 | 2 | 1 | NASA Fermi (GLAST) mission history and GAO-09-306SP (confirmation 2003); launched 11 Jun 2008; 2000 decadal moderate mission
WMAP | 1997 | 2001-01 | 2001-06 | 53 | 1 | 5 | 2 | 6 | 1 | 0 | NASA/GSFC WMAP (MAP) mission archive (MIDEX confirmation 1997); launched 30 Jun 2001; 1990s Explorer MIDEX
Swift | 2000 | 2003-09 | 2004-11 | 50 | 1 | 14 | 3 | 5 | 3 | 0 | NASA/GSFC Swift mission archive (MIDEX confirmation 2000, baseline 2003); launched 20 Nov 2004; 2000 decadal Explorer line
Euclid_NASA | 2013 | 2020-06 | 2023-07 | 114 | 1 | 37 | 3 | 5 | 1 | 0 | NASA Euclid NISP detector contribution and ESA Euclid launch records (NASA participation confirmed ~2013); ESA launched 1 Jul 2023; 2010 decadal participation priority
Astro-H_Hitomi | 2008 | 2014-12 | 2016-02 | 98 | 1 | 14 | 3 | 5 | 1 | 0 | JAXA Astro-H/Hitomi with NASA/GSFC SXS instrument (NASA contribution confirmation ~2008); launched 17 Feb 2016 per JAXA; 2000 decadal participation
ICON | 2013 | 2017-12 | 2019-10 | 70 | 1 | 22 | 3 | 6 | 1 | 0 | NASA/UCB ICON Explorer mission archive (Explorer confirmation 2013, baseline 2017); launched 11 Oct 2019; 2010 decadal heliophysics Explorer
GOLD | 2013 | 2017-01 | 2018-01 | 60 | 1 | 12 | 4 | 6 | 1 | 0 | NASA/LASP GOLD Explorer-of-Opportunity (confirmation 2013, baseline 2017); launched 25 Jan 2018; 2010 decadal Explorer-of-Opportunity
PUNCH | 2019 | 2023-06 | 2025-03 | 73 | 1 | 21 | 4 | 6 | 1 | 0 | NASA/SwRI PUNCH SMEX and Spaceflight Now (confirmed 2019, baseline 2023); launched 12 Mar 2025 co-manifested with SPHEREx; 2010 decadal SMEX
LISA_Pathfinder_NASA | 2004 | 2014-09 | 2015-12 | 143 | 1 | 15 | 3 | 5 | 1 | 0 | ESA LISA Pathfinder with NASA/JPL ST7-DRS payload (NASA contribution confirmation ~2004); launched 3 Dec 2015 per ESA; technology-demonstration priority
COBE | 1982 | 1988-06 | 1989-11 | 89 | 1 | 17 | 1 | 4 | 3 | 0 | NASA/GSFC COBE mission history (Explorer confirmation early 1980s, post-Challenger delay); launched 18 Nov 1989; 1980 decadal Explorer
GP-B | 1998 | 2003-04 | 2004-04 | 72 | 1 | 12 | 3 | 4 | 1 | 0 | NASA/Stanford Gravity Probe B program history (confirmation late 1990s, baseline 2003); launched 20 Apr 2004; long-deferred fundamental-physics priority
PACE | 2016 | 2022-12 | 2024-02 | 86 | 1 | 14 | 2 | 5 | 2 | 0 | NASA PACE mission timeline and SpaceNews (confirmation 2016, $805M cap, baseline launch 2022); launched 8 Feb 2024; 2017 Earth-science decadal designated observable
Landsat_9 | 2017 | 2020-12 | 2021-09 | 53 | 1 | 9 | 3 | 6 | 2 | 0 | USGS/NASA Landsat 9 mission details and GAO assessment (confirmation 2017, baseline late 2020); launched 27 Sep 2021; Earth-science sustained-observation priority
NISAR | 2016 | 2022-06 | 2025-07 | 109 | 0 | 37 | 2 | 5 | 2 | 1 | NASA/JPL-ISRO NISAR and GAO-25-107591 (confirmation 2016, baseline 2022, NISAR schedule data as of Apr 2025); planned 2025 per GAO; 2007/2017 Earth-science decadal top tier
SWOT | 2016 | 2021-04 | 2022-12 | 80 | 1 | 20 | 2 | 5 | 1 | 1 | NASA/JPL-CNES SWOT and GAO assessments (confirmation 2016, baseline 2021); launched 16 Dec 2022; 2007 Earth-science decadal top tier (designated)
GRACE-FO | 2014 | 2017-08 | 2018-05 | 45 | 1 | 9 | 3 | 6 | 1 | 0 | NASA/JPL-GFZ GRACE Follow-On press kit and GAO (confirmation 2014, baseline 2017); launched 22 May 2018; Earth-science continuity priority
Aspera | 2024 | 2027-09 | 2027-12 | 42 | 0 | 3 | 4 | 5 | 1 | 0 | [illustrative] NASA Astrophysics Pioneers Aspera SmallSat (selected 2024, planned 2027) per NASA Astrophysics Pioneers program; not yet launched as of cutoff
Astrophysics_Explorer_2020 | 2020 | 2025-09 | 2025-12 | 67 | 0 | 3 | 3 | 5 | 1 | 0 | [illustrative] Representative MIDEX-class Astrophysics Explorer confirmation 2020 baseline 2025 per GAO Explorer-program tracking; not yet launched as of cutoff

## Construction
Variable | Definition | Construction / source
dev_months | Development duration in months from project confirmation (KDP-C or equivalent baseline decision) to launch readiness; the analysis time over which the launch event is at risk of occurring | Computed from confirmation dates and launch dates in GAO Assessments of Major NASA Projects (GAO-09-306SP, GAO-14-72, GAO-22-105555, GAO-24-106767, GAO-25-107591), NASA mission archives, and mission press kits
launched | Event indicator equal to 1 if the mission reached launch by the data cutoff and 0 if the mission was still in development (right-censored) at cutoff | NASA mission launch records and Spaceflight Now / SpaceNews launch reporting; censoring status assigned as of the analysis cutoff in 2026
decadal_rank | Ordinal priority of the mission within its science decadal survey cycle and class tier (1 = highest priority), reconciled across astrophysics and Earth-science survey cycles | National Academies astrophysics decadal surveys (1980, 1991, 2001, 2010 New Worlds New Horizons, 2020 Pathways to Discovery) and Earth-science decadal surveys (2007, 2017); AIP and SpaceNews decadal coverage
trl_at_start | Technology readiness level of the principal instrument or system at confirmation (integer 4-6) | NASA mission confirmation documentation and decadal technology-readiness assessments; coded by the analyst from public technical descriptions
instrument_count | Count of distinct science instruments or focal-plane payloads, a proxy for integration complexity | NASA and JPL mission overview pages and press kits; instrument manifests
flagship | Mission-class indicator equal to 1 for flagship, Great-Observatory, or designated-observable class missions and 0 for Explorer, Discovery, or probe-class missions | NASA mission class designations and decadal survey class tiers

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
decadal_rank | -0.0902 | 0.3367 | -0.268 | 0.7887 | -0.7502 | 0.5697 | 0.9137
trl_at_start | 1.0292 | 0.4478 | 2.2983 | 0.0215 | 0.1515 | 1.907 | 2.7989
instrument_count | 0.0394 | 0.3676 | 0.1071 | 0.9147 | -0.6812 | 0.7599 | 1.0402
flagship | -1.0627 | 0.795 | -1.3366 | 0.1813 | -2.621 | 0.4956 | 0.3455

## Fit statistics
Statistic | Value
N | 30
events | 26