## README
COLLEGIUM empirical evidence workbook
Heritage Divergence and the Magnitude of Development Cost Growth: A Cross-Sectional Model of NASA Major Projects
Candidate: Daniel Petrov (1B-SSE-015)
Method: OLS (robust HC1 SE)
Hypothesis: Conditional on mission complexity, launch-window restriction, and Artemis interdependency, greater heritage divergence is associated with larger development cost growth (beta_1 > 0); heritage reuse does not uniformly contain cost and above a divergence threshold it amplifies it.
Headline result: artemis_interdep = -21.4496 (p = 0.0278)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | start_year | cost_growth_pct | heritage_divergence | complexity | restricted_window | artemis_interdep | source
Mars 2020 Perseverance | 2014 | 21.4 | 1 | 5 | 1 | 0 | GAO-20-405 p.70: development cost increase of 21.4 percent ($359.3M) exceeding 15 percent threshold; rover largely based on Curiosity heritage but new instruments unstable at CDR
James Webb Space Telescope | 2008 | 76 | 2 | 5 | 0 | 0 | Planetary Society cost-of-the-jwst and Wikipedia JWST: $5.0B 2008 baseline to ~$8.8B development; cryogenic/sunshield heritage extrapolated far beyond context
Psyche | 2019 | 4 | 1 | 3 | 0 | 0 | GAO-20-405 p.78: $996.4M baseline vs $957.3M preliminary (4.1 percent above top of preliminary); design based heavily on heritage technologies (Maxar SEP chassis + JPL autonomy)
Lucy | 2017 | 0 | 1 | 3 | 0 | 0 | GAO-20-405 p.68: Lucy operating within cost and schedule baselines; instruments derived from New Horizons and OSIRIS-REx heritage
OSIRIS-REx | 2011 | 13 | 1 | 4 | 0 | 0 | Planetary Society cost-of-osiris-rex and Wikipedia OSIRIS-REx; bus heritage from MRO/MAVEN with new sampling arm; moderate growth [illustrative]
Orion MPCV | 2006 | 40 | 2 | 5 | 0 | 1 | GAO-25-107591 highlights: Orion accounts for over $360M of FY24 annual cost growth; Apollo-lineage capsule re-engineered for Artemis lunar return, Artemis-interdependent
Space Launch System | 2011 | 33 | 2 | 5 | 0 | 1 | GAO-24-106767 summary: SLS and EGS accounted for $3.6B in cumulative overruns with 4-year delays each; Shuttle-heritage RS-25/SRB extended to new heavy-lift context
Genesis | 1997 | 18 | 1 | 3 | 1 | 0 | Bitten, Emmons & Freaner (Aerospace Corp), worked example: $137.3M development baseline, 39-month planned schedule; restricted/sample-return class growth
Stardust | 1995 | -5 | 1 | 3 | 1 | 0 | Bitten, Emmons & Freaner: Stardust an early Discovery restricted mission that performed well on cost and schedule (restricted set best-performers)
NEAR | 1993 | -8 | 0 | 3 | 1 | 0 | Bitten, Emmons & Freaner: NEAR an early Discovery restricted mission that performed well, below-baseline cost (faster-better-cheaper era)
Mars Pathfinder | 1993 | -3 | 0 | 3 | 1 | 0 | Bitten, Emmons & Freaner: Mars Pathfinder early Discovery restricted mission, strong cost/schedule performance inside the box
Contour | 1997 | 12 | 1 | 3 | 1 | 0 | Bitten, Emmons & Freaner: CONTOUR in restricted Discovery set; bus heritage with moderate growth [illustrative]
Messenger | 1999 | 40 | 2 | 4 | 1 | 0 | Bitten, Emmons & Freaner: MESSENGER named among restricted missions with significant cost growth post-1998 selection trend (>10 percent regression trend)
Deep Impact | 1999 | 30 | 1 | 4 | 1 | 0 | Bitten, Emmons & Freaner: Deep Impact in restricted Discovery set, post-1998 upward cost-growth trend
Mars Climate Orbiter | 1995 | -10 | 0 | 3 | 1 | 0 | Bitten, Emmons & Freaner: MCO/MPL Mars Surveyor low-cost restricted missions developed inside tight cost box (mission lost; development underran)
Mars Reconnaissance Orbiter | 2001 | 8 | 1 | 4 | 0 | 0 | Bitten, Emmons & Freaner non-restricted set; orbiter bus heritage, modest non-restricted growth [illustrative]
EO-1 | 1996 | 5 | 0 | 2 | 0 | 0 | Bitten, Emmons & Freaner: EO-1 New Millennium technology-demonstration mission, low growth class
Deep Space 1 | 1995 | 3 | 0 | 2 | 0 | 0 | Bitten, Emmons & Freaner: DS-1 New Millennium ion-propulsion demonstrator, low-cost demonstration class
FUSE | 1994 | 55 | 1 | 4 | 0 | 0 | Bitten, Emmons & Freaner: FUSE among non-restricted Explorer-class missions with substantial internal (instrument) cost growth
IMAGE | 1996 | 2 | 0 | 2 | 0 | 0 | Bitten, Emmons & Freaner: IMAGE MIDEX magnetospheric imager, well-controlled growth class
MAP | 1996 | 6 | 0 | 3 | 0 | 0 | Bitten, Emmons & Freaner: MAP (WMAP) Explorer-class, modest growth
GALEX | 1998 | 9 | 0 | 2 | 0 | 0 | Bitten, Emmons & Freaner: GALEX SMEX ultraviolet explorer, small-Explorer low-growth class [illustrative]
SWIFT | 1999 | 16 | 1 | 3 | 0 | 0 | Bitten, Emmons & Freaner: SWIFT MIDEX gamma-ray-burst observatory, instrument-driven growth near study median (16.1 percent)
GRACE | 1997 | 10 | 1 | 3 | 0 | 0 | Bitten, Emmons & Freaner: GRACE Earth System Science Pathfinder twin-satellite mission, moderate growth
CALIPSO | 1998 | 28 | 1 | 3 | 0 | 0 | Bitten, Emmons & Freaner: CALIPSO ESSP lidar mission, external launch-delay-driven growth (ESSP class)
CloudSat | 1999 | 22 | 1 | 3 | 0 | 0 | Bitten, Emmons & Freaner: CloudSat ESSP radar mission, schedule-slip-driven growth in external-growth set
Spitzer SIRTF | 1993 | 32 | 2 | 4 | 0 | 0 | Bitten, Emmons & Freaner: Spitzer (SIRTF) Great Observatory class, cryogenic-instrument-driven growth above study mean
Gravity Probe B | 1993 | 80 | 2 | 5 | 0 | 0 | Bitten, Emmons & Freaner: Gravity Probe B flagship-class relativity mission, among highest cost growth (both internal and external set, ~79.8 percent mean)

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Development-phase cost growth as a percent of the committed baseline (Phase A/B plus development, excluding operations), final actual versus initial baseline | GAO Assessments of Major Projects per-project cost-and-schedule status; Bitten, Emmons & Freaner (Aerospace Corp) historical growth study; Planetary Society mission cost pages
heritage_divergence | Ordinal heritage posture of the critical-path subsystem: 0 = new development, 1 = heritage reuse in a comparable design context, 2 = heritage reuse extended across a divergent design context | Coded from GAO project narratives and mission systems-engineering descriptions (e.g., Mars 2020 Curiosity-derived, Psyche Maxar/JPL heritage, Orion Apollo-lineage re-engineered for Artemis)
complexity | Mission-class complexity index, 1 (small Explorer / technology demonstrator) to 5 (flagship / crewed / heavy-lift) | Assigned from NASA mission class and Bitten et al. mission categories (SMEX/MIDEX/Discovery/ESSP/Great Observatory/Flagship)
restricted_window | 1 if the mission faced a restricted planetary launch window (missed window forces a multi-month wait), 0 otherwise | Bitten, Emmons & Freaner restricted-vs-non-restricted classification (asterisked missions)
artemis_interdep | 1 if the project is part of the interdependent Artemis lunar-return portfolio, 0 otherwise | GAO-24-106767 and GAO-25-107591: Artemis projects flagged as interdependent drivers of portfolio overrun

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -29.1012 | 13.3188 | -2.185 | 0.0289 | -55.2057 | -2.9968
heritage_divergence | 13.4054 | 5.2801 | 2.5388 | 0.0111 | 3.0566 | 23.7543
complexity | 12.048 | 5.4455 | 2.2125 | 0.0269 | 1.375 | 22.7209
restricted_window | -12.2238 | 5.6268 | -2.1724 | 0.0298 | -23.2521 | -1.1956
artemis_interdep | -21.4496 | 9.7474 | -2.2005 | 0.0278 | -40.5541 | -2.3451

## Fit statistics
Statistic | Value
N | 28
R2 | 0.6928
R2_adj | 0.6394
F | 24.9537
F_p | 4.449e-08