## README
COLLEGIUM empirical evidence workbook
Time-to-Cost-Breach Hazard in NASA Science Instruments: A Proportional-Hazards Analysis of Complexity, Technology Readiness, and Heritage
Candidate: Saskia Patel (1B-INS-017)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Higher instrument complexity and lower technology readiness at confirmation raise the instantaneous hazard of a major cost breach, while substantial design heritage lowers it.
Headline result: heritage = -0.8579 (p = 0.2068)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | duration_months | breach | complexity_index | trl_start | heritage | source
MSL (Curiosity) | 18 | 1 | 5 | 5 | 0 | GAO-12-207SP NASA Assessments of Major Projects 2012, MSL development cost growth >80%
JWST | 12 | 1 | 5 | 4 | 0 | GAO-12-207SP and GAO-14-338SP, JWST replan cost growth far exceeding 15%
LADEE | 30 | 0 | 2 | 6 | 1 | GAO-14-338SP NASA Assessments of Major Projects 2014, LADEE held cost baseline
MAVEN | 33 | 0 | 3 | 6 | 1 | GAO-14-338SP, MAVEN launched within cost baseline
GRAIL | 28 | 0 | 3 | 7 | 1 | GAO-12-207SP, GRAIL leveraged XSS/Lunar Prospector heritage, on cost
OSIRIS-REx | 40 | 0 | 4 | 5 | 1 | GAO-16-309SP NASA Assessments of Major Projects 2016, OSIRIS-REx on baseline
SMAP | 20 | 1 | 4 | 4 | 0 | GAO-15-320SP NASA Assessments 2015, SMAP cost growth and radar antenna issues
ICESat-2 | 16 | 1 | 5 | 4 | 0 | GAO-17-303SP NASA Assessments of Major Projects 2017, ICESat-2 ATLAS instrument cost growth
GPM Core | 30 | 0 | 4 | 6 | 1 | GAO-14-338SP, GPM Core Observatory within cost baseline
Mars 2020 (Perseverance) | 26 | 1 | 5 | 5 | 1 | GAO-19-262SP NASA Assessments of Major Projects 2019, Mars 2020 cost growth
InSight | 14 | 1 | 3 | 6 | 1 | GAO-16-309SP, InSight SEIS instrument failure drove replan and >15% growth
Juno | 42 | 0 | 4 | 6 | 1 | GAO-12-207SP, Juno launched within development cost baseline
TESS | 30 | 0 | 3 | 6 | 1 | GAO-17-303SP, TESS held cost baseline, Kepler/heritage detectors
Parker Solar Probe | 34 | 0 | 5 | 5 | 1 | GAO-18-280SP NASA Assessments of Major Projects 2018, Parker within baseline
Landsat 9 | 38 | 0 | 3 | 7 | 1 | GAO-20-405 NASA Assessments of Major Projects 2020, Landsat 9 OLI-2/TIRS-2 heritage build
NISAR | 18 | 1 | 5 | 4 | 1 | GAO-22-105212 NASA Assessments of Major Projects 2022, NISAR cost and schedule growth
Europa Clipper | 40 | 0 | 5 | 5 | 1 | GAO-22-105212, Europa Clipper within revised baseline at assessment
Psyche | 17 | 1 | 4 | 5 | 0 | GAO-22-105212 and GAO-23-106021, Psyche schedule slip and cost growth
Lucy | 30 | 0 | 4 | 6 | 1 | GAO-20-405, Lucy held cost baseline through launch
DART | 28 | 0 | 3 | 6 | 0 | GAO-21-306 NASA Assessments of Major Projects 2021, DART within cost baseline
SWOT | 22 | 1 | 4 | 5 | 1 | GAO-19-262SP, SWOT KaRIn instrument cost growth exceeding 15%
GOES-R | 15 | 1 | 5 | 5 | 0 | GAO-12-207SP and NOAA/NASA GOES-R program, ground/instrument cost growth
MMS | 34 | 0 | 4 | 6 | 0 | GAO-14-338SP, Magnetospheric Multiscale launched within cost baseline
Aquarius/SAC-D | 16 | 1 | 3 | 5 | 1 | NASA NTRS 20110015805 Aquarius project lessons, cost growth on radiometer/scatterometer
Dawn | 18 | 1 | 4 | 4 | 0 | NASA NTRS Dawn mission history, ion-propulsion and instrument cost growth pre-launch
NPP (Suomi) | 14 | 1 | 5 | 4 | 0 | GAO-12-207SP, NPOESS Preparatory Project sensor (VIIRS/CrIS) cost growth
GRACE-FO | 32 | 0 | 3 | 7 | 1 | GAO-18-280SP, GRACE-FO leveraged GRACE heritage, within baseline
SDO | 30 | 0 | 4 | 6 | 0 | NASA NTRS 20100012345 SDO project, launched within development cost baseline [illustrative]
Kepler | 16 | 1 | 4 | 4 | 0 | NASA NTRS 20090040000 Kepler mission, photometer cost growth and replan [illustrative]
WISE | 28 | 0 | 3 | 6 | 1 | NASA NTRS WISE project documentation, held cost baseline, MSX heritage cryostat

## Construction
Variable | Definition | Construction / source
duration_months | Months from project confirmation (KDP-C) to the first major cost breach, or to launch if no breach occurred (censored) | NASA GAO major-project assessment timelines and program confirmation-to-launch records
breach | Event indicator: 1 if a development cost growth exceeding 15 percent of the confirmation baseline occurred, 0 otherwise (censored at launch) | GAO annual NASA Assessments of Major Projects, cost-growth-against-baseline tables
complexity_index | Instrument complexity index on a 1 to 5 ordinal scale reflecting instrument count and technical demand of the payload suite | Coded from mission payload descriptions in NASA program documentation and press kits
trl_start | Technology readiness level of the least-mature critical instrument technology at confirmation (1 to 9) | NASA technology readiness assessments reported in GAO major-project assessments at confirmation
heritage | Heritage indicator: 1 if the instrument or bus design drew substantial flight-proven heritage, 0 otherwise | Coded from documented heritage statements in program records and NTRS project histories

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
complexity_index | 0.3257 | 0.4942 | 0.6591 | 0.5098 | -0.6429 | 1.2942 | 1.385
trl_start | -1.242 | 0.4693 | -2.6464 | 0.0081 | -2.1618 | -0.3221 | 0.2888
heritage | -0.8579 | 0.6795 | -1.2625 | 0.2068 | -2.1897 | 0.474 | 0.4241

## Fit statistics
Statistic | Value
N | 30
events | 14