## README
COLLEGIUM empirical evidence workbook
What Drives Development Cost Growth in NASA Major Projects? An Ordinary Least Squares Analysis of Scale, Mission Class, and Formulation Maturity
Candidate: Saskia Patel (1B-INS-017)
Method: OLS (robust HC1 SE)
Hypothesis: Percent development cost growth rises with project scale (log life-cycle cost), is higher for flagship-class missions, and is higher for projects carrying early-formulation immaturity, with the formulation-maturity indicator carrying the strongest association.
Headline result: early_formulation = 41.4819 (p = 1.475e-06)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | pct_dev_cost_growth | lcc_musd | log_lcc | flagship | early_formulation | source
JWST | 77.8 | 8825.4 | 9.0854 | 1 | 1 | GAO-18-280SP p.61 project profile: development cost growth +77.8% vs FY2009 rebaseline ($2581.1M->$6188.8M); life-cycle cost estimate $8,825.4M. Flagship astrophysics (Large Strategic). Early-formulation instability: confirmed with immature detectors/sunshield, later rebaselined.
SGSS | 93.4 | 1207.9 | 7.0966 | 0 | 1 | GAO-18-280SP p.89 project profile (Space Network Ground Segment Sustainment): development cost growth +93.4% vs FY2013 baseline ($493.9M->$955.1M); life-cycle cost $1,207.9M. Ground-segment, non-flagship. Early-formulation: software-intensive ground system, severe pre-ORR growth.
ICESat-2 | 36.6 | 1063.6 | 6.9694 | 0 | 1 | GAO-15-320SP Assessments of Large-Scale Projects: ICESat-2 development cost +36.6% ($558.9M->$763.7M) vs original confirmation baseline; life-cycle cost $1,063.6M (GAO-18-280SP p.55). Earth science, non-flagship. Early-formulation: new photon-counting ATLAS laser drove growth.
InSight | 22.8 | 828.9 | 6.7201 | 0 | 1 | GAO-18-280SP p.57 project profile: cumulative development cost growth +22.8% ($541.8M->$673.5M) vs FY2014 baseline; life-cycle cost $828.9M. Discovery planetary, non-flagship. Early-formulation: SEIS seismometer vacuum-seal failure forced 2-year slip and rework.
EGS | 14.9 | 3230.7 | 8.0805 | 1 | 0 | GAO-18-280SP p.51 project profile (Exploration Ground Systems): development cost growth +14.9% ($1,843.5M->$2,264.9M) vs FY2014 baseline; life-cycle cost $3,230.7M. Human-spaceflight ground (Large Strategic). Implementation-phase replan, not early-formulation.
SLS | 1.5 | 9843.2 | 9.1945 | 1 | 0 | GAO-18-280SP p.87 project profile (Space Launch System): development cost growth +1.5% ($7,021.4M->$9,695.4M is then-year; GAO reports +1.5% Feb2018 vs FY2014) ; life-cycle cost $9,843.2M. Human-spaceflight launch vehicle (Large Strategic). Implementation replan.
NISAR | 3.5 | 896.9 | 6.7989 | 0 | 0 | GAO-18-280SP p.81 project profile (NASA-ISRO SAR): development cost growth +3.5% ($661.0M->$683.0M) vs FY2016 baseline; life-cycle cost $896.9M. Earth science, non-flagship. Confirmed near implementation, low early-formulation instability.
Mars2020 | 0.6 | 2458.2 | 7.8072 | 1 | 0 | GAO-18-280SP p.71 project profile (Mars 2020): development cost growth +0.6% ($1,676.9M->$1,687.6M) vs FY2016 baseline; life-cycle cost $2,458.2M. Flagship planetary (Large Strategic, MSL heritage rover). Stable, implementation phase.
PSP | -0.3 | 1548.2 | 7.3448 | 0 | 0 | GAO-18-280SP p.77 project profile (Parker Solar Probe): development cost change -0.3% ($1,055.7M->$1,050.3M) vs FY2014 baseline; life-cycle cost $1,548.2M. Heliophysics LWS, non-flagship. Stable, implementation.
GRACE-FO | 0 | 431.9 | 6.0682 | 0 | 0 | GAO-18-280SP p.53 project profile (GRACE Follow-On): development cost change 0% ($264.0M baseline) vs FY2014; life-cycle cost $431.9M. Earth science, non-flagship. GRACE recurring build, implementation.
ICON | 0 | 252.7 | 5.5322 | 0 | 0 | GAO-18-280SP p.59 project profile (Ionospheric Connection Explorer): development cost change 0% ($196.0M) at GAO-18; life-cycle cost $252.7M. Explorer-class heliophysics, non-flagship. (Later +9.4% in GAO-20-405 after schedule slip.)
Landsat9 | 0 | 885 | 6.7856 | 0 | 0 | GAO-18-280SP p.63 project profile (Landsat 9): development cost change 0% ($634.2M) vs FY2018 baseline; life-cycle cost $885.0M. Earth science, non-flagship. OLI-2/TIRS-2 build-to-print, implementation.
SWOT | 0 | 754.9 | 6.6266 | 0 | 0 | GAO-18-280SP p.89 project profile (Surface Water and Ocean Topography): development cost change 0% ($571.5M) vs FY2016 baseline; life-cycle cost $754.9M. Earth science, non-flagship. Implementation.
RBI | 0 | 304.8 | 5.7197 | 0 | 0 | GAO-18-280SP p.83 project profile (Radiation Budget Instrument): development cost change 0% ($202.0M) vs FY2016 baseline; life-cycle cost $304.8M. Instrument project, non-flagship (later canceled). Implementation phase at assessment.
TDRS | -11 | 336.7 | 5.8192 | 0 | 0 | GAO-18-280SP p.93 project profile (Tracking and Data Relay Satellite): development cost change -11.0% ($323.2M->$283.3M) vs FY2015 baseline; life-cycle cost $336.7M. Comms relay, non-flagship. Recurring TDRS build, implementation.
ICON_2020 | 9.4 | 252.7 | 5.5322 | 0 | 1 | GAO-20-405 Table 2 (p.13): ICON cumulative development cost growth +9.4% (in dollars +9.4M; 24-month schedule slip) vs original FY2014 baseline; life-cycle cost $252.7M (GAO-18-280SP p.59). Explorer heliophysics, non-flagship. Early-formulation: commercial-launch-vehicle and instrument delays.
Aquarius | 17.8 | 400 | 5.9915 | 0 | 1 | GAO-11-239SP Assessments of Large-Scale Projects: Aquarius/SAC-D development cost +17.8% ($193.0M->$227.3M) vs original baseline; life-cycle cost ~$400M (NASA/CONAE Aquarius mission cost, then-year). Earth science, non-flagship. Early-formulation: L-band radiometer growth.
Dawn | 34.5 | 446 | 6.1003 | 0 | 1 | GAO-11-239SP: Dawn development cost +34.5% ($198.0M->$266.4M) vs original confirmation baseline; life-cycle cost ~$446M (NASA Dawn total mission cost). Discovery planetary, non-flagship. Early-formulation: ion-propulsion and instrument integration growth.
Glory | 112.3 | 424 | 6.0497 | 0 | 1 | GAO-11-239SP: Glory development cost +112.3% ($159.0M->$337.6M) vs original baseline; life-cycle cost ~$424M (NASA Glory total, then-year). Earth science, non-flagship. Early-formulation: first spaceflight build of APS aerosol polarimeter.
Kepler | 24.2 | 649 | 6.4754 | 0 | 1 | GAO-11-239SP: Kepler development cost +24.2% ($313.0M->$388.7M) vs original baseline; life-cycle cost ~$649M (NASA Kepler mission total). Discovery astrophysics, non-flagship. Early-formulation: new CCD photometer and focal-plane growth.
LRO | 7.2 | 583 | 6.3682 | 0 | 0 | GAO-11-239SP: Lunar Reconnaissance Orbiter development cost +7.2% ($421.0M->$451.3M) vs original baseline; life-cycle cost ~$583M (NASA LRO total). Lunar science, non-flagship. Implementation, heritage detectors limited early-formulation growth.
MSL | 86 | 2470 | 7.812 | 1 | 1 | GAO-11-239SP: Mars Science Laboratory development cost +86.0% ($969.0M->$1,802.2M) vs original baseline; life-cycle cost ~$2,470M (NASA MSL total). Flagship planetary (Large Strategic). Early-formulation: sky-crane EDL, ChemCam/SAM instrument growth, 2-year slip.
SDO | 11.7 | 856 | 6.7523 | 0 | 0 | GAO-11-239SP: Solar Dynamics Observatory development cost +11.7% ($597.0M->$667.0M) vs original baseline; life-cycle cost ~$856M (NASA SDO total). LWS heliophysics, non-flagship. Implementation phase, contained growth.
WISE | -0.1 | 320 | 5.7683 | 0 | 0 | GAO-11-239SP: Wide-field Infrared Survey Explorer development cost -0.1% ($192.0M->$191.8M) vs original baseline; life-cycle cost ~$320M (NASA WISE total). Explorer astrophysics, non-flagship. Implementation, on-budget.
Suomi-NPP | 26 | 1500 | 7.3132 | 0 | 1 | GAO-11-239SP: NPOESS Preparatory Project (Suomi NPP) development cost +26.0% vs original baseline; life-cycle cost ~$1,500M (NASA/NOAA NPP total). Earth science, non-flagship. Early-formulation: VIIRS sensor and NPOESS-program turbulence drove growth.
SOFIA | 19.3 | 3000 | 8.0064 | 1 | 1 | GAO-11-239SP: Stratospheric Observatory for Infrared Astronomy development cost +19.3% vs baseline; life-cycle cost ~$3,000M (NASA/DLR SOFIA program total, then-year). Large Strategic airborne astrophysics. Early-formulation: airframe modification and telescope integration.
Spitzer | 29.3 | 1300 | 7.1701 | 1 | 1 | GAO-04-642 NASA Lack of Disciplined Cost-Estimating: SIRTF/Spitzer development cost +29.3% ($472.0M->$610.5M) vs original baseline; life-cycle cost ~$1,300M (NASA Spitzer mission total). Great Observatory (Large Strategic) astrophysics. Early-formulation: cryogenic payload growth.
MER | 16.7 | 1080 | 6.9847 | 1 | 0 | GAO-04-642: Mars Exploration Rovers development cost +16.7% ($657.2M->$767.0M) vs original baseline; life-cycle cost ~$1,080M (NASA MER twin-rover program total). Large Strategic planetary. Implementation, Pathfinder heritage limited early instability.
Gravity-Probe-B | 33.9 | 760 | 6.6333 | 0 | 1 | GAO-04-642: Gravity Probe B development cost +33.9% ($529.6M->$709.3M) vs original baseline; life-cycle cost ~$760M (NASA GP-B program total). Fundamental-physics, non-flagship. Early-formulation: cryogenic relativity gyroscope, new technology.
Landsat-7 | 14.1 | 666 | 6.5013 | 0 | 0 | GAO-04-642: Landsat-7 development cost +14.1% ($445.8M->$508.8M) vs original baseline; life-cycle cost ~$666M (NASA/USGS Landsat-7 total). Earth science, non-flagship. Implementation, ETM+ builds on TM heritage.
EO-1 | 57.9 | 200 | 5.2983 | 0 | 1 | GAO-04-642: New Millennium EO-1 development cost +57.9% ($111.7M->$176.4M) vs original baseline; life-cycle cost ~$200M (NASA EO-1 total). Technology-demo Earth science, non-flagship. Early-formulation: first spaceborne hyperspectral imager (Hyperion).

## Construction
Variable | Definition | Construction / source
pct_dev_cost_growth | Cumulative percent growth in development cost relative to the original confirmation (KDP-C) baseline | GAO NASA major-project assessments: GAO-04-642, GAO-11-239SP, GAO-15-320SP, GAO-18-280SP, GAO-20-405. Each value is the development-cost change reported by GAO for the project, cited per row in the source column.
lcc_musd | Life-cycle cost estimate in millions of then-year dollars | GAO assessment project profiles (life-cycle cost estimate) and NASA mission cost records, cited per row
log_lcc | Natural logarithm of the life-cycle cost estimate in millions of dollars | Computed as ln(lcc_musd); enters the model as the scale regressor
flagship | Binary indicator equal to 1 for Large Strategic / flagship-class missions (life-cycle cost and strategic priority placing the project in NASA's largest mission tier), 0 otherwise | Coded from NASA mission-class designation and the GAO portfolio profile
early_formulation | Binary indicator equal to 1 when the project's cost growth was driven by instability rooted in early formulation: significant technology immaturity at confirmation, a first-of-kind instrument or subsystem, or a formulation-era rebaseline, 0 when growth (or stability) occurred in a design-mature, implementation-phase project | Coded from the GAO assessment narrative and project technology-maturity record, cited per row

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -23.2668 | 38.9029 | -0.5981 | 0.5498 | -99.5151 | 52.9815
log_lcc | 3.9157 | 6.1141 | 0.6404 | 0.5219 | -8.0678 | 15.8992
flagship | 1.8936 | 13.4494 | 0.1408 | 0.888 | -24.4667 | 28.254
early_formulation | 41.4819 | 8.616 | 4.8145 | 1.475e-06 | 24.5949 | 58.3689

## Fit statistics
Statistic | Value
N | 31
R2 | 0.4927
R2_adj | 0.4363
F | 9.0353
F_p | 0.0002619