## README
COLLEGIUM empirical evidence workbook
Predicting Major Cost Growth in Cislunar and Comparable NASA Major Projects: A Logit Cliometric Analysis of 30 Demonstrators, 2005-2024
Candidate: Keiko Feld (1B-SDA-097)
Method: Logit (binary outcome)
Hypothesis: Conditional on baseline cost and baseline schedule, cislunar NASA major projects exhibit a higher probability of incurring major cost growth (greater than 25 percent over baseline) than non-cislunar major projects of comparable scope.
Headline result: log_baseline_lrd = 0.9697 (p = 0.612)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | abp_year | baseline_cost_musd | current_cost_musd | cost_growth_pct | baseline_lrd_months | current_lrd_months | schedule_slip_months | cislunar | sponsor_directorate | contracting_instrument | log_baseline_cost | log_baseline_lrd | major_growth | source
Orion MPCV | 2015 | 11300 | 14500 | 28.32 | 93 | 128 | 35 | 1 | ESDMD | cost_plus | 9.3326 | 4.5326 | 1 | GAO-25-107591 (2025); GAO-24-106767 (2024); NASA OIG IG-20-018
SLS Block 1B | 2023 | 4995 | 5700 | 14.11 | 60 | 72 | 12 | 1 | ESDMD | cost_plus | 8.5162 | 4.0943 | 0 | NASA OIG IG-24-015 (Aug 2024); GAO-24-106767 (2024)
Gateway Initial Capability | 2023 | 3562 | 5300 | 48.79 | 48 | 60 | 12 | 1 | ESDMD | mixed | 8.1781 | 3.8712 | 1 | GAO-24-106878 (2024); GAO-24-106767 (2024)
HLS Initial Capability | 2023 | 2890 | 2890 | 0 | 53 | 53 | 0 | 1 | ESDMD | firm_fixed_price | 7.969 | 3.9703 | 0 | GAO-25-107591 (2025); NASA HLS contract Apr 2021
VIPER | 2020 | 433.5 | 609.6 | 40.62 | 36 | 60 | 24 | 1 | SMD | cost_plus | 6.0719 | 3.5835 | 1 | NASA news release 2024-07; SpacePolicyOnline 2024-07; cancelled 2024
Lunar Trailblazer | 2019 | 55 | 63 | 14.55 | 30 | 60 | 30 | 1 | SMD | firm_fixed_price | 4.0073 | 3.4012 | 0 | Caltech Trailblazer cost review page; Wikipedia Lunar Trailblazer
CLPS IM-1 Nova-C | 2018 | 77 | 118 | 53.25 | 36 | 72 | 36 | 1 | SMD | firm_fixed_price | 4.3438 | 3.5835 | 1 | NASA CLPS Task Order awards; Intuitive Machines IM-1 mission record
CLPS Peregrine | 2019 | 79.5 | 108 | 35.85 | 28 | 60 | 32 | 1 | SMD | firm_fixed_price | 4.3758 | 3.3322 | 1 | NASA CLPS Task Order awards 2019; Astrobotic Peregrine M1 record
CLPS Blue Ghost M1 | 2021 | 93.3 | 101 | 8.25 | 40 | 52 | 12 | 1 | SMD | firm_fixed_price | 4.5358 | 3.6889 | 0 | NASA CLPS Task Order to Firefly 2021; mission flown Mar 2025
CAPSTONE | 2019 | 13.7 | 32.7 | 138.69 | 18 | 42 | 24 | 1 | STMD | firm_fixed_price | 2.6174 | 2.8904 | 1 | Advanced Space CAPSTONE program; NASA press kit; launched Jun 2022
LRO | 2005 | 504 | 504 | 0 | 42 | 48 | 6 | 1 | SMD | cost_plus | 6.2226 | 3.7377 | 0 | NASA NSSDCA LRO record; GAO-09-326SP
LADEE | 2008 | 263 | 280 | 6.46 | 40 | 60 | 20 | 1 | SMD | cost_plus | 5.5722 | 3.6889 | 0 | NASA Ames LADEE press kit; NASA mission summary
GRAIL | 2008 | 470 | 496 | 5.53 | 36 | 40 | 4 | 1 | SMD | cost_plus | 6.1527 | 3.5835 | 0 | NASA JPL GRAIL press kit; NASA mission summary
Psyche | 2017 | 996.4 | 1200 | 20.43 | 60 | 84 | 24 | 0 | SMD | cost_plus | 6.9041 | 4.0943 | 0 | NASA news release Jun 2022; GAO-22-105212; planetary.org Psyche
Europa Clipper | 2019 | 4250 | 5200 | 22.35 | 72 | 84 | 12 | 0 | SMD | cost_plus | 8.3547 | 4.2767 | 0 | GAO-24-106767 (2024); SpacePolicyOnline cost growth article 2024
Mars Sample Return | 2020 | 7000 | 11000 | 57.14 | 156 | 240 | 84 | 0 | SMD | cost_plus | 8.8537 | 5.0499 | 1 | NASA Administrator press 2024-04-15; MSR IRB-2 report; SpaceNews 2023-09
Dragonfly | 2019 | 2400 | 3350 | 39.58 | 84 | 108 | 28 | 0 | SMD | cost_plus | 7.7832 | 4.4308 | 1 | NASA OIG IG-25-011 (Sep 2025); SpaceNews 2024-04; NASA confirms cost 2024
Roman Space Telescope | 2020 | 3934 | 4300 | 9.3 | 84 | 84 | 12 | 0 | SMD | cost_plus | 8.2774 | 4.4308 | 0 | NASA KDP-C 2020 baseline; OIG report on COVID impact; NASA Roman page 2025-12
JWST | 2009 | 5000 | 9700 | 94 | 84 | 180 | 96 | 0 | SMD | cost_plus | 8.5172 | 4.4308 | 1 | GAO-12-207SP; Wikipedia JWST cost summary; NASA JWST launch Dec 2021
Lucy | 2017 | 981 | 981 | 0 | 48 | 48 | 0 | 0 | SMD | cost_plus | 6.8886 | 3.8712 | 0 | Planetary Society Lucy cost article; Wikipedia Lucy; NASA Lucy launch Oct 2021
OSAM-1 | 2020 | 808 | 2050 | 153.71 | 36 | 84 | 48 | 0 | STMD | cost_plus | 6.6946 | 3.5835 | 1 | NASA OIG IG-24-002 (Oct 2023); NASA news release 2024-03-01 cancellation
Landsat 9 | 2017 | 650 | 750 | 15.38 | 48 | 56 | 8 | 0 | SMD | cost_plus | 6.477 | 3.8712 | 0 | NASA Landsat 9 GAO project information sheet; Wikipedia Landsat 9
NEO Surveyor | 2022 | 1200 | 1400 | 16.67 | 48 | 72 | 24 | 0 | SMD | cost_plus | 7.0901 | 3.8712 | 0 | GAO-24-106767 (2024); NASA NEO Surveyor program page
NISAR | 2014 | 808 | 1500 | 85.64 | 72 | 132 | 60 | 0 | SMD | cost_plus | 6.6946 | 4.2767 | 1 | NASA NISAR press kit; ISRO-NASA joint mission record; launch Jul 2025
DART | 2017 | 308.5 | 330 | 6.97 | 48 | 60 | 12 | 0 | SMD | cost_plus | 5.7317 | 3.8712 | 0 | NASA APL DART press kit; impact 2022-09-26
Tess | 2014 | 200 | 287 | 43.5 | 42 | 42 | 0 | 0 | SMD | cost_plus | 5.2983 | 3.7377 | 1 | NASA TESS press kit; mission summary
ICON | 2013 | 168 | 242 | 44.05 | 36 | 72 | 36 | 0 | SMD | cost_plus | 5.124 | 3.5835 | 1 | NASA ICON press kit; launched Oct 2019; NASA news
GOES-T | 2015 | 2300 | 2400 | 4.35 | 72 | 84 | 12 | 0 | SMD | cost_plus | 7.7407 | 4.2767 | 0 | NOAA-NASA GOES-R series program; GAO-22-105212
TROPICS | 2019 | 30 | 40 | 33.33 | 30 | 42 | 12 | 0 | SMD | firm_fixed_price | 3.4012 | 3.4012 | 1 | NASA TROPICS press kit; Astra failure Jun 2022; subsequent Rocket Lab launches
ASTHROS | 2019 | 40 | 48 | 20 | 36 | 60 | 24 | 0 | SMD | cost_plus | 3.6889 | 3.5835 | 0 | NASA JPL ASTHROS program page; balloon mission scheduling delays

## Construction
Variable | Definition | Construction / source
major_growth | Binary indicator equal to 1 if cost growth from Agency Baseline Commitment to most-recent estimate exceeds 25 percent, 0 otherwise | Computed by candidate from GAO Major Project Assessments and NASA OIG audits using the 25 percent threshold consistent with NASA Space Flight Program and Project Management Requirements NPR 7120.5F rebaselining trigger
cislunar | Indicator equal to 1 if primary operating regime is cislunar (lunar transfer, lunar orbit, or lunar surface), 0 otherwise | Coded by candidate from mission concept of operations
log_baseline_cost | Natural logarithm of approved Agency Baseline Commitment life-cycle cost in millions of USD | Derived from GAO and NASA baseline at Key Decision Point C or contract award
log_baseline_lrd | Natural logarithm of approved baseline development duration in months from authority to proceed to launch readiness | Derived from GAO and NASA baseline schedule
sponsor_directorate | NASA mission directorate of record: ESDMD, SMD, or STMD | NASA organizational records
contracting_instrument | Dominant contracting vehicle: cost_plus, firm_fixed_price, or mixed | FedBizOpps and NASA contracting record

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high
const | -2.1106 | 5.368 | -0.3932 | 0.6942 | -12.6317 | 8.4105
cislunar | 0.1028 | 0.8603 | 0.1195 | 0.9049 | -1.5834 | 1.789
log_baseline_cost | -0.2881 | 0.4399 | -0.655 | 0.5125 | -1.1502 | 0.574
log_baseline_lrd | 0.9697 | 1.9119 | 0.5072 | 0.612 | -2.7776 | 4.7169

## Fit statistics
Statistic | Value
N | 30
pseudo_R2 | 0.011
LL | -20.4992