## README
COLLEGIUM empirical evidence workbook
Cost-Overrun Hazard in JPL-Class Flight Programs: A Cliometric Survival Model of Development Cost Breach
Candidate: Caspar Mwangi (1B-MPM-062)
Method: Cox proportional-hazards (PHReg)
Hypothesis: The instantaneous hazard of a development cost-overrun breach in a JPL-class flight program rises with new-technology content, flagship scale, and payload complexity, so that the estimated coefficients on new_tech, flagship, and complexity_hi are positive (hazard ratios above one).
Headline result: complexity_hi = 0.5159 (p = 0.6945)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | confirm_year | base_cost_musd | final_cost_musd | duration_months | event | log_base_cost | new_tech | flagship | complexity_hi | source
Mars Science Laboratory (Curiosity) | 2006 | 1600 | 2470 | 62 | 1 | 7.378 | 1 | 1 | 1 | Wikipedia Mars Science Laboratory: medium-cost cap exceeded, final development cost reached $2.47B, 84% overrun, 2009 launch slipped to Nov 2011 (~26 mo)
InSight | 2012 | 675 | 830 | 50 | 1 | 6.515 | 1 | 0 | 1 | Wikipedia InSight: cost grew from $675M to $830M (+$150M) after SEIS vacuum-leak; March 2016 launch postponed to May 2018 (~26 mo delay)
Psyche | 2019 | 996 | 1130 | 48 | 1 | 6.904 | 1 | 0 | 0 | Planetary Society psyche-cost ($960.6M est) and GAO-23-106021 via SpaceNews: cost grew to ~$1.13B by Jan 2023; July 2022 launch slipped to Oct 2023 (~15 mo)
Juno | 2005 | 700 | 960 | 72 | 1 | 6.551 | 0 | 1 | 0 | Wikipedia Juno: ~$700M (FY2003) proposed; NASA budget restrictions postponed June 2009 to Aug 2011 (~26 mo slip) with cost growth
Dawn | 2004 | 373 | 446 | 42 | 1 | 5.921 | 1 | 0 | 1 | Wikipedia Dawn: projected $373M, cost overruns inflated final to $446M (2007); multiple cancellations/reinstatements, 2006 target to Sept 2007
James Webb Space Telescope | 2011 | 8000 | 9700 | 123 | 1 | 8.987 | 1 | 1 | 1 | Wikipedia JWST: 2011 rebaseline $8B cap, final lifecycle $9.7B (+~21%); 2018 baseline launch slipped to Dec 2021 (37 mo)
Europa Clipper | 2019 | 4250 | 5000 | 60 | 1 | 8.355 | 1 | 1 | 1 | SpacePolicyOnline (Zurbuchen): agency baseline commitment changed $4.25B to $5B (+$750M, 17.6%); launched Oct 2024
Mars 2020 (Perseverance) | 2016 | 2200 | 2510 | 52 | 1 | 7.696 | 1 | 1 | 1 | SpacePolicyOnline GAO-24-106767: $310.0M development cost growth from development difficulties and higher procurement costs; launched on-window July 2020
Orion (crew vehicle) | 2015 | 6700 | 7239 | 96 | 1 | 8.81 | 1 | 1 | 1 | SpacePolicyOnline GAO-24-106767: $539.2M development cost increase tied to Artemis I slip and poor contractor performance [base illustrative]
Spitzer Space Telescope | 1998 | 500 | 776 | 60 | 1 | 6.215 | 1 | 1 | 0 | Wikipedia Spitzer: $776M launched Aug 2003 after 1990s redesigns/budget-driven slips of roughly a decade from ~1990 plan [base illustrative]
NISAR | 2014 | 1118 | 1147 | 132 | 1 | 7.019 | 1 | 0 | 1 | Wikipedia NISAR: NASA portion ~$1.118B; 2024 thermal-coating rework returned reflector to JPL, launch slipped to July 2025 from earlier targets
Mars Reconnaissance Orbiter | 2002 | 617 | 720 | 40 | 0 | 6.425 | 0 | 0 | 1 | Wikipedia MRO: ~$720M total; launched on schedule Aug 2005 [base illustrative, censored]
Lucy | 2017 | 981 | 981 | 55 | 0 | 6.889 | 0 | 0 | 0 | Wikipedia Lucy: $981M spacecraft mission; launched on schedule Oct 2021 at opening of launch window (no overrun); GAO-24 noted $8M reduction
MAVEN | 2010 | 367 | 582 | 40 | 0 | 5.905 | 0 | 0 | 0 | Wikipedia MAVEN: development $366.8M, ~$100M under original estimate; launched exactly on plan Nov 18 2013 (censored)
OSIRIS-REx | 2011 | 800 | 1160 | 60 | 0 | 6.685 | 0 | 0 | 0 | Wikipedia OSIRIS-REx: ~$800M primary mission; launched exactly on schedule Sept 8 2016 (censored)
Soil Moisture Active Passive (SMAP) | 2012 | 916 | 916 | 38 | 0 | 6.82 | 0 | 0 | 0 | Wikipedia SMAP: $916M design/development/launch/ops; launched Jan 2015 (censored)
GRAIL | 2008 | 496 | 496 | 40 | 0 | 6.207 | 0 | 0 | 0 | Wikipedia GRAIL: $496M budget; launched two days after plan Sept 10 2011, essentially on schedule (censored)
Fermi (GLAST) | 2004 | 690 | 690 | 48 | 0 | 6.537 | 0 | 1 | 0 | Wikipedia Fermi: launched on schedule June 11 2008 within window; battery-replacement delays days only (censored) [base illustrative]
Parker Solar Probe | 2014 | 1500 | 1500 | 52 | 0 | 7.313 | 1 | 1 | 0 | Wikipedia Parker Solar Probe: ~$1.5B; launched Aug 12 2018 (censored, on-plan after early redesign)
GRACE-FO | 2013 | 430 | 430 | 52 | 0 | 6.064 | 0 | 0 | 0 | Wikipedia GRACE-FO: launched on schedule May 22 2018 (censored) [base illustrative]
SPHEREx | 2019 | 395 | 395 | 40 | 0 | 5.979 | 1 | 0 | 0 | GAO-25-107591 coverage and NASA: SPHEREx attributed apparent reduction to removal of inadvertently included ops costs; launched Mar 2025 (censored) [base illustrative]
Roman Space Telescope | 2020 | 3200 | 3200 | 60 | 0 | 8.071 | 1 | 1 | 1 | Wikipedia/NASA Nancy Grace Roman: ~$3.2B development cap held under review in GAO assessments; in development, no breach as of 2025 (censored) [base illustrative]
NEO Surveyor | 2022 | 1200 | 1200 | 48 | 0 | 7.09 | 1 | 0 | 0 | NASA/GAO: NEO Surveyor ~$1.2B life-cycle commitment, in development under review (censored) [base illustrative]
Dragonfly | 2023 | 3350 | 3350 | 48 | 0 | 8.117 | 1 | 1 | 1 | NASA Dragonfly confirmation ~$3.35B life-cycle commitment (2024); in development, no breach as of 2025 (censored)
DAVINCI | 2021 | 1000 | 1000 | 48 | 0 | 6.908 | 1 | 0 | 1 | NASA Discovery DAVINCI Venus mission ~$1B commitment, in development under GAO review (censored) [base illustrative]
VERITAS | 2021 | 1000 | 1000 | 48 | 0 | 6.908 | 1 | 0 | 1 | NASA Discovery VERITAS Venus mission ~$1B commitment, delayed by JPL institutional issues but cost-cap held under review (censored) [base illustrative]

## Construction
Variable | Definition | Construction / source
duration_months | Months of development exposure from program confirmation (KDP-C) to the cost-overrun breach (for events) or to launch (for censored cases) | Compiled from NASA mission confirmation and launch dates; GAO Assessments of Major Projects (GAO-23-106021, GAO-24-106767, GAO-25-107591) and mission press records
event | Indicator equal to 1 if the program breached the GAO/congressional 15 percent development-cost-growth threshold or underwent a cost-driven agency rebaseline, 0 if censored at launch with no breach | GAO Assessments of Major Projects reporting threshold (15 percent development cost growth or 6-month milestone slip); SpacePolicyOnline GAO coverage
log_base_cost | Natural log of the program baseline (confirmed) development or life-cycle cost commitment in millions of USD | NASA confirmation budgets; The Planetary Society Planetary Science Budget Dataset; mission press kits and Wikipedia mission cost sections
new_tech | Indicator equal to 1 if the program required significant first-of-kind or low-heritage technology, 0 for high-heritage builds | NASA mission descriptions and GAO technology-maturity assessments
flagship | Indicator equal to 1 for flagship or strategic missions above the roughly $1B class, 0 for competed PI-led cost-capped missions (Discovery/New Frontiers/Explorer) | NASA program classification; GAO Assessments of Major Projects
complexity_hi | Indicator equal to 1 for high payload or instrument-integration complexity, 0 otherwise | NASA mission payload manifests and instrument descriptions

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
log_base_cost | -0.9685 | 0.6362 | -1.5221 | 0.128 | -2.2155 | 0.2786 | 0.3797
new_tech | 1.3466 | 1.2942 | 1.0405 | 0.2981 | -1.1901 | 3.8832 | 3.8443
flagship | 1.1354 | 1.0862 | 1.0452 | 0.2959 | -0.9936 | 3.2643 | 3.1123
complexity_hi | 0.5159 | 1.3134 | 0.3928 | 0.6945 | -2.0584 | 3.0902 | 1.6751

## Fit statistics
Statistic | Value
N | 26
events | 11