## README
COLLEGIUM empirical evidence workbook
Drivers of Development Cost Growth in JPL-Class Flight Programs: A Cliometric Ordinary-Least-Squares Model of Scale, Schedule, and First-of-Kind Technology
Candidate: Caspar Mwangi (1B-MPM-062)
Method: OLS (robust HC1 SE)
Hypothesis: Development cost growth in JPL-class flight programs rises with schedule slip and with first-of-kind technology content, while larger baseline programs do not grow proportionally faster once schedule and novelty are held constant.
Headline result: instr_count = 4.5498 (p = 0.0005445)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | cost_growth_pct | ln_base_cost | base_cost_musd | final_cost_musd | sched_delay_mo | ln_mass_kg | mass_kg | instr_count | first_of_kind | mission_class | source
MSL Curiosity | 56 | 7.391 | 1622 | 2530 | 24 | 7.951 | 2839 | 10 | 1 | flagship | Dreier C., The Cost of MSL Curiosity, The Planetary Society, 2014: ~56% cost growth and 2-yr (24 mo) slip to a $2.53B total (baseline ~$1.62B implied) (planetary.org/space-policy/cost-of-msl-curiosity)
JWST | 94 | 8.517 | 5000 | 9700 | 84 | 6.703 | 815 | 4 | 1 | flagship | GAO JWST reporting and GAO-18-273: 95% growth from ~$5.0B (2009 baseline) to ~$9.7B and a ~7-yr (84 mo) launch slip (gao.gov/products/gao-18-273)
Psyche | 18 | 6.791 | 890 | 1050 | 16 | 7.866 | 2608 | 3 | 0 | competed | NASA Psyche lifecycle ~$985M and The Planetary Society Psyche cost page ($960.6M); 1-yr (16 mo) launch slip to 2023 (planetary.org/space-policy/psyche-cost)
InSight | 23 | 6.515 | 675 | 830 | 24 | 6.082 | 438 | 3 | 0 | competed | Foust J., InSight delay adds $150 million, SpaceNews, 2016: $675M baseline to ~$830M and 2-yr (24 mo) slip 2016->2018 (spacenews.com/insight-delay-adds-150-million-to-missions-cost)
SLS Block 1 | 10.3 | 9.18 | 9700 | 10700 | 19 | 0 | 0 | 0 | 1 | flagship | GAO SLS reporting via SpaceNews: +10% from the 2014 baseline to $10.7B and +19 mo to June 2020; launch vehicle mass coded 0 (spacenews.com/jwst-and-sls-drive-up-cost-and-schedule-growth-on-nasa-programs)
Mars 2020 Perseverance | 15 | 7.696 | 2200 | 2530 | 0 | 7.951 | 2839 | 7 | 0 | flagship | Clery D., Cost of Mars 2020 may rise up to 15%, Science (AAAS), 2017: development ~$2.2B, ~15% growth, MSL design reuse, on-time 2020 launch (science.org/content/article/cost-mars-2020-mission-may-rise-15)
Europa Clipper | 17.6 | 8.355 | 4250 | 5000 | 0 | 8.517 | 5000 | 9 | 0 | flagship | Smith M., NASA reveals Europa Clipper cost growth, SpacePolicyOnline, 2024: $4.25B to $5.0B (~17.6%) (spacepolicyonline.com/news/nasa-reveals-europa-clipper-cost-growth-mars-sample-return-replan)
OSIRIS-REx | 4.9 | 6.697 | 810 | 850 | 0 | 7.712 | 2235 | 5 | 0 | competed | Dreier C., Cost of OSIRIS-REx, The Planetary Society (spacecraft development $558.5M, mission $1.16B); near-baseline, on-schedule 2016 launch [illustrative growth est.] (planetary.org/space-policy/cost-of-osiris-rex)
GRAIL | 0 | 6.207 | 496 | 496 | 0 | 5.273 | 195 | 1 | 0 | competed | Dreier C., Implementing Missions Within Budget, The Planetary Society, 2013: GRAIL completed on schedule and under budget; baseline ~$496M (planetary.org/articles/20130529-implementing-missions-within-budget-good-news)
LADEE | 0 | 5.635 | 280 | 280 | 0 | 5.799 | 330 | 4 | 0 | competed | NASA Science LADEE page (~$280M lifecycle); on schedule and under budget per The Planetary Society 2013 within-budget review (science.nasa.gov/mission/ladee)
Orion MPCV | 29 | 9.21 | 10000 | 12900 | 48 | 9.17 | 9600 | 0 | 1 | flagship | GAO-24-106767: Orion accounts for $2.9B (65%) of the portfolio's development overrun; crewed-vehicle first of class with multi-year slip (gao.gov/products/gao-24-106767)
NISAR | 18.1 | 7.147 | 1270 | 1500 | 18 | 7.937 | 2800 | 2 | 1 | competed | NISAR (satellite), Wikipedia and Foust J., NISAR planned to launch March 2025 after antenna repairs, SpaceNews: ~$1.5B total, >1-yr (18 mo) slip, dual-band SAR first of class (en.wikipedia.org/wiki/NISAR_(satellite))
Lucy | 4.1 | 6.856 | 950 | 989 | 0 | 7.378 | 1600 | 3 | 0 | competed | NASA Lucy ~$989M lifecycle (Newsweek; The Planetary Society Lucy cost page); development contained, on-time 2021 launch (planetary.org/space-policy/lucy-cost)
ICESat-2 | 25 | 6.685 | 800 | 1000 | 27 | 7.824 | 2500 | 1 | 1 | operational | Foust J., Paying for ICESat-2 overruns, SpaceNews and Spaceflight Now: ICESat-2 ~$200M+ over budget (~25%) with 2+ yr (27 mo) ATLAS-laser slip; ~$1.1B total (spacenews.com/41729paying-for-icesat-2-overruns-delays-international-earth-science-launches)
Dragonfly | 100 | 7.424 | 1675 | 3350 | 28 | 7.003 | 1100 | 5 | 1 | flagship | NASA OIG IG-25-011 and Foust J., NASA confirms Dragonfly despite doubled costs, SpaceNews: ~2x cost growth to $3.35B lifecycle and >2-yr (28 mo) slip to 2028 (oig.nasa.gov/wp-content/uploads/2025/09/final-report-ig-25-011-nasas-managment-of-the-dragonfly-project.pdf)
Roman Space Telescope | 0 | 8.366 | 4300 | 4300 | 0 | 8.517 | 5000 | 2 | 0 | flagship | Roman Space Telescope reporting (Scientific American; SpaceNews): mission held within its $4.3B lifecycle and ahead of its formal launch readiness date (en.wikipedia.org/wiki/Nancy_Grace_Roman_Space_Telescope)
VIPER | 40 | 6.215 | 500 | 700 | 12 | 6.215 | 500 | 4 | 1 | competed | GAO-24-106767 VIPER: documented cost growth and schedule slip prior to the 2024 cancellation; lunar rover first of class [illustrative pct from GAO trend] (gao.gov/products/gao-24-106767)

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Percent growth of development cost from the confirmation (KDP-C) baseline to the current or final development cost estimate | GAO NASA Assessments of Major Projects (gao-24-106767, gao-23-106021, gao-18-273, gao-08-18); NASA OIG IG-25-011; The Planetary Society mission cost analyses
ln_base_cost | Natural log of the confirmation-baseline development cost in millions of US dollars (program scale proxy) | Mission confirmation baselines from GAO assessments, NASA OIG, The Planetary Society, and Science (AAAS)
sched_delay_mo | Total launch-readiness-date slip in months from the baseline plan | GAO assessments; SpaceNews; The Planetary Society; mission press records
first_of_kind | Indicator equal to 1 when the program fields a first-of-its-class capability (new vehicle, instrument, or operating regime), else 0 | Mission technical descriptions; NASA OIG; GAO assessments
instr_count | Number of distinct science instruments or major payload elements carried | Mission payload manifests and NASA Science mission pages

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 14.0609 | 16.2752 | 0.8639 | 0.3876 | -17.8379 | 45.9596
ln_base_cost | -3.9387 | 2.4384 | -1.6153 | 0.1063 | -8.718 | 0.8405
sched_delay_mo | 0.9079 | 0.0757 | 11.9955 | 3.753e-33 | 0.7595 | 1.0562
first_of_kind | 18.6076 | 10.9293 | 1.7025 | 0.0887 | -2.8135 | 40.0286
instr_count | 4.5498 | 1.3158 | 3.4579 | 0.0005445 | 1.9709 | 7.1287

## Fit statistics
Statistic | Value
N | 17
R2 | 0.779
R2_adj | 0.7054
F | 67.3255
F_p | 4.064e-08