## README
COLLEGIUM empirical evidence workbook
Does an Independent Cost Estimate Delay the First Baseline Breach? A Survival Analysis of NASA Major Projects
Candidate: Annika Pereira (1B-MPM-063)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Conditional on program scope and technology maturity, programs confirmed with a binding independent cost and schedule estimate face a lower hazard of first baseline breach (hazard ratio below one) than programs confirmed on the program office estimate alone.
Headline result: trl_at_confirmation = -1.1084 (p = 0.0065)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | confirmation_year | independent_estimate | scope_class | trl_at_confirmation | baseline_cost_musd | duration_months | breach_event | log_baseline | source
James Webb Space Telescope | 2009 | 0 | 3 | 5 | 5000 | 30 | 1 | 8.5172 | GAO-18-280SP and GAO-21-406, NASA: JWST 2009 rebaseline cost ~$5.0B grew to $8.8B, launch slipped ~7 years; pre-JCL confirmation
Mars Science Laboratory (Curiosity) | 2008 | 0 | 3 | 5 | 1630 | 18 | 1 | 7.3963 | GAO-11-239SP, MSL development cost grew from $1.63B to $2.5B, launch slipped from 2009 to 2011 (~26 mo); confirmed before JCL policy
Orion Multi-Purpose Crew Vehicle | 2015 | 1 | 3 | 6 | 6768 | 28 | 1 | 8.82 | GAO-24-106767, Orion cumulative cost overrun $2.9B (65% of portfolio); JCL applied at 2015 confirmation
Space Launch System | 2014 | 1 | 3 | 6 | 7021 | 30 | 1 | 8.8567 | GAO-24-106767 and GAO-19-262SP, SLS development overran baseline, ~4 year schedule delay; JCL at confirmation
Exploration Ground Systems | 2014 | 1 | 2 | 6 | 2767 | 30 | 1 | 7.9255 | GAO-24-106767, EGS schedule delay ~4 years and cost overrun within the SLS/Orion/EGS triad; JCL applied
GRAIL | 2009 | 1 | 2 | 6 | 496 | 40 | 0 | 6.2066 | GAO-12-207SP, GRAIL launched on schedule August 2011 within cost baseline; SRB/JCL confirmation, no breach
Juno | 2008 | 1 | 3 | 6 | 1107 | 42 | 0 | 7.0094 | GAO-12-207SP, Juno launched August 2011 on baseline schedule and near cost target; no >15% breach
Mars Atmosphere and Volatile Evolution (MAVEN) | 2010 | 1 | 2 | 6 | 671 | 36 | 0 | 6.5088 | GAO-14-338SP, MAVEN launched November 2013 on baseline cost and schedule; JCL applied
Origins Spectral Interpretation (OSIRIS-REx) | 2011 | 1 | 2 | 6 | 800 | 48 | 0 | 6.6846 | GAO-16-309SP, OSIRIS-REx launched September 2016 within baseline; JCL confidence level applied at confirmation
Solar Probe Plus (Parker Solar Probe) | 2014 | 1 | 3 | 5 | 1554 | 40 | 0 | 7.3486 | GAO-18-280SP, Parker Solar Probe launched August 2018 within baseline cost and schedule; JCL applied
Ice Cloud and land Elevation Satellite-2 (ICESat-2) | 2012 | 1 | 2 | 5 | 1077 | 20 | 1 | 6.9819 | GAO-17-303SP, ICESat-2 development cost grew and launch slipped from 2017 to 2018 (~12 mo); JCL applied
Soil Moisture Active Passive (SMAP) | 2012 | 1 | 2 | 6 | 916 | 18 | 1 | 6.82 | GAO-15-320SP, SMAP launch slipped from late 2014 to January 2015; minor cost growth; JCL applied
Magnetospheric Multiscale (MMS) | 2009 | 1 | 2 | 6 | 1100 | 40 | 0 | 7.0031 | GAO-15-320SP, MMS launched March 2015 within baseline; JCL applied at confirmation
Gravity and Extreme Magnetism (GEMS) | 2011 | 1 | 2 | 4 | 119 | 9 | 1 | 4.7791 | GAO-12-207SP, GEMS exceeded cost estimate and was cancelled at confirmation review 2012; JCL flagged overrun early
Psyche | 2019 | 1 | 3 | 5 | 985 | 18 | 1 | 6.8926 | GAO-23-106021 and NASA 2022 release, Psyche launch slipped from 2022 to 2023 (~13 mo), triggered independent review; JCL/SRB applied
Lucy | 2017 | 1 | 2 | 5 | 981 | 30 | 0 | 6.8886 | GAO-19-262SP, Lucy launched October 2021 within baseline cost and schedule; JCL applied
Double Asteroid Redirection Test (DART) | 2017 | 1 | 2 | 5 | 330 | 40 | 0 | 5.7991 | GAO-20-405, DART launched November 2021 within baseline cost; JCL applied
Europa Clipper | 2019 | 1 | 3 | 6 | 4250 | 30 | 1 | 8.3547 | GAO-25-107591, Europa Clipper life-cycle grew toward $5.2B with added reserves; launched Oct 2024; JCL applied
Roman Space Telescope (WFIRST) | 2020 | 1 | 3 | 6 | 3934 | 18 | 1 | 8.2774 | GAO-25-107591, Roman experienced schedule pressure toward Oct 2026 LRD; JCL applied at confirmation
NEO Surveyor | 2022 | 1 | 2 | 5 | 1200 | 18 | 1 | 7.0901 | GAO-23-106021, NEO Surveyor replanned with launch delayed ~2 years to 2027/2028; JCL applied
Dragonfly | 2023 | 1 | 3 | 5 | 3350 | 12 | 1 | 8.1167 | GAO-25-107591 and SpaceNews, Dragonfly replan delayed LRD to July 2028 (~1 year) and raised cost; JCL applied
SPHEREx | 2019 | 1 | 2 | 6 | 488 | 12 | 0 | 6.1903 | GAO-25-107591, SPHEREx launched March 2025 within baseline cost and schedule; JCL applied
Landsat 9 | 2015 | 1 | 2 | 7 | 885 | 24 | 0 | 6.7856 | GAO-19-262SP, Landsat 9 launched September 2021 within baseline; JCL applied
NISAR (NASA-ISRO SAR) | 2016 | 1 | 2 | 5 | 808 | 30 | 1 | 6.6946 | GAO-25-107591, NISAR launch slipped multiple times into 2024/2025; cost grew; JCL applied
DAVINCI | 2021 | 1 | 3 | 4 | 1000 | 15 | 1 | 6.9078 | GAO-24-106767, DAVINCI Venus mission experienced schedule pressure and launch delay; JCL applied
VERITAS | 2021 | 1 | 2 | 5 | 1000 | 9 | 1 | 6.9078 | GAO-23-106021, VERITAS Venus mission delayed at least 3 years due to JPL workforce constraints; JCL applied
Imaging X-ray Polarimetry Explorer (IXPE) | 2017 | 1 | 1 | 6 | 188 | 40 | 0 | 5.2364 | GAO-19-262SP, IXPE launched December 2021 within baseline cost and schedule; JCL applied
Stratospheric Observatory (SOFIA) upgrade | 2008 | 0 | 2 | 5 | 500 | 14 | 1 | 6.2146 | [illustrative] SOFIA program experienced early cost growth before JCL policy; figures approximate from GAO-12-207SP narrative
Transiting Exoplanet Survey Satellite (TESS) | 2013 | 1 | 2 | 6 | 287 | 42 | 0 | 5.6595 | GAO-18-280SP, TESS launched April 2018 within baseline cost and schedule; JCL applied
Surface Water Ocean Topography (SWOT) | 2016 | 1 | 2 | 5 | 1112 | 30 | 1 | 7.0139 | GAO-22-105212, SWOT launch slipped from 2021 to December 2022 (~14 mo); JCL applied
Kepler | 2006 | 0 | 2 | 5 | 312 | 9 | 1 | 5.743 | GAO-09-306SP, Kepler $77.5M development cost growth (24.8%) and 9-month launch delay; confirmed before JCL policy
Glory | 2005 | 0 | 1 | 5 | 259 | 16 | 1 | 5.5568 | GAO-09-306SP, Glory $37.0M development cost growth (14.3%) and 16-month launch delay; pre-JCL confirmation
Lunar Reconnaissance Orbiter | 2006 | 0 | 2 | 6 | 422 | 8 | 1 | 6.045 | GAO-09-306SP, LRO $52.3M development cost growth (12.4%) and 8-month launch delay; pre-JCL confirmation
Aquarius | 2006 | 0 | 1 | 5 | 191 | 10 | 1 | 5.2523 | GAO-09-306SP, Aquarius $15.9M cost growth (8.3%) and 10-month launch delay; pre-JCL confirmation
Gamma-ray Large Area Space Telescope (Fermi/GLAST) | 2005 | 0 | 2 | 5 | 690 | 42 | 0 | 6.5367 | GAO-09-306SP, GLAST launched June 2008 within revised baseline after design churn; pre-JCL confirmation
Dawn | 2004 | 0 | 2 | 5 | 373 | 12 | 1 | 5.9216 | GAO-09-306SP and NASA, Dawn cost grew and was briefly cancelled/reinstated 2006, launch slipped to 2007; pre-JCL confirmation
Wide-field Infrared Survey Explorer (WISE) | 2007 | 0 | 1 | 6 | 320 | 24 | 0 | 5.7683 | GAO-10-227SP, WISE launched December 2009 within baseline cost and schedule; confirmed before full JCL mandate
Mars Reconnaissance Orbiter | 2002 | 0 | 2 | 6 | 720 | 40 | 0 | 6.5793 | GAO-06-647SP, Mars Reconnaissance Orbiter launched August 2005 within baseline; pre-JCL confirmation

## Construction
Variable | Definition | Construction / source
duration_months | Months from confirmation (KDP-C) to the first baseline breach event, or to the censoring date for programs that never breached | Coded from GAO NASA Assessments of Major Projects series (GAO-09-306SP through GAO-25-107591) confirmation and milestone dates
breach_event | 1 if the program recorded a first baseline breach (development cost growth at or above 15 percent or a milestone slip at or above 6 months, NASA's congressional re-reporting trigger), 0 if censored without a breach | GAO NASA Assessments of Major Projects series; NASA major program reporting thresholds
independent_estimate | 1 if a binding independent cost and schedule estimate (Joint Confidence Level / Standing Review Board independent assessment) was applied at confirmation, 0 otherwise (chiefly pre-2009 confirmations before the JCL mandate) | GAO NASA Assessments of Major Projects series; NASA JCL policy history
log_baseline | Natural log of the confirmed baseline life-cycle or development cost estimate in millions of USD, a proxy for program scope | GAO NASA Assessments of Major Projects series baseline cost fields
trl_at_confirmation | Technology readiness level of the driving subsystem at confirmation, a proxy for technology maturity | GAO NASA Assessments of Major Projects technology-maturity narratives; project critical-design-review records

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
independent_estimate | -0.4644 | 0.4436 | -1.0467 | 0.2952 | -1.3339 | 0.4052 | 0.6285
log_baseline | 0.1242 | 0.2299 | 0.5404 | 0.5889 | -0.3264 | 0.5749 | 1.1323
trl_at_confirmation | -1.1084 | 0.4071 | -2.7226 | 0.0065 | -1.9063 | -0.3105 | 0.3301

## Fit statistics
Statistic | Value
N | 38
events | 23