## README
COLLEGIUM empirical evidence workbook
Independent Cost Estimating and the Hazard of Statutory Cost Breach in NASA Major Projects: A Cox Proportional-Hazards Analysis
Candidate: Annika Pereira (1B-MPM-063)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Projects whose confirmation cost baseline was established under a high-confidence independent estimating process (icost_rigor = 1) face a lower hazard of crossing NASA's 15 percent statutory cost-breach threshold, holding project scale and crewed status constant.
Headline result: crewed = 0.7561 (p = 0.3911)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | confirm_year | baseline_lcc_b | icost_rigor | complexity | crewed | months_to_event | event | source
Europa Clipper | 2019 | 4.25 | 1 | 1.447 | 0 | 60 | 1 | GAO-25-107591 NASA Assessments of Major Projects (Jul 2025); Planetary Society Europa Clipper cost chart (baseline $4.25B 2019 -> ~$5.0B, 18% growth, launched Oct 2024)
Roman Space Telescope | 2020 | 3.2 | 1 | 1.163 | 0 | 84 | 0 | NASA WFIRST/Roman confirmation 2 Mar 2020, dev cost $3.2B max $3.934B; SpaceNews 'Pandemic causes delay and cost increase' (launch slip to May 2027, under 15% threshold)
NEO Surveyor | 2022 | 1.2 | 1 | 0.182 | 0 | 72 | 0 | SpacePolicyOnline 'Asteroid-Hunting Telescope Clears NASA Review' (KDP-C 2022, $1.2B baseline, 2-yr slip 2026->2028); SpaceNews 'NEO Surveyor launch delayed despite funding boost'
Psyche | 2019 | 0.99 | 1 | -0.01 | 0 | 57 | 0 | NASA/JPL Psyche confirmation 2019 (~$0.99B at KDP-C); Spaceflight Now / Space.com (final ~$1.13B 2023, ~14% growth, 15-month launch slip, below 15% statutory threshold), launched Oct 2023
Dragonfly | 2024 | 3.35 | 1 | 1.209 | 0 | 18 | 0 | GAO-25-107591 (Dragonfly est. life-cycle $3.35B, launch July 2028); NASA OIG IG-25-011 'NASA's Management of the Dragonfly Project'
SPHEREx | 2021 | 0.49 | 1 | -0.713 | 0 | 48 | 0 | GAO-25-107591 (SPHEREx dev cost reduced $8.3M from prior year, no overrun); NASA SPHEREx confirmation 2021, launched Mar 2025
Lucy | 2017 | 0.98 | 1 | -0.02 | 0 | 48 | 0 | NASA Discovery program Lucy confirmation 2017 (~$0.98B life-cycle); NASA press kit (launched Oct 2021 on schedule, no statutory breach)
OSIRIS-REx | 2013 | 0.8 | 1 | -0.223 | 0 | 84 | 0 | Planetary Society 'Cost of OSIRIS-REx'; NASA New Frontiers OSIRIS-REx confirmation 2013 (~$0.8B), launched Sep 2016 on baseline
InSight | 2014 | 0.68 | 1 | -0.386 | 0 | 49 | 1 | NASA Discovery InSight; NASA OIG and press releases (2015 instrument leak forced 26-month slip from Mar 2016 to May 2018, ~$153.8M cost growth, breached threshold)
Mars 2020 Perseverance | 2016 | 2.44 | 1 | 0.892 | 0 | 55 | 0 | NASA Mars 2020 confirmation 2016 (~$2.44B life-cycle); NASA press kit (launched July 2020 on schedule)
James Webb Space Telescope | 2009 | 5 | 0 | 1.609 | 0 | 108 | 1 | GAO-25-107591 historical-overrun discussion; GAO/NASA replan history (2011 rebaseline to $8.8B from ~$5B, multi-year delay, major statutory breach)
SLS Block 1 | 2014 | 7.02 | 1 | 1.949 | 1 | 84 | 1 | GAO-25-107591 (SLS exited portfolio after $3.6B in overruns and 4-year delay); NASA SLS Block 1 baseline 2014
Orion MPCV | 2015 | 6.77 | 1 | 1.913 | 1 | 120 | 1 | GAO-25-107591 (Orion accounts for >$360M of annual cost growth FY25); NASA Orion baseline; GAO accumulated overrun figures
Exploration Ground Systems | 2014 | 2.74 | 1 | 1.008 | 1 | 84 | 1 | GAO-25-107591 (EGS exited portfolio after $3.6B in overruns and 4-year delay equiv.); NASA EGS baseline 2014
Gateway (PPE/HALO) | 2020 | 5.3 | 0 | 1.668 | 1 | 42 | 1 | GAO-25-107591 (Gateway Initial Capability among 4 projects = ~60% of $32.1B dev portfolio); GAO-24-106767 cost-growth identification
Human Landing System | 2021 | 4 | 0 | 1.386 | 1 | 30 | 1 | GAO-25-107591 (HLS Initial Capability among 4 largest dev projects); GAO HLS schedule/cost-risk findings
NISAR | 2016 | 1.5 | 1 | 0.405 | 0 | 96 | 1 | NASA-ISRO NISAR confirmation 2016 (~$1.5B NASA share baseline ~$0.9B); GAO-25-107591 (NISAR schedule data Apr 2025, multi-year slip 2020->2024)
Landsat 9 | 2017 | 0.88 | 1 | -0.128 | 0 | 48 | 0 | NASA/USGS Landsat 9 confirmation 2017 (~$0.88B); NASA press kit (launched Sep 2021 on baseline)
GRACE Follow-On | 2012 | 0.43 | 1 | -0.844 | 0 | 72 | 0 | NASA/GFZ GRACE-FO confirmation ~2012 (~$0.43B NASA); NASA press kit (launched May 2018, within baseline)
ICESat-2 | 2013 | 1.1 | 1 | 0.095 | 0 | 60 | 1 | NASA ICESat-2 confirmation 2013 (~$1.1B life-cycle); NASA/GAO assessments (ATLAS instrument cost growth and ~2-year slip 2016->2018)
TESS | 2014 | 0.34 | 1 | -1.079 | 0 | 42 | 0 | NASA Explorer TESS confirmation 2014 (~$0.34B); NASA press kit (launched Apr 2018 near baseline)
Parker Solar Probe | 2014 | 1.55 | 1 | 0.438 | 0 | 48 | 0 | NASA LWS Parker Solar Probe confirmation 2014 (~$1.55B life-cycle); NASA press kit (launched Aug 2018 on schedule)
MAVEN | 2010 | 0.67 | 1 | -0.4 | 0 | 40 | 0 | NASA Mars Scout MAVEN confirmation 2010 (~$0.67B); NASA press kit (launched Nov 2013 on baseline)
GOES-R | 2010 | 3 | 0 | 1.099 | 0 | 84 | 1 | NOAA/NASA GOES-R confirmation; GAO weather-satellite assessments (multi-year delay and cost growth, statutory breach)
DART | 2018 | 0.31 | 1 | -1.171 | 0 | 38 | 0 | NASA Planetary Defense DART confirmation 2018 (~$0.31B life-cycle, ~$0.245B dev); NASA press kit (launched Nov 2021 on schedule)
VERITAS | 2021 | 1.2 | 1 | 0.182 | 0 | 36 | 1 | NASA Discovery VERITAS selected 2021; SpaceNews / NASA (institutional stand-down and multi-year delay post-2022, schedule breach)
DAVINCI | 2021 | 1.05 | 1 | 0.049 | 0 | 36 | 1 | NASA Discovery DAVINCI selected 2021; NASA replanning and launch slip 2029->2030s (schedule/cost pressure)
Mars Sample Return | 2022 | 8 | 0 | 2.079 | 0 | 30 | 1 | GAO-25-107591 / NASA Watch (MSR potential life-cycle $8-11B, baseline delayed, independent review board cost breach)

## Construction
Variable | Definition | Construction / source
event | 1 if the project crossed NASA's 15 percent statutory development-cost-growth reporting threshold; 0 if censored (launched or still in development without breaching) | GAO-25-107591 NASA Assessments of Major Projects (Jul 2025): 30 of 53 historical projects stayed below the 15 percent reporting threshold
months_to_event | Months from confirmation (Key Decision Point C) to the first statutory cost breach, or to censoring at launch / latest GAO assessment | NASA confirmation dates and launch dates; GAO annual major-project assessments
icost_rigor | 1 if the confirmation baseline was set under a high-confidence independent process (Joint Confidence Level at the 70 percent policy point, independent cost estimate, Standing Review Board concurrence); 0 otherwise | NASA Joint Confidence Level policy (Kuo 2011; Butts 2009); NASA Standing Review Board Handbook (Gilligan 2023)
complexity | Natural log of the confirmation-phase baseline life-cycle cost in billions of US dollars, a proxy for project scale and technical complexity | NASA confirmation baselines compiled from GAO assessments and Planetary Society cost charts
crewed | 1 if a human-spaceflight or Artemis project; 0 if a robotic science mission | GAO-25-107591 portfolio classification

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
icost_rigor | -1.2453 | 0.7931 | -1.5702 | 0.1164 | -2.7997 | 0.3092 | 0.2879
complexity | -0.277 | 0.5427 | -0.5103 | 0.6098 | -1.3407 | 0.7867 | 0.7581
crewed | 0.7561 | 0.8817 | 0.8576 | 0.3911 | -0.972 | 2.4842 | 2.13

## Fit statistics
Statistic | Value
N | 28
events | 14