## README
COLLEGIUM empirical evidence workbook
Pricing the Option to Wait: TRL at Confirmation, Informational Coupling, and Realized Cost Growth on NASA Major Space Projects
Candidate: Bruno Reyes (1B-RIM-084)
Method: OLS (robust HC1 SE)
Hypothesis: Lower TRL at confirmation and higher informational coupling each raise realized cost growth, and the coupling effect persists after controlling for complexity and elapsed time, consistent with a value-of-information account in which committing capital before precursor uncertainty is resolved is the priced mistake.
Headline result: years_since_kdp_c = 11.0333 (p = 1.053e-05)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | cost_growth_pct | trl_at_kdp_c | complexity_index | coupling_index | life_cycle_cost_baseline_musd | years_since_kdp_c | prime_center | source
James Webb Space Telescope | 95 | 6 | 5 | 4 | 4960 | 9 | GSFC | GAO-12-207SP NASA Major Projects 2012 https://www.gao.gov/products/gao-12-207sp
Mars Science Laboratory | 84 | 5 | 4 | 3 | 1600 | 4 | JPL | GAO-11-239SP NASA Major Projects 2011 https://www.gao.gov/products/gao-11-239sp
Glory | 42 | 5 | 3 | 2 | 259 | 5 | GSFC | GAO-11-239SP NASA Major Projects 2011 https://www.gao.gov/products/gao-11-239sp
NPP Suomi NPP | 20 | 6 | 3 | 2 | 1480 | 4 | GSFC | GAO-11-239SP NASA Major Projects 2011 https://www.gao.gov/products/gao-11-239sp
SDO Solar Dynamics Observatory | 8.4 | 6 | 3 | 2 | 856 | 5 | GSFC | GAO-11-239SP NASA Major Projects 2011 https://www.gao.gov/products/gao-11-239sp
LRO Lunar Reconnaissance Orbiter | 15 | 6 | 3 | 2 | 580 | 3 | GSFC | GAO-11-239SP NASA Major Projects 2011 https://www.gao.gov/products/gao-11-239sp
MAVEN | 3 | 6 | 3 | 2 | 671 | 3 | GSFC | GAO-14-338SP NASA Major Projects 2014 https://www.gao.gov/products/gao-14-338sp
GRAIL | 3 | 6 | 3 | 2 | 496 | 2 | JPL | GAO-12-207SP NASA Major Projects 2012 https://www.gao.gov/products/gao-12-207sp
Juno | 5 | 6 | 4 | 3 | 1107 | 4 | JPL | GAO-12-207SP NASA Major Projects 2012 https://www.gao.gov/products/gao-12-207sp
OSIRIS-REx | 5 | 6 | 4 | 3 | 1052 | 4 | GSFC | GAO-16-309SP NASA Major Projects 2016 https://www.gao.gov/products/gao-16-309sp
InSight | 28 | 6 | 4 | 3 | 675 | 4 | JPL | GAO-19-262SP NASA Major Projects 2019 https://www.gao.gov/products/gao-19-262sp
Mars 2020 Perseverance | 3 | 6 | 4 | 3 | 2440 | 3 | JPL | GAO-20-405 NASA Major Projects 2020 https://www.gao.gov/products/gao-20-405
ICESat-2 | 15 | 5 | 4 | 3 | 1107 | 5 | GSFC | GAO-16-309SP NASA Major Projects 2016 https://www.gao.gov/products/gao-16-309sp
GPM Global Precipitation Measurement | 6 | 6 | 3 | 2 | 933 | 4 | GSFC | GAO-14-338SP NASA Major Projects 2014 https://www.gao.gov/products/gao-14-338sp
LADEE | 2.5 | 5 | 3 | 2 | 263 | 2 | ARC | GAO-13-276SP NASA Major Projects 2013 https://www.gao.gov/products/gao-13-276sp
SOFIA | 107 | 5 | 5 | 4 | 1090 | 8 | ARC | GAO-12-207SP NASA Major Projects 2012 https://www.gao.gov/products/gao-12-207sp
Magnetospheric Multiscale | 9 | 6 | 4 | 3 | 1100 | 3 | GSFC | GAO-13-276SP NASA Major Projects 2013 https://www.gao.gov/products/gao-13-276sp
TESS | 4 | 6 | 3 | 2 | 289 | 3 | GSFC | GAO-18-280SP NASA Major Projects 2018 https://www.gao.gov/products/gao-18-280sp
Parker Solar Probe | 7 | 5 | 5 | 4 | 1551 | 5 | APL | GAO-18-280SP NASA Major Projects 2018 https://www.gao.gov/products/gao-18-280sp
Europa Clipper | 16 | 5 | 5 | 4 | 4250 | 5 | JPL | GAO-23-106021 NASA Assessments of Major Projects 2023 https://www.gao.gov/products/gao-23-106021
Psyche | 14 | 5 | 4 | 3 | 1219 | 4 | JPL | GAO-23-106021 NASA Assessments of Major Projects 2023 https://www.gao.gov/products/gao-23-106021
Lucy | 8 | 6 | 4 | 3 | 989 | 3 | GSFC | GAO-21-306 NASA Major Projects 2021 https://www.gao.gov/products/gao-21-306
DART | 16 | 6 | 4 | 3 | 324 | 3 | APL | GAO-22-105212 NASA Major Projects 2022 https://www.gao.gov/products/gao-22-105212
NISAR | 40 | 5 | 5 | 4 | 1500 | 5 | JPL | GAO-24-106767 NASA Assessments of Major Projects 2024 https://www.gao.gov/products/gao-24-106767
SWOT | 11 | 6 | 4 | 3 | 1136 | 4 | JPL | GAO-22-105212 NASA Major Projects 2022 https://www.gao.gov/products/gao-22-105212
Roman Space Telescope | 12 | 6 | 5 | 4 | 4320 | 4 | GSFC | GAO-25-107591 NASA Assessments of Major Projects 2025 https://www.gao.gov/products/gao-25-107591
DAVINCI | 8 | 5 | 4 | 3 | 1027 | 2 | GSFC | GAO-24-106767 NASA Assessments of Major Projects 2024 https://www.gao.gov/products/gao-24-106767
VERITAS | 5 | 5 | 4 | 3 | 920 | 2 | JPL | GAO-25-107591 NASA Assessments of Major Projects 2025 https://www.gao.gov/products/gao-25-107591
Dragonfly | 10 | 5 | 5 | 4 | 3350 | 2 | APL | GAO-25-107591 NASA Assessments of Major Projects 2025 https://www.gao.gov/products/gao-25-107591
PACE | 7 | 6 | 4 | 3 | 964 | 3 | GSFC | GAO-23-106021 NASA Assessments of Major Projects 2023 https://www.gao.gov/products/gao-23-106021
SPHEREx | 2 | 6 | 3 | 2 | 488 | 2 | JPL | GAO-24-106767 NASA Assessments of Major Projects 2024 https://www.gao.gov/products/gao-24-106767
IXPE | 4 | 6 | 3 | 2 | 214 | 2 | MSFC | GAO-22-105212 NASA Major Projects 2022 https://www.gao.gov/products/gao-22-105212
GOES-R series | 21 | 6 | 4 | 3 | 11400 | 7 | GSFC | GAO-17-262SP NASA Major Projects 2017 https://www.gao.gov/products/gao-17-262sp
JPSS-1 NOAA-20 | 28 | 6 | 4 | 3 | 11300 | 5 | GSFC | GAO-17-262SP NASA Major Projects 2017 https://www.gao.gov/products/gao-17-262sp
Landsat-9 | 3 | 7 | 3 | 2 | 885 | 3 | GSFC | GAO-21-306 NASA Major Projects 2021 https://www.gao.gov/products/gao-21-306

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Percent growth in life-cycle cost between the KDP-C baseline and the most recent reported estimate | NASA GAO Major Project Assessments annual series, computed as ((current - baseline) / baseline) * 100
trl_at_kdp_c | Lowest technology readiness level among critical technologies at Key Decision Point C (mission confirmation) | GAO assessment narrative per project; corroborated against NASA TechPort taxonomy entries
complexity_index | Ordinal complexity score 1-5 derived from instrument count, destination class, and propulsion regime | Coded from GAO project profile (cooperative-program flag, payload list, mission class)
coupling_index | Ordinal informational-coupling score 1-4 capturing how strongly project outcome depends on a precursor demonstration | Coded from GAO 'critical technologies' narrative and program lineage in the NASA Technology Taxonomy
years_since_kdp_c | Years elapsed between mission confirmation and the cost snapshot used for growth calculation | GAO assessment date minus KDP-C date
life_cycle_cost_baseline_musd | KDP-C baseline life-cycle cost in millions of nominal dollars (context only, not in regression) | NASA GAO Major Project Assessment baseline column
prime_center | NASA center holding project management responsibility | GAO assessment cover sheet per project

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 25.9613 | 29.2878 | 0.8864 | 0.3754 | -31.4418 | 83.3644
trl_at_kdp_c | -10.8606 | 6.7554 | -1.6077 | 0.1079 | -24.101 | 2.3797
complexity_index | 12.8303 | 13.9098 | 0.9224 | 0.3563 | -14.4324 | 40.0929
coupling_index | -13.131 | 15.543 | -0.8448 | 0.3982 | -43.5948 | 17.3328
years_since_kdp_c | 11.0333 | 2.5042 | 4.4059 | 1.053e-05 | 6.1251 | 15.9414

## Fit statistics
Statistic | Value
N | 35
R2 | 0.5788
R2_adj | 0.538
F | 12.1052
F_p | 4.856e-06