## README
COLLEGIUM empirical evidence workbook
Pricing the Information Deficit: Entry Technology Readiness, Design Maturity, and Realized Cost Growth in NASA Major Projects
Candidate: Bruno Reyes (1B-RIM-084)
Method: OLS (robust HC1 SE)
Hypothesis: Projects entering the design phase with lower technology readiness and lower design maturity, conditions equivalent to a larger unpriced information deficit, exhibit larger realized cost growth relative to the KDP-C baseline.
Headline result: Lower entry TRL and lower design maturity at PDR are associated with significantly higher realized cost growth, consistent with a positive shadow price on resolving technical uncertainty before committing capital.
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | year_assessed | entry_TRL | design_pct_at_PDR | lifecycle_cost_musd | critical_tech_below_TRL6 | cost_growth_pct | schedule_slip_months | source
JWST | 2020 | 4 | 82 | 9700 | 1 | 95 | 84 | GAO-20-405 NASA Assessments of Major Projects
SLS Block 1 | 2020 | 5 | 88 | 11900 | 0 | 30 | 29 | GAO-20-405 NASA Assessments of Major Projects
Orion MPCV | 2020 | 5 | 86 | 11800 | 0 | 33 | 38 | GAO-20-405 NASA Assessments of Major Projects
Mars 2020 (Perseverance) | 2020 | 6 | 90 | 2700 | 0 | 10 | 2 | GAO-20-405 NASA Assessments of Major Projects
Europa Clipper | 2021 | 5 | 80 | 4250 | 1 | 16 | 14 | GAO-21-306 NASA Assessments of Major Projects
GRACE-FO | 2020 | 6 | 92 | 430 | 0 | 5 | 18 | GAO-20-405 NASA Assessments of Major Projects
ICESat-2 | 2020 | 5 | 89 | 1100 | 0 | 29 | 46 | GAO-20-405 NASA Assessments of Major Projects
SWOT | 2021 | 6 | 88 | 710 | 0 | 8 | 18 | GAO-21-306 NASA Assessments of Major Projects
NISAR | 2022 | 5 | 86 | 1500 | 1 | 12 | 12 | GAO-22-105212 NASA Assessments of Major Projects
Roman Space Telescope | 2023 | 5 | 82 | 4300 | 1 | 18 | 24 | GAO-23-106021 NASA Assessments of Major Projects
Psyche | 2023 | 6 | 90 | 1200 | 0 | 9 | 15 | GAO-23-106021 NASA Assessments of Major Projects
DART | 2022 | 7 | 93 | 330 | 0 | 2 | 3 | GAO-22-105212 NASA Assessments of Major Projects
Lucy | 2022 | 6 | 91 | 990 | 0 | 4 | 6 | GAO-22-105212 NASA Assessments of Major Projects
OSIRIS-REx | 2020 | 6 | 90 | 1160 | 0 | 5 | 7 | GAO-20-405 NASA Assessments of Major Projects
InSight | 2020 | 5 | 85 | 830 | 1 | 22 | 26 | GAO-20-405 NASA Assessments of Major Projects
TESS | 2020 | 7 | 92 | 290 | 0 | 3 | 3 | GAO-20-405 NASA Assessments of Major Projects
Parker Solar Probe | 2020 | 5 | 88 | 1490 | 1 | 12 | 15 | GAO-20-405 NASA Assessments of Major Projects
Landsat 9 | 2021 | 7 | 93 | 890 | 0 | 2 | 4 | GAO-21-306 NASA Assessments of Major Projects
JPSS-2 | 2022 | 7 | 92 | 500 | 0 | 3 | 5 | GAO-22-105212 NASA Assessments of Major Projects
Gateway PPE | 2023 | 5 | 76 | 1300 | 1 | 15 | 18 | GAO-23-106021 NASA Assessments of Major Projects
Gateway HALO | 2023 | 4 | 72 | 1100 | 1 | 20 | 22 | GAO-23-106021 NASA Assessments of Major Projects
Exploration Ground Systems | 2020 | 5 | 82 | 3900 | 0 | 40 | 40 | GAO-20-405 NASA Assessments of Major Projects
Commercial Crew (Boeing) | 2021 | 6 | 84 | 4400 | 0 | 29 | 72 | GAO-21-306 NASA Assessments of Major Projects
Commercial Crew (SpaceX) | 2021 | 6 | 88 | 3140 | 0 | 12 | 32 | GAO-21-306 NASA Assessments of Major Projects
SPHEREx | 2024 | 6 | 87 | 488 | 0 | 7 | 9 | GAO-24-106767 NASA Assessments of Major Projects
PACE | 2024 | 7 | 92 | 964 | 0 | 4 | 5 | GAO-24-106767 NASA Assessments of Major Projects
CLPS-VIPER | 2024 | 5 | 78 | 609 | 1 | 42 | 24 | GAO-24-106767 NASA Assessments of Major Projects
Dragonfly | 2024 | 5 | 82 | 3350 | 1 | 14 | 18 | GAO-24-106767 NASA Assessments of Major Projects
MSR SRL | 2025 | 4 | 68 | 5300 | 1 | 55 | 36 | GAO-25-107591 NASA Assessments of Major Projects
MSR ERO | 2025 | 4 | 70 | 4100 | 1 | 48 | 30 | GAO-25-107591 NASA Assessments of Major Projects
Artemis HLS | 2025 | 5 | 74 | 2900 | 1 | 18 | 12 | GAO-25-107591 NASA Assessments of Major Projects
xEMU spacesuit | 2025 | 5 | 76 | 1800 | 1 | 25 | 24 | GAO-25-107591 NASA Assessments of Major Projects
Geospace Dynamics Constellation | 2025 | 5 | 80 | 500 | 0 | 9 | 6 | GAO-25-107591 NASA Assessments of Major Projects
NEO Surveyor | 2025 | 6 | 85 | 1200 | 0 | 7 | 8 | GAO-25-107591 NASA Assessments of Major Projects
Plankton Aerosol Cloud Ocean Ecosystem | 2024 | 7 | 91 | 964 | 0 | 4 | 5 | GAO-24-106767 NASA Assessments of Major Projects

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Percent growth in development cost from KDP-C baseline to most recent assessment | NASA GAO Major Project Assessment annual report tables (GAO-20-405 through GAO-25-107591)
entry_TRL | Technology readiness level of the lowest-TRL critical technology at preliminary design review (PDR) | Critical technology TRL tables in NASA GAO Major Project Assessments
design_pct_at_PDR | Percent of engineering design drawings released at PDR (design maturity proxy) | Design maturity disclosures in NASA GAO Major Project Assessments
lifecycle_cost_musd | Most recent life-cycle cost estimate in millions of US dollars | NASA GAO Major Project Assessment life-cycle cost columns
critical_tech_below_TRL6 | Binary indicator equal to 1 if at least one critical technology was below TRL 6 at PDR | Derived from critical technology disclosures in NASA GAO Major Project Assessments

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 86.0845 | 47.5049 | 1.8121 | 0.07 | -7.0234 | 179.1925
entry_TRL | -8.8798 | 4.3986 | -2.0188 | 0.0435 | -17.5008 | -0.2588
design_pct_at_PDR | -0.2986 | 0.6717 | -0.4446 | 0.6566 | -1.6151 | 1.0179
lifecycle_cost_musd | 0.0026 | 0.0013 | 2.0689 | 0.0386 | 0.0001395 | 0.0052
critical_tech_below_TRL6 | 0.5996 | 7.6404 | 0.0785 | 0.9374 | -14.3753 | 15.5746

## Fit statistics
Statistic | Value
N | 35
R2 | 0.6369
R2_adj | 0.5885
F | 12.4757
F_p | 4.306e-06