## README
COLLEGIUM empirical evidence workbook
Does Model-Based Systems Engineering Shorten Schedule Slip? A Cox Proportional-Hazards Analysis of NASA Major Projects, 2012-2025
Candidate: Soren Eze (1B-DME-098)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H1: Programs that adopted MBSE at or before SRR experience a higher hazard of reaching launch (shorter time to launch conditional on still being in development), conditional on planned life-cycle duration and risk class. Specifically, the hazard ratio exp(beta_1) is greater than 1, equivalently beta_1 > 0. H0: beta_1 = 0.
Headline result: class_a = -0.0832 (p = 0.9005)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
program | duration_months | launched | mbse_adoption | life_cycle_years | class_a | cost_growth_pct | source
James Webb Space Telescope | 228 | 1 | 0 | 25 | 1 | 94 | GAO-22-105212 NASA Major Projects Assessment 2022
Mars Science Laboratory | 96 | 1 | 0 | 9 | 1 | 51.4 | GAO-12-207SP NASA Major Projects 2012
Mars 2020 Perseverance | 72 | 1 | 1 | 7 | 1 | 11.7 | GAO-21-306 NASA Major Projects 2021
OSIRIS-REx | 84 | 1 | 0 | 7 | 0 | 48.3 | GAO-19-262SP NASA Major Projects 2019
GRAIL | 40 | 1 | 0 | 3 | 0 | -2 | GAO-13-276SP NASA Major Projects 2013
MAVEN | 48 | 1 | 0 | 4 | 0 | 0 | GAO-14-338SP NASA Major Projects 2014
LADEE | 36 | 1 | 0 | 2 | 0 | 0 | GAO-14-338SP NASA Major Projects 2014
InSight | 84 | 1 | 0 | 7 | 0 | 23 | GAO-19-262SP NASA Major Projects 2019
SWOT | 102 | 1 | 1 | 8 | 0 | 53.4 | GAO-23-106021 NASA Major Projects 2023
ICESat-2 | 114 | 1 | 0 | 7 | 0 | 50 | GAO-19-262SP NASA Major Projects 2019
GOES-R | 132 | 1 | 0 | 12 | 1 | 51.9 | GAO-19-262SP NASA Major Projects 2019
Landsat 9 | 72 | 1 | 1 | 6 | 0 | 31.5 | GAO-22-105212 NASA Major Projects 2022
Europa Clipper | 108 | 1 | 1 | 11 | 1 | 22.4 | GAO-23-106021 NASA Major Projects 2023
Lucy | 72 | 1 | 1 | 12 | 0 | 0.8 | GAO-22-105212 NASA Major Projects 2022
Psyche | 84 | 1 | 1 | 8 | 0 | 39.5 | GAO-23-106021 NASA Major Projects 2023
NISAR | 108 | 1 | 1 | 8 | 0 | 36.4 | GAO-24-106767 NASA Major Projects 2024
SLS Block 1 | 144 | 1 | 1 | 12 | 1 | 44.4 | GAO-21-306 NASA Major Projects 2021
Orion MPCV | 168 | 1 | 1 | 15 | 1 | 35.3 | GAO-21-306 NASA Major Projects 2021
DART | 60 | 1 | 1 | 5 | 0 | 7.1 | GAO-22-105212 NASA Major Projects 2022
TESS | 72 | 1 | 0 | 5 | 0 | 43.5 | GAO-19-262SP NASA Major Projects 2019
Parker Solar Probe | 84 | 1 | 1 | 8 | 0 | 0 | GAO-19-262SP NASA Major Projects 2019
Roman Space Telescope | 96 | 0 | 1 | 10 | 1 | 34.4 | GAO-24-106767 NASA Major Projects 2024
JPSS-1 | 72 | 1 | 0 | 7 | 0 | 1.1 | GAO-19-262SP NASA Major Projects 2019
JPSS-2 | 84 | 1 | 1 | 7 | 0 | 0 | GAO-23-106021 NASA Major Projects 2023
PACE | 72 | 1 | 1 | 6 | 0 | 19.8 | GAO-23-106021 NASA Major Projects 2023
DAVINCI | 84 | 0 | 1 | 9 | 0 | 30 | GAO-24-106767 NASA Major Projects 2024
VERITAS | 96 | 0 | 1 | 10 | 0 | 9.1 | GAO-24-106767 NASA Major Projects 2024
SPHEREx | 60 | 1 | 1 | 4 | 0 | 101.7 | GAO-23-106021 NASA Major Projects 2023
Dragonfly | 120 | 0 | 1 | 15 | 0 | 294.1 | GAO-25-107591 NASA Major Projects 2025
HLS Starship | 72 | 0 | 1 | 5 | 1 | 0 | GAO-24-106767 NASA Major Projects 2024 [illustrative duration]

## Construction
Variable | Definition | Construction / source
duration_months | Elapsed development time in months from authority to proceed to launch (event=1) or to most recent GAO assessment date (censored, event=0) | GAO NASA Major Projects Assessment series 2012-2025
launched | Event indicator equal to 1 if program reached launch by the most recent assessment, 0 if still in development (right-censored) | GAO NASA Major Projects Assessment series 2012-2025; NASA launch manifest
mbse_adoption | Indicator equal to 1 if program adopted Model-Based Systems Engineering or Digital Mission Engineering tooling at or before System Requirements Review, 0 otherwise | Coded from NASA project plans and prime contractor technical-paper record, cross-checked against AMOS and Acta Astronautica corpora
life_cycle_years | Planned life-cycle duration from authority to proceed to end of prime mission, in years | GAO Major Projects Assessment; NASA mission planning documents
class_a | Indicator equal to 1 if program is NASA Class A (highest priority, lowest risk tolerance), 0 otherwise | NPR 8705.4 risk classification; GAO program descriptions

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
mbse_adoption | 0.1129 | 0.4726 | 0.2388 | 0.8113 | -0.8134 | 1.0391 | 1.1195
life_cycle_years | -0.6593 | 0.1703 | -3.8717 | 0.0001081 | -0.993 | -0.3255 | 0.5172
class_a | -0.0832 | 0.6654 | -0.1251 | 0.9005 | -1.3873 | 1.2209 | 0.9201

## Fit statistics
Statistic | Value
N | 30
events | 25