## README
COLLEGIUM empirical evidence workbook
Cost-Growth Hazard in JPL Deep-Space Missions: A Cox Survival-Analysis of Confirmation-to-Launch Budget Escalation
Candidate: Gabriel Novak (1B-OPS-027)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H1: The instantaneous hazard that a deep-space mission crosses a fixed 15 percent confirmation-to-launch cost-growth threshold rises with the share of formulation-phase technological immaturity carried into implementation; the Cox coefficient on carry_immaturity is strictly positive and its hazard ratio exceeds one. H0: the coefficient is zero and the hazard ratio equals one.
Headline result: baseline_dev_cost_musd = -0.0003426 (p = 0.3228)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | kdpc_year | launch_year | dev_months | baseline_dev_cost_musd | final_dev_cost_musd | pct_growth | event_growth15 | carry_immaturity | new_tech | source
Mars Science Laboratory (Curiosity) | 2008 | 2011 | 40 | 969 | 1800 | 86 | 1 | 0.78 | 1 | NASA OIG IG-12-021 (2012-09-27): dev cost 969M->1.8B, 86pct overrun; GAO-12-207SP technology-maturity narrative (sample-analysis instruments below TRL6 at confirmation); Planetary Society Cost of MSL Curiosity
InSight | 2014 | 2018 | 54 | 675 | 830 | 23 | 1 | 0.55 | 1 | SpaceNews 2016 InSight delay adds 150M (675M->830M); NASA OIG/GAO-15-320SP (SEIS seismometer immaturity at confirmation); Planetary Society InSight cost
Psyche | 2019 | 2023 | 48 | 985 | 1110 | 12.7 | 0 | 0.4 | 1 | Planetary Society What happened with Psyche (KDP-C 2019, software 1yr slip, dev growth); GAO-24-106767; IEPC-2017-153 Psyche overview (adapted commercial SEP/power, mixed heritage TRL) basis for carry_immaturity
Lucy | 2017 | 2021 | 49 | 981 | 981 | 0 | 0 | 0.22 | 0 | Parabolic Arc 2020 (GAO): Lucy 981.1M on cost/schedule; GAO-19-262SP (only Lucy matured technologies to TRL6; solar array not a critical technology) basis for low carry_immaturity; Planetary Society Cost of Lucy
OSIRIS-REx | 2013 | 2016 | 38 | 800 | 800 | 0 | 0 | 0.3 | 0 | Spaceflight Now 2016 OSIRIS-REx under budget (>30M reserve at launch); Planetary Society Cost of OSIRIS-REx (dev 558.5M); GAO-16-309SP
Juno | 2008 | 2011 | 39 | 700 | 1100 | 57 | 1 | 0.5 | 1 | Wikipedia Juno (cites NASA): 700M FY03 baseline -> ~1.1B; JPL Juno Launch Press Kit 2011; GAO-09-306SP solar/instrument maturity; Planetary Society Juno spending
GRAIL | 2009 | 2011 | 30 | 496 | 496 | 0 | 0 | 0.18 | 0 | GRAIL project management IEEE 6496871 (launched on cost/schedule/spec, under budget); NASA budgeted 496M; Wikipedia GRAIL
MAVEN | 2010 | 2013 | 42 | 671 | 671 | 0 | 0 | 0.25 | 0 | Spaceflight Now 2013 MAVEN under 671M budget; Planetary Society MAVEN cost; GAO-13-276SP
SMAP | 2012 | 2015 | 36 | 916 | 916 | 0 | 0 | 0.28 | 0 | Wikipedia SMAP (cites NASA): 916M invested, launched 2015 within baseline; GAO-15-320SP NASA assessments
Mars 2020 (Perseverance) | 2016 | 2020 | 49 | 2440 | 2725 | 11.7 | 0 | 0.35 | 1 | NASA OIG IG-17-009 Mars 2020 (2016 KDP-C, dev cost and growth); GAO-21-306; Planetary Society Perseverance cost
Europa Clipper | 2019 | 2024 | 60 | 4250 | 5000 | 17.6 | 1 | 0.45 | 1 | SpacePolicyOnline 2024 Europa Clipper cost growth (4.25B->5B, 17.6pct); GAO-25-107591 technology-maturity narrative; Wikipedia Europa Clipper
GRACE-FO | 2013 | 2018 | 60 | 430 | 521 | 21.2 | 1 | 0.3 | 1 | GAO NASA assessments GRACE-FO development growth (430M->521M); JPL GRACE-FO Laser Ranging Interferometer documented new-technology demonstrator (first dual-spacecraft laser interferometer) basis for carry_immaturity
Dawn | 2004 | 2007 | 36 | 373 | 446 | 19.6 | 1 | 0.48 | 1 | Planetary Society Dawn cost (dev growth 373M->446M, 2006 near-cancellation); GAO-09-306SP (ion-propulsion immaturity); Wikipedia Dawn
Deep Impact | 2001 | 2005 | 42 | 267 | 330 | 23.6 | 1 | 0.42 | 1 | Wikipedia Deep Impact (cites NASA): cost growth 267M->330M; NASA Discovery (first cometary impactor + autonomous impactor navigation, novel) basis for carry_immaturity
Stardust | 1996 | 1999 | 38 | 168 | 168 | 0 | 0 | 0.2 | 0 | NASA Stardust press kit (Discovery, on budget 168M); Wikipedia Stardust
Genesis | 1997 | 2001 | 44 | 216 | 264 | 22.2 | 1 | 0.38 | 1 | Wikipedia Genesis (cites NASA): development growth 216M->264M; NASA Discovery (novel solar-wind collector/sample-return capsule) basis for carry_immaturity; carry_immaturity [illustrative] exact TRL count
Spitzer Space Telescope | 1998 | 2003 | 60 | 670 | 800 | 19.4 | 1 | 0.52 | 1 | Wikipedia Spitzer/SIRTF cost growth 670M->800M; NASA Great Observatories; GAO large-scale projects (cryogenic-instrument immaturity)
NuSTAR | 2009 | 2012 | 33 | 140 | 165 | 17.9 | 1 | 0.33 | 1 | Wikipedia NuSTAR (SMEX) cost growth 140M->165M, 2010 funding hold; Caltech NuSTAR (first hard X-ray focusing optics in space, novel multilayer mirrors/CdZnTe detectors) basis for carry_immaturity
GALEX | 2001 | 2003 | 28 | 103 | 103 | 0 | 0 | 0.2 | 0 | NASA GALEX (SMEX, on budget 103M); Caltech/JPL GALEX
WISE | 2006 | 2009 | 40 | 320 | 320 | 0 | 0 | 0.27 | 0 | Wikipedia WISE (cites NASA): launched within budget 320M; JPL WISE
Phoenix | 2003 | 2007 | 46 | 386 | 420 | 8.8 | 0 | 0.32 | 1 | Wikipedia Phoenix (Mars Scout) cost 386M->420M; NASA Phoenix (recovered Mars Surveyor 2001 lander heritage hardware, moderate maturity) basis for carry_immaturity
GRAIL-class Discovery (Kepler) | 2007 | 2009 | 33 | 488 | 591 | 21.1 | 1 | 0.4 | 1 | Planetary Society Kepler cost (dev growth to ~591M); NASA Discovery Kepler; GAO-09-306SP (photometer immaturity)
MRO (Mars Reconnaissance Orbiter) | 2002 | 2005 | 38 | 580 | 720 | 24.1 | 1 | 0.36 | 1 | Wikipedia MRO (cites NASA): development cost growth 580M->720M; JPL MRO; GAO-05/06 large-scale projects
Aquarius/SAC-D | 2004 | 2011 | 84 | 287 | 287 | 0 | 0 | 0.24 | 0 | NASA Aquarius (JPL, ESSP) launched within budget 287M; Wikipedia Aquarius

## Construction
Variable | Definition | Construction / source
dev_months | Development duration in months from Key Decision Point C (confirmation) to launch, or to right-censoring at launch for missions that never crossed the threshold | Computed from documented KDP-C confirmation dates and launch dates (NASA mission records, GAO NASA Assessments of Major Projects, Planetary Society mission cost pages)
event_growth15 | Event indicator: 1 if the mission's development cost exceeded its confirmation (KDP-C) baseline by 15 percent or more at or before launch; 0 if right-censored at launch without crossing the threshold | Derived from documented confirmation baseline development cost vs final/current development cost (NASA OIG audits, GAO assessments, Planetary Society cost charts)
carry_immaturity | Share of formulation-phase technological immaturity carried into implementation, scaled 0 to 1, operationalized from the count of confirmation-phase instruments and critical subsystems assessed below TRL 6 relative to the mission's technology set | Confirmation-review technology-readiness profiles and GAO technology-maturity assessments; values without an individually published TRL count are marked illustrative in the source column
baseline_dev_cost_musd | Confirmation (KDP-C) baseline development cost in millions of nominal US dollars; scale control | NASA OIG audits, GAO NASA Assessments of Major Projects, Planetary Society mission cost pages, mission press kits

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
carry_immaturity | 4.2289 | 1.9154 | 2.2078 | 0.0273 | 0.4747 | 7.9831 | 68.6435
baseline_dev_cost_musd | -0.0003426 | 0.0003465 | -0.9887 | 0.3228 | -0.001 | 0.0003365 | 0.9997

## Fit statistics
Statistic | Value
N | 24
events | 12