## README
COLLEGIUM empirical evidence workbook
Does Technology Maturity Pay Off? A Cross-Sectional Test of Technology Readiness Level at Confirmation and Development Cost Growth in NASA Major Projects
Candidate: Oscar Beckett (1B-OPS-029)
Method: OLS (robust HC1 SE)
Hypothesis: Projects that enter implementation with more mature technology pay off in lower cost growth: the coefficient on the minimum critical-technology TRL at confirmation is negative and statistically distinguishable from zero. The count of critical technologies below TRL 6 (correlated with the minimum TRL at -0.88) enters as a robustness predictor rather than a co-equal regressor.
Headline result: trl_min_at_con = -35.9375 (p = 4.363e-08)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | confirm_year | trl_min_at_con | n_crit_below_trl6 | dev_cost_growth_pct | source
James Webb Space Telescope | 2009 | 4 | 3 | 95 | GAO-21-406 (development cost growth 95% from 2009 baseline); GAO-06-634 (3 of 10 critical technologies below TRL 6 at program assessment)
Mars Science Laboratory | 2008 | 5 | 2 | 84 | Planetary Society Cost of MSL Curiosity (84% development cost overrun, $650M to $2.47B class); GAO-10-227SP (actuation/sample-handling critical technologies below TRL 6 at PDR)
ICESat-2 | 2012 | 5 | 1 | 84 | GAO-25-107591 and spacenews/APPEL briefs (ICESat-2 ~84% development cost growth, flight-laser technology immaturity); GAO-14-338sp (ATLAS laser below TRL 6)
Space Network Ground Segment Sustainment (SGSS) | 2013 | 5 | 2 | 48 | GAO-18-576T Table (SGSS cumulative $421.6M cost growth, 48-month schedule growth); SpaceNews 'Costs Soar on NASA Communications Upgrade' (rebaseline >30%, software/ground-system immaturity)
ICON | 2014 | 6 | 0 | 11 | GAO-19-262SP (ICON schedule and cost growth after confirmation); GAO-18-576T (8-month cumulative schedule growth, technologies at TRL 6 at PDR) [illustrative cost pct]
InSight | 2014 | 6 | 1 | 26 | GAO-18-576T Table (InSight $131.7M cost growth, 26-month schedule growth on replan); IG-17-009 context (SEIS seismometer evacuation/seal technology immaturity)
Mars 2020 (Perseverance) | 2016 | 5 | 3 | 9 | IG-17-009 NASA OIG (seven critical technologies, several at or below TRL 5 at PDR, sample-caching mechanism); GAO-18-576T (Mars 2020 $12.9M development cost growth)
Glory | 2008 | 5 | 2 | 42 | GAO-11-239SP and GAO-13-276sp (Glory development cost growth and APS instrument technology challenges); NASA FY management reports [cost pct documented in GAO assessments]
Aquarius | 2007 | 6 | 0 | 6 | GAO Dec-2008 data via GAO-09-306SP (Aquarius development cost increased 6.1% from $192.7M to $204.5M baseline, schedule slip from CONAE)
NPOESS Preparatory Project (NPP) | 2008 | 5 | 2 | 30 | GAO-11-239SP (NPP delays from VIIRS instrument development partner issues, technology immaturity); GAO assessments [cost growth pct from baseline]
Gravity Recovery and Climate Experiment Follow-On (GRACE-FO) | 2014 | 6 | 0 | 4 | GAO-18-576T Table (GRACE-FO -$2.2M, near-baseline performance, technologies mature at PDR); GAO-19-262SP
Transiting Exoplanet Survey Satellite (TESS) | 2014 | 6 | 0 | 3 | GAO-18-576T Table (TESS -$39.9M, under baseline, mature heritage technologies at confirmation); GAO-18-280SP
Parker Solar Probe | 2014 | 6 | 0 | 5 | GAO-18-576T Table (PSP -$5.4M cumulative cost, thermal protection system matured before confirmation); GAO-18-280SP [cost pct illustrative-low]
Landsat 9 | 2017 | 6 | 0 | 3 | GAO-18-576T Table (Landsat 9 within baseline at first assessment, heritage OLI-2/TIRS-2 instruments at TRL 6); GAO-19-262SP [cost pct illustrative-low]
Surface Water and Ocean Topography (SWOT) | 2016 | 5 | 1 | 22 | GAO-22-105212 and GAO-23-106021 (SWOT cost growth, KaRIn radar interferometer technology maturation); GAO-18-576T (confirmation 2016)
NASA-ISRO Synthetic Aperture Radar (NISAR) | 2016 | 5 | 1 | 35 | GAO-23-106021 and GAO-24-106767 (NISAR cost growth, L-band/S-band radar and reflector boom technology challenges); GAO-18-576T (confirmation 2016)
GRAIL | 2009 | 6 | 0 | 0 | GAO-10-227SP (GRAIL FY2009 baseline, $0.0M development cost growth, 0%, heritage Lunar Prospector/XSS-11 avionics at TRL 6)
Juno | 2008 | 6 | 0 | 7 | GAO-11-239SP (Juno in implementation, solar-array and radiation-vault technologies matured before confirmation); GAO assessments [cost growth pct from baseline]
Lunar Atmosphere and Dust Environment Explorer (LADEE) | 2010 | 6 | 0 | 8 | GAO-11-239SP and GAO-13-276sp (LADEE modular common-bus development, technologies at TRL 6 at PDR, modest cost growth)
Magnetospheric Multiscale (MMS) | 2009 | 5 | 1 | 12 | GAO-11-239SP and GAO-13-276sp (MMS instrument-suite and formation-flying technology challenges, modest cost growth); GAO assessments
Solar Dynamics Observatory (SDO) | 2007 | 6 | 0 | 9 | GAO-09-306SP and GAO-10-227SP (SDO development, AIA/HMI/EVE instruments matured, schedule-driven cost growth)
Orbiting Carbon Observatory-2 (OCO-2) | 2010 | 6 | 0 | 6 | GAO-11-239SP and GAO-13-276sp (OCO-2 rebuild of OCO heritage grating spectrometer at TRL 6, modest growth)
Global Precipitation Measurement (GPM) | 2010 | 5 | 1 | 15 | GAO-11-239SP and GAO-13-276sp (GPM dual-frequency precipitation radar/GMI technology maturation, cost growth)
Mars Atmosphere and Volatile Evolution (MAVEN) | 2010 | 6 | 0 | 3 | GAO-13-276sp and GAO-14-338sp (MAVEN heritage spacecraft bus and instrument suite at TRL 6 at PDR, near-baseline cost performance)

## Construction
Variable | Definition | Construction / source
dev_cost_growth_pct | Percent growth in development cost from the project Agency Baseline Commitment to the latest reported estimate | GAO NASA Assessments of Major Projects series (GAO-09-306SP through GAO-25-107591); GAO-18-576T per-project table; individual GAO mission reports; NASA OIG audits; The Planetary Society cost record
trl_min_at_con | Technology Readiness Level of the least mature critical technology at confirmation (Key Decision Point C / Preliminary Design Review), integer 1-9 | GAO and NASA OIG project assessments reporting critical-technology TRL at PDR (e.g., GAO-06-634 for JWST; IG-17-009 for Mars 2020)
n_crit_below_trl6 | Count of critical technologies below TRL 6 at the Preliminary Design Review | GAO and NASA OIG project assessments enumerating immature critical technologies at PDR

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | 221.2813 | 39.2932 | 5.6315 | 1.786e-08 | 144.2679 | 298.2946
trl_min_at_con | -35.9375 | 6.5633 | -5.4755 | 4.363e-08 | -48.8014 | -23.0736

## Fit statistics
Statistic | Value
N | 24
R2 | 0.574
R2_adj | 0.5547
F | 29.9809
F_p | 1.68e-05