## README
COLLEGIUM empirical evidence workbook
Cost, Complexity, and the Hazard of Schedule Slip: A Proportional-Hazards Model of NASA Planetary and Major Science Missions
Candidate: Lorenzo Aziz (1B-PLA-038)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H0: cost and instrument complexity have no association with the hazard of schedule slip (beta_1 = beta_2 = 0). H1: higher cost and a larger instrument complement raise the hazard of schedule slip (beta_1 > 0, beta_2 > 0).
Headline result: instruments = -0.0308 (p = 0.8402)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | confirm_year | launch_year | dev_months | cost_musd | ln_cost | instruments | slip | source
Psyche | 2017 | 2023 | 81 | 1200 | 7.0901 | 4 | 1 | NASA/JPL Psyche press kit and Wikipedia: selected Jan 2017, planned launch 2022 slipped to launched 13 Oct 2023; ~US$1.2B; 4 instruments (gao-25-107591 tracks Psyche)
Europa Clipper | 2015 | 2024 | 112 | 5000 | 8.5172 | 9 | 0 | Wikipedia Europa Clipper / NASA Science: KDP-C ~2015, launched 14 Oct 2024 within baselined Oct 2024 window (weather shifts only); ~US$5.0B; 9 instruments
Mars 2020 Perseverance | 2016 | 2020 | 48 | 2750 | 7.9194 | 7 | 0 | Wikipedia Perseverance: planned and launched July 2020; ~US$2.75B; 7 primary instruments
OSIRIS-REx | 2011 | 2016 | 64 | 800 | 6.6846 | 6 | 0 | Wikipedia OSIRIS-REx: selected May 2011, planned 2016 and launched 8 Sep 2016; ~US$800M dev; 6 instruments
InSight | 2012 | 2018 | 69 | 830 | 6.7214 | 4 | 1 | Wikipedia InSight: selected Aug 2012, planned Mar 2016 slipped to launched 5 May 2018 (SEIS leak); US$830M; 4 instruments
Lucy | 2017 | 2021 | 57 | 981 | 6.8885 | 3 | 0 | Wikipedia Lucy: selected Jan 2017, planned and launched Oct 2021; US$981M; 3 instruments
MSL Curiosity | 2006 | 2011 | 63 | 2470 | 7.812 | 10 | 1 | Wikipedia Mars Science Laboratory: planned 2009 slipped to launched 26 Nov 2011; US$2.47B dev; ~10 science instruments
MAVEN | 2010 | 2013 | 37 | 582.5 | 6.3673 | 8 | 0 | Wikipedia MAVEN: selected 2010, launched on schedule 18 Nov 2013; US$582.5M; 8 instrument suites
Juno | 2005 | 2011 | 74 | 1100 | 7.0031 | 9 | 0 | Wikipedia Juno: selected 1 Jun 2005, planned and launched Aug 2011; ~US$1.1B development; 9 instruments
New Horizons | 2001 | 2006 | 50 | 700 | 6.5511 | 7 | 0 | Wikipedia New Horizons: selected Nov 2001, planned and launched 19 Jan 2006; ~US$700M; 7 instruments
DART | 2017 | 2021 | 53 | 330 | 5.7991 | 2 | 0 | Wikipedia DART: Phase C Jun 2017, launched 24 Nov 2021 on Nov-2021 plan; US$330M; 2 imaging instruments (DRACO+LICIACube)
JWST | 2008 | 2021 | 161 | 9700 | 9.1799 | 4 | 1 | Wikipedia JWST: confirmed for construction 2008, planned 2007/2018 slipped to launched 25 Dec 2021; ~US$9.7B; 4 instruments
Parker Solar Probe | 2014 | 2018 | 53 | 1500 | 7.3132 | 4 | 0 | Wikipedia Parker Solar Probe: confirmation ~2014, launched 12 Aug 2018 on 2018 plan; US$1.5B; 4 instruments
Mars Reconnaissance Orbiter | 2001 | 2005 | 46 | 716.6 | 6.5746 | 6 | 0 | Wikipedia MRO: Lockheed selected Oct 2001, launched 12 Aug 2005 on 2005 plan; US$716.6M; 6 instruments
GRAIL | 2007 | 2011 | 45 | 496 | 6.2066 | 3 | 0 | Wikipedia GRAIL: selected Dec 2007 Discovery, launched 10 Sep 2011 on Sep-2011 plan; US$496M; 3 instruments
Dawn | 2004 | 2007 | 42 | 446 | 6.1003 | 3 | 1 | Wikipedia Dawn: selected 2001 planned 2006, reinstated 2004, slipped to launched 27 Sep 2007; US$446M final; 3 instruments
Cassini | 1990 | 1997 | 93 | 2600 | 7.8633 | 12 | 0 | Wikipedia Cassini-Huygens: US development ~1990, launched 15 Oct 1997 on Oct-1997 plan; US$2.6B US share; 12 orbiter instruments
Mars Phoenix | 2005 | 2007 | 26 | 420 | 6.0403 | 6 | 0 | Wikipedia Phoenix: CDR/confirm Jun 2005, launched 4 Aug 2007 on 2007 plan; ~US$420M; 6 instruments
Galileo | 1983 | 1989 | 81 | 1390 | 7.2371 | 11 | 1 | Wikipedia Galileo: Phase C early 1980s, planned May 1986 slipped (Challenger) to launched 18 Oct 1989; ~US$1.39B [illustrative cost]; 11 orbiter instruments
Spitzer | 1998 | 2003 | 67 | 776 | 6.6542 | 3 | 0 | Wikipedia Spitzer (SIRTF): restructured/confirmed ~1998, launched 25 Aug 2003 on revised baseline; US$776M; 3 instruments
SWOT | 2016 | 2022 | 78 | 1200 | 7.0901 | 6 | 1 | Wikipedia SWOT / space.com: Phase C ~2016, contracted Apr 2021 launch slipped to launched 16 Dec 2022; ~US$1.2B [illustrative cost]; 6 instruments
GRACE-FO | 2013 | 2018 | 64 | 430 | 6.0638 | 5 | 0 | Wikipedia GRACE-FO: confirmation ~2013, launched 22 May 2018; ~US$430M NASA [illustrative cost]; 5 measurement systems

## Construction
Variable | Definition | Construction / source
dev_months | Development schedule length in months, from mission confirmation/selection to actual launch | Computed from confirmation/selection year and actual launch month/year documented per mission (NASA/JPL press kits; Wikipedia mission pages, sourced)
slip | Event indicator: 1 if the mission's launch slipped beyond its originally baselined launch date or window; 0 if launched on the baseline (right-censored) | Coded from documented planned-versus-actual launch records per mission
ln_cost | Natural log of development/lifecycle cost in millions of current USD | Per-mission cost figures from NASA/JPL press kits and mission documentation; three approximate figures marked [illustrative]
instruments | Count of primary science instruments in the payload complement | Instrument complements documented per mission (mission press kits and Wikipedia mission pages)
cost_musd | Development/lifecycle cost in millions of current USD | Source column of data.csv cites each figure

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
ln_cost | -1.4964 | 0.9935 | -1.5062 | 0.132 | -3.4435 | 0.4508 | 0.2239
instruments | -0.0308 | 0.1529 | -0.2016 | 0.8402 | -0.3305 | 0.2689 | 0.9696

## Fit statistics
Statistic | Value
N | 22
events | 7