## README
COLLEGIUM empirical evidence workbook
When Does the Overrun Begin? A Cox Proportional-Hazards Model of Cost-and-Schedule Baseline Breach in NASA Planetary Missions
Candidate: Aaron Iverson (1B-PLA-039)
Method: Cox proportional-hazards (PHReg)
Hypothesis: H1: development complexity and novelty raise the instantaneous hazard of baseline breach. Specifically, greater spacecraft mass and a larger instrument complement increase the breach hazard (HR > 1), while substantial design heritage lowers it (HR < 1). H0 is that none of these covariates shifts the breach hazard (all HR = 1), consistent with a memoryless, complexity-invariant overrun process.
Headline result: heritage = -0.4952 (p = 0.4554)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
mission | confirm_year | dur_months | breach | cost_growth_pct | mass_t | n_instr | heritage | source
Mars Science Laboratory (Curiosity) | 2008 | 38 | 1 | 84 | 3.893 | 10 | 0 | Planetary Society, Cost of MSL Curiosity (planetary.org/space-policy/cost-of-msl-curiosity); GAO MSL cost overrun reporting; baseline $1.1B (2008) to $2.53B, 26-month delay
InSight | 2012 | 72 | 1 | 36.2 | 0.694 | 3 | 1 | Planetary Society, Cost of Mars InSight (planetary.org/space-policy/cost-of-mars-insight); SpaceNews, InSight delay adds $150M (spacenews.com/insight-delay-adds-150-million); $675M baseline +$153.8M, 26-month delay; Phoenix bus heritage
Mars 2020 (Perseverance) | 2016 | 52 | 1 | 15 | 1.025 | 7 | 1 | Science/AAAS, Cost of Mars 2020 may rise up to 15% (science.org/content/article/cost-mars-2020-mission-may-rise-15); MSL heritage bus; $2.46B development
OSIRIS-REx | 2013 | 40 | 0 | 0 | 2.11 | 5 | 1 | Planetary Society, Cost of OSIRIS-REx (planetary.org/space-policy/cost-of-osiris-rex); $588.5M spacecraft dev within cap; eoPortal OSIRIS-REx (5 instruments, 2110 kg wet)
Psyche | 2017 | 72 | 1 | 30.5 | 2.747 | 4 | 0 | GAO-22-105212 portfolio data (gao.gov/assets/gao-22-105212.pdf); JPL Psyche Quick Facts (jpl.nasa.gov/press-kits/psyche/quick-facts); $159M cumulative overrun, 15-month delay; 2747 kg, DSOC tech demo
Lucy | 2017 | 48 | 1 | 1.3 | 1.55 | 3 | 1 | GAO 2021/2022 assessments (gao.gov/assets/gao-22-105212.pdf); Wikipedia Lucy spacecraft (1550 kg wet, 3 instruments); higher-than-expected cost reported
DART | 2017 | 53 | 0 | 0 | 0.61 | 1 | 0 | Planetary Society, Cost of DART (planetary.org/space-policy/cost-of-dart); $324.5M dev within baseline; DART Wikipedia (DRACO instrument, ~610 kg); APL new bus
Europa Clipper | 2015 | 112 | 1 | 17.6 | 6.065 | 9 | 0 | SpacePolicyOnline, NASA Reveals Europa Clipper Cost Growth (spacepolicyonline.com/news/nasa-reveals-europa-clipper-cost-growth-mars-sample-return-replan); $4.25B to $5B (+$750M); Wikipedia Europa Clipper (9 instruments)
Dragonfly | 2024 | 48 | 1 | 100 | 0.45 | 5 | 0 | SpaceNews, NASA confirms Dragonfly despite doubled costs (spacenews.com/nasa-confirms-dragonfly-mission-despite-doubled-costs); NASA OIG Dragonfly cost increases (oig.nasa.gov); $850M Phase A-D cap, lifecycle doubled to $3.35B
NEO Surveyor | 2023 | 48 | 1 | 12 | 1.3 | 1 | 0 | GAO-25-107591 (gao.gov/assets/gao-25-107591.pdf); NASA Science NEO Surveyor (science.nasa.gov/mission/neo-surveyor); replanned launch and budget growth; single IR instrument [illustrative mass]
Juno | 2008 | 60 | 0 | 0 | 3.625 | 9 | 0 | GAO-14-338SP NASA assessments (gao.gov/assets/gao-14-338sp.pdf); NSSDCA Juno (3625 kg wet, 9 instruments); launched 2011 on baseline
GRAIL | 2008 | 33 | 0 | 0 | 0.307 | 1 | 1 | GAO NASA assessments 2011-2012; NSSDCA GRAIL (two 307 kg orbiters, MoonKAM/LGRS); XSS-11/Lunar Prospector lineage; on baseline
MAVEN | 2010 | 45 | 0 | 0 | 2.454 | 8 | 1 | GAO-14-338SP (gao.gov/assets/gao-14-338sp.pdf); NSSDCA MAVEN (2454 kg wet, 8 instruments); Mars Odyssey/MRO bus heritage; on baseline
LADEE | 2010 | 30 | 0 | 0 | 0.383 | 4 | 0 | GAO NASA assessments 2012-2013; NSSDCA LADEE (383 kg, Modular Common Spacecraft Bus, 4 instruments); on baseline
Mars Reconnaissance Orbiter | 2003 | 30 | 0 | 0 | 2.18 | 6 | 1 | NASA MRO press kit (mars.nasa.gov); NSSDCA MRO (2180 kg wet, 6 instruments); Lockheed Mars orbiter heritage; on baseline at 2005 launch
Phoenix | 2003 | 54 | 1 | 10 | 0.67 | 7 | 1 | Planetary Society Phoenix cost reporting; NSSDCA Phoenix (670 kg, Mars Surveyor 2001 lander heritage); modest development growth
Dawn | 2004 | 82 | 1 | 29 | 1.218 | 3 | 0 | GAO-08-301SP NASA major projects (gao.gov); Planetary Society Dawn cost; $373M baseline grew ~$70M; ion-propulsion new bus; 1218 kg
New Horizons | 2003 | 33 | 0 | 0 | 0.478 | 7 | 0 | NASA New Horizons press kit (pluto.jhuapl.edu); NSSDCA New Horizons (478 kg, 7 instruments); APL bus; launched on baseline 2006
MESSENGER | 2002 | 40 | 1 | 15 | 1.108 | 7 | 0 | GAO NASA assessments; NSSDCA MESSENGER (1108 kg wet, 7 instruments); APL new Mercury bus; development growth and slip
Mars Odyssey | 1999 | 24 | 0 | 0 | 0.725 | 3 | 1 | NASA Mars Odyssey press kit (mars.nasa.gov); NSSDCA Odyssey (725 kg, 3 instruments); Mars Climate Orbiter bus lineage; on baseline 2001
Stardust | 1997 | 40 | 0 | 0 | 0.385 | 2 | 1 | NASA Discovery program records; NSSDCA Stardust (385 kg, SRC + dust analyzer); SpaceProbe bus heritage; on baseline 1999
Deep Impact | 2001 | 40 | 1 | 18 | 0.973 | 3 | 0 | GAO Discovery cost reporting; NSSDCA Deep Impact (973 kg, flyby + impactor, 3 instruments); development growth; Ball new bus
GRACE-FO | 2012 | 48 | 0 | 0 | 0.6 | 2 | 1 | GAO-19-262SP (gao.gov/assets/gao-19-262sp.pdf); NSSDCA GRACE-FO (two 600 kg satellites); GRACE heritage; on baseline
Mars Sample Return (SRL/ERO baseline) | 2022 | 60 | 1 | 50 | 4 | 3 | 0 | GAO-25-107591 (gao.gov/assets/gao-25-107591.pdf); NASA MSR independent review board; significant cost growth and replan; mass and instruments [illustrative]
VERITAS | 2021 | 60 | 1 | 40 | 1.4 | 3 | 1 | GAO assessments and SpaceNews VERITAS delay reporting; mission paused for institutional reasons causing baseline disruption; Magellan/parametric heritage; mass/instruments [illustrative]

## Construction
Variable | Definition | Construction / source
dur_months | Months of development exposure from confirmation (authority-to-proceed) to launch; the survival time over which a mission is at risk of first baseline breach | NASA project lifecycle records; mission press kits; NSSDCA spacecraft pages
breach | Event indicator: 1 if the mission breached its confirmed cost or schedule baseline before launch (recorded overrun or rebaseline), 0 if it reached launch on baseline (right-censored) | GAO Assessments of Major Projects (GAO-25-107591, GAO-24-106767, GAO-23-106021); Planetary Society mission cost pages
cost_growth_pct | Cumulative development cost growth from the confirmation baseline, percent (descriptive; not a model covariate) | GAO assessments; Planetary Society cost-of-mission analyses; SpaceNews and SpacePolicyOnline reporting
mass_t | Spacecraft launch (wet) mass in metric tons; the leading parametric cost-driver in NASA cost-estimation practice | NSSDCA spacecraft master catalog; JPL/APL press kits; eoPortal
n_instr | Number of science instruments carried; a proxy for payload complexity and integration scope | Mission press kits; NSSDCA; eoPortal instrument lists
heritage | Bus/spacecraft heritage indicator: 1 if the design substantially reused a flown bus or lineage, 0 if largely new development | Manufacturer lineage records (Lockheed Martin, APL, Ball); mission documentation

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
mass_t | -0.5229 | 0.2869 | -1.8229 | 0.0683 | -1.0851 | 0.0393 | 0.5928
n_instr | 0.1674 | 0.1503 | 1.1138 | 0.2653 | -0.1271 | 0.4619 | 1.1822
heritage | -0.4952 | 0.6635 | -0.7464 | 0.4554 | -1.7957 | 0.8052 | 0.6094

## Fit statistics
Statistic | Value
N | 25
events | 14