## README
COLLEGIUM empirical evidence workbook
The Hazard of Sequencing: A Cox Survival Analysis of Development-to-Launch Duration Across NASA Planetary Campaign Elements
Candidate: Stefan Lindqvist (1B-MAR-041)
Method: Cox proportional-hazards (PHReg)
Hypothesis: Conditional on cost growth, technology readiness risk, and flagship class, an element's ordinal sequencing position is associated with the hazard of reaching launch (the speed of development); H0 is that the coefficient on seq_pos is zero.
Headline result: flagship = -1.7842 (p = 0.1948)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | campaign_line | seq_pos | dev_months | cost_growth_pct | new_tech | flagship | launched | source
Mars Pathfinder | mars_surface | 1 | 46 | 0 | 4 | 0 | 1 | NASA/JPL Mars Pathfinder press kit (1996); launch 1996-12-04; Discovery-era baseline
Mars Global Surveyor | mars_orbiter | 1 | 30 | 0 | 1 | 0 | 1 | NASA Mars Global Surveyor fact sheet; launch 1996-11-07; rapid Mars Surveyor Program element
Mars Odyssey | mars_orbiter | 2 | 40 | 5 | 1 | 0 | 1 | NASA/JPL 2001 Mars Odyssey press kit; launch 2001-04-07; post-1999-failure rebaseline
Mars Exploration Rover | mars_surface | 2 | 38 | 8 | 6 | 0 | 1 | NASA/JPL MER press kit (2003); launch 2003-06/07; airbag EDL heritage from Pathfinder
Mars Reconnaissance Orbiter | mars_orbiter | 3 | 52 | 4 | 3 | 0 | 1 | NASA/JPL MRO press kit (2005); launch 2005-08-12; HiRISE new instrument
Phoenix | mars_surface | 3 | 44 | 6 | 4 | 0 | 1 | NASA/JPL Phoenix press kit (2007); launch 2007-08-04; Mars Scout, reused 2001 lander hardware
Mars Science Laboratory | mars_surface | 4 | 84 | 82 | 8 | 1 | 1 | GAO-11-364SP; NASA MSL; confirmed 2006, launch slipped 2009 to 2011-11-26; dev cost ~1.6B to ~2.5B
MAVEN | mars_orbiter | 4 | 42 | 0 | 2 | 0 | 1 | NASA/JPL MAVEN press kit (2013); launch 2013-11-18; on-baseline Mars Scout follow-on
InSight | mars_surface | 5 | 66 | 22 | 3 | 0 | 1 | GAO-16-309SP; NASA InSight; SEIS leak slipped launch 2016 to 2018-05-05; ~26-month slip
Mars 2020 Perseverance | mars_surface | 6 | 90 | 3 | 7 | 1 | 1 | GAO-20-405; NASA Mars 2020 press kit; confirmed 2016, launch 2020-07-30; sample caching new tech
Mars Sample Return segment | mars_sample_return | 7 | 80 | 60 | 9 | 1 | 0 | NASA MSR replan (SpacePolicyOnline 2024); Muirhead et al. Acta Astronautica 176 (2020); in replan, not launched [illustrative dev-month projection]
NEAR Shoemaker | smallbody | 1 | 32 | 0 | 2 | 0 | 1 | NASA NEAR press kit; first Discovery mission; launch 1996-02-17
Stardust | smallbody | 2 | 40 | 0 | 3 | 0 | 1 | NASA/JPL Stardust press kit; launch 1999-02-07; aerogel sample capture new tech
Genesis | smallbody | 3 | 46 | 12 | 4 | 0 | 1 | NASA/JPL Genesis press kit; launch 2001-08-08; solar-wind collector
Deep Impact | smallbody | 4 | 42 | 15 | 4 | 0 | 1 | NASA/JPL Deep Impact press kit; launch 2005-01-12; impactor new tech
Dawn | smallbody | 5 | 72 | 20 | 5 | 0 | 1 | GAO-08-1051; NASA Dawn; ion propulsion, cancelled-and-reinstated, launch 2007-09-27
OSIRIS-REx | smallbody | 6 | 60 | 0 | 5 | 0 | 1 | NASA/JPL/GSFC OSIRIS-REx press kit; New Frontiers; launch 2016-09-08; TAGSAM on baseline
Lucy | smallbody | 7 | 54 | 5 | 3 | 0 | 1 | NASA Lucy press kit; Discovery; launch 2021-10-16; near-baseline
Psyche | smallbody | 8 | 81 | 20 | 4 | 0 | 1 | JPL IRB report (2022); confirmed 2017-01, launch slipped 2022 to 2023-10-13; software/staffing slip
DART | smallbody | 9 | 48 | 4 | 4 | 0 | 1 | NASA/APL DART press kit; launch 2021-11-24; planetary-defense demo near baseline
Juno | outer | 1 | 60 | 0 | 3 | 0 | 1 | NASA/JPL Juno press kit; New Frontiers; launch 2011-08-05; near baseline
New Horizons | outer | 1 | 50 | 0 | 3 | 0 | 1 | NASA/APL New Horizons press kit; New Frontiers; launch 2006-01-19; fast development
Cassini | outer | 1 | 96 | 18 | 7 | 1 | 1 | NASA/JPL Cassini-Huygens; flagship; launch 1997-10-15; long flagship development
Galileo | outer | 1 | 108 | 40 | 6 | 1 | 1 | NASA/JPL Galileo; flagship; Challenger-driven slip to 1989-10-18; large schedule/cost growth
Europa Clipper | outer | 2 | 72 | 18 | 6 | 1 | 1 | SpacePolicyOnline; Planetary Society Europa Clipper cost chart; ABC 4.25B to 5B (2022); launch 2024-10-14
Europa Lander concept | outer | 3 | 84 | 40 | 8 | 1 | 0 | NASA Europa Lander pre-Phase-A concept studies; not confirmed/launched as of 2026 [illustrative dev-month projection]
GRAIL | moon | 1 | 40 | 0 | 2 | 0 | 1 | NASA/JPL GRAIL press kit; Discovery; launch 2011-09-10; on baseline
Lunar Reconnaissance Orbiter | moon | 1 | 44 | 10 | 3 | 0 | 1 | NASA/GSFC LRO press kit; launch 2009-06-18; modest growth
LADEE | moon | 2 | 38 | 0 | 2 | 0 | 1 | NASA/Ames LADEE press kit; launch 2013-09-06; modular bus on baseline
VIPER | moon | 3 | 60 | 30 | 5 | 0 | 0 | GAO-24-106767; NASA VIPER; CLPS rover restructured/cancelled before delivery (2024); ~30% growth pre-cancellation

## Construction
Variable | Definition | Construction / source
dev_months | Duration in months from project confirmation (KDP-C / agency baseline commitment) to actual or current target launch; the survival time to the launch event | GAO Annual Assessments of NASA Major Projects; NASA/JPL mission press kits; mission confirmation and launch records
launched | Event indicator: 1 if the element completed development and launched (event observed); 0 if still in development, replan, or cancelled before delivery (right-censored) as of mid-2026 | NASA mission status; SpacePolicyOnline 2024 MSR replan; GAO-24-106767 (VIPER)
seq_pos | Ordinal position of the element in the committed acquisition sequence of its campaign line (orbiter, surface, small-body, outer, moon, sample-return) | Coded from campaign architecture history; Muirhead et al. Acta Astronautica 176 (2020) for the Mars sample-return chain
cost_growth_pct | Development cost growth over the element baseline, in percent | GAO Annual Assessments; Planetary Society Europa Clipper cost chart; JPL Psyche IRB report (2022)
new_tech | Count of new or mission-critical technologies the element had to mature, a readiness-risk proxy | NASA/JPL press kits and mission technology descriptions; parametric readiness logic per Friz et al. Acta Astronautica 166 (2019)
flagship | Indicator: 1 if the element is flagship-class (largest cost tier), 0 otherwise | NASA mission-class designation; GAO major-project tiering

## Results
Term | Coefficient | Std. error | z | p-value | 95% CI low | 95% CI high | Hazard ratio
seq_pos | -0.1132 | 0.0984 | -1.15 | 0.2501 | -0.3062 | 0.0797 | 0.893
cost_growth_pct | -0.0333 | 0.0228 | -1.4603 | 0.1442 | -0.078 | 0.0114 | 0.9672
new_tech | -0.4382 | 0.2589 | -1.6929 | 0.0905 | -0.9456 | 0.0692 | 0.6452
flagship | -1.7842 | 1.3763 | -1.2964 | 0.1948 | -4.4817 | 0.9133 | 0.1679

## Fit statistics
Statistic | Value
N | 30
events | 27