## README
COLLEGIUM empirical evidence workbook
Schedule Slip as the Proximate Driver of Cost Growth in NASA Major Projects: A Cross-Sectional Test of the Cost-Schedule Coupling
Candidate: Theodore Nair (1B-ITI-058)
Method: OLS (robust HC1 SE)
Hypothesis: Conditional on program scale and crewed status, a longer schedule slip is associated with larger life-cycle cost growth across NASA major projects; the coefficient on schedule_slip_mo is positive and statistically distinguishable from zero.
Headline result: crewed = -29.9211 (p = 0.0377)
This workbook is fully auditable. The Data sheet lists every input observation with its source. The Construction sheet defines each variable. The Results sheet is the estimator output (coefficients, standard errors, test statistics, p-values, confidence intervals, N, fit). Any number in the paper or dissertation can be traced here.

## Data
project | cost_growth_pct | schedule_slip_mo | baseline_lcc_musd | ln_baseline_lcc | crewed | source
CCP (SpaceX) | 5.26 | 43 | 2599 | 7.8629 | 1 | GAO-22-105212 Table 9 (p.130)
SGSS | 127.37 | 48 | 493.9 | 6.2023 | 0 | GAO-22-105212 Table 9 (p.130)
Landsat 9 | -15.65 | -2 | 885 | 6.7856 | 0 | GAO-22-105212 Table 9 (p.130)
Lucy | 0.82 | -1 | 981.1 | 6.8887 | 0 | GAO-22-105212 Table 9 (p.130)
DART | 5.32 | -3 | 313.9 | 5.7491 | 0 | GAO-22-105212 Table 9 (p.130)
JWST | 98.8 | 90 | 4963.6 | 8.5099 | 0 | GAO-22-105212 Table 9 (p.130)
LCRD | 21.62 | 25 | 262.7 | 5.571 | 0 | GAO-22-105212 Table 9 (p.130)
EGS | 26.82 | 41 | 2812.9 | 7.942 | 1 | GAO-22-105212 Table 9 (p.130)
SLS | 29.99 | 41 | 9064 | 9.1121 | 1 | GAO-22-105212 Table 9 (p.130)
Psyche | -3.09 | 0 | 996.4 | 6.9041 | 0 | GAO-22-105212 Table 9 (p.130)
LBFD | 19.68 | 11 | 582.4 | 6.3672 | 0 | GAO-22-105212 Table 9 (p.130)
SWOT | 8.94 | 14 | 754.9 | 6.6266 | 0 | GAO-22-105212 Table 9 (p.130)
NISAR | 12.03 | 12 | 866.9 | 6.7649 | 0 | GAO-22-105212 Table 9 (p.130)
VIPER | 0 | 0 | 433.5 | 6.0719 | 0 | GAO-22-105212 Table 9 (p.130)
Orion | 22.4 | 13 | 11283.5 | 9.3311 | 1 | GAO-22-105212 Table 9 (p.130)
PACE | 8.35 | 4 | 889.7 | 6.7909 | 0 | GAO-22-105212 Table 9 (p.130)
Europa Clipper | 17.65 | -11 | 4250 | 8.3547 | 0 | GAO-22-105212 Table 9 (p.130)
SPHEREx | 0 | 0 | 451.4 | 6.1124 | 0 | GAO-22-105212 Table 9 (p.130)
OSAM-1 | 8.21 | 0 | 1780 | 7.4844 | 0 | GAO-22-105212 Table 9 (p.130)
Roman | 9.7 | 7 | 3934.4 | 8.2775 | 0 | GAO-22-105212 project summary (p.113)

## Construction
Variable | Definition | Construction / source
cost_growth_pct | Life-cycle cost growth in percent, computed as (current life-cycle cost estimate minus original baseline life-cycle cost estimate) divided by the original baseline, times 100 | Derived from GAO-22-105212 Table 9 (p.130) current and original baseline life-cycle cost estimates; Roman from GAO-22-105212 project summary (p.113)
schedule_slip_mo | Schedule slip in months, the count of calendar months between the original baseline launch-readiness date and the current launch-readiness date (negative where a project pulled its date earlier) | Computed from GAO-22-105212 Table 9 (p.130) original and current launch-readiness dates; 'Spring' coded as April per GAO convention
ln_baseline_lcc | Natural logarithm of the original baseline life-cycle cost estimate in millions of dollars, a proxy for program scale | GAO-22-105212 Table 9 (p.130) original baseline life-cycle cost column
crewed | Indicator equal to one for human-spaceflight programs (Commercial Crew, Exploration Ground Systems, Space Launch System, Orion) and zero otherwise | GAO-22-105212 project classifications; programs supporting crewed Artemis or ISS transportation

## Results
Term | Coefficient | Std. error | t | p-value | 95% CI low | 95% CI high
const | -11.8308 | 42.9606 | -0.2754 | 0.783 | -96.0321 | 72.3705
schedule_slip_mo | 1.1928 | 0.3454 | 3.4534 | 0.0005536 | 0.5159 | 1.8698
ln_baseline_lcc | 2.5363 | 6.3124 | 0.4018 | 0.6878 | -9.8357 | 14.9084
crewed | -29.9211 | 14.3986 | -2.0781 | 0.0377 | -58.1418 | -1.7004

## Fit statistics
Statistic | Value
N | 20
R2 | 0.6666
R2_adj | 0.6041
F | 9.3172
F_p | 0.0008466